## All Sites
| Martinsburg 613 | Date Tested | Version | Tomah 676 | Date Tested | Version | Dublin 557 | Date Tested | Version | Orlando 675 | Date Tested | Version
TS2 - Match COB Data to Payer Sequence - Skipped - Production Only | P | 2019-02-07 | 35 | P | 2019-02-08 | 35 | P | 2019-03-12 | 36 | P | 2019-02-27 | 35
TS3 - Match COB Data to Payer Sequence - Resubmit - Production Only | P | 2019-02-07 | 35 | P | 2019-02-08 | 35 | P | 2019-03-12 | 36 | P | 2019-02-26 | 35
TS4 - Transmitting SNF Claims with Revenue Codes - Production Only | P | 2019-02-11 | 35 | P | 2019-02-07 | 35 | P | 2019-03-15 | 36 | Not Tested (Couldn't find claims that met the the prerequisites)
TS5 - RCB Header Displays T for Test Claims - Production Only | P | 2019-02-07 | 35 | P | 2019-02-08 | 35 | P | 2019-03-15 | 36 | P | 2019-02-26 | 35
TS6 - Removal of EDI-Transmit option NO | P | 2019-02-07 | 35 | P | 2019-02-25 | 35 | P | 2019-03-12 | 36 | P | 2019-03-14 | 36
TS7 - Non-MCCF Pay-to Address Rate Types - Editing | P | 2019-02-07 | 35 | P | 2019-03-12 | 36 | P | 2019-02-28 | 35 | P | 2019-02-21 | 35
TS8 - Non-MCCF Pay-to Address Rate Types - CMS1500 | P | 2019-02-07 | 35 | P | 2019-03-12 | 36 | P | 2019-02-28 | 35 | P | 2019-02-21 | 35
TS9 - Non-MCCF Pay-to Address Rate Types - UB04 | P | 2019-02-07 | 35 | P | 2019-03-12 | 36 | P | 2019-02-28 | 35 | P | 2019-02-21 | 35
TS10 -Non-MCCF Pay-to Address Rate Types - J430D | P | 2019-02-07 | 35 | N/A | N/A | N/A | P | 2019-02-28 | 35 | P | 2019-03-19 | 36
TS11 - Regenerate Unbilled Amounts Reports | P | 2019-02-07 | 35 | P | 2019-03-12 | 36 | P | 2019-02-21 | 35 | P | 2019-02-26 | 35
TS18 - Remove Fatal Error | P | 2019-02-07 | 35 | P | 2019-03-12 | 36 | P | 2019-02-21 | 35 | P | 2019-02-26 | 35
TS17 - CMN Using No at the Prompt | P | 2019-02-07 | 35 | P | 2019-02-25 | 35 | P | 2019-02-21 | 35 | P | 2019-03-18 | 36
TS12 - CMN Oxygen and E&P Nutrition - Editing Procedure - Development Only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TS13 - CMN Oxygen - Development Only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TS14 - CMN Enteral and Parenteral Nutrition - Enteral - Development Only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TS15 - CMN Enteral and Parenteral Nutrition - Parenteral - Development Only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TS16 - CMN Enteral and Parenteral Nutrition - Both - Development Only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TS1 - Claims Tracking Indicator of Recorded Coded - Development Only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IB592-TS10 - Insurance Co Editor (1) | P | 2019-03-15 | 36 | P | 2019-02-08 | 35 | P | 2019-02-21 | 35 | P | 2019-02-26 | 35
IB592-TS11 - Insurance Co Editor (2) | P | 2019-03-15 | 36 | P | 2019-02-08 | 35 | P | 2019-02-21 | 35 | P | 2019-02-26 | 35
IB592-TS12 - Dental Payer ID/Dental Address | P | 2019-03-15 | 36 | P | 2019-02-08 | 35 | P | 2019-02-21 | 35 | P | 2019-02-21 | 35
IB592-TS13 - No Dental Payer ID/No Dental Address | P | 2019-03-15 | 36 | P | 2019-02-08 | 35 | P | 2019-02-21 | 35 | P | 2019-02-21 | 35
IB621-TS1 - eInsurance TAS Insurance Co Enter/Edit - Payer Linking | P | 2019-03-12 | 36 | P | 2019-02-08 | 35 | P | 2019-03-12 | 36 | P | 2019-02-19 | 35
V33 installed date | 2018-11-28 |  |  | 2018-12-10 |  |  | 2018-12-10 |  |  | 2018-12-10
V34 installed date | Skipped |  |  | Skipped |  |  | Skipped |  |  | Skipped
V35 installed date | 2019-02-06 |  |  | 2019-02-07 |  |  | 2019-02-12 |  |  | 2019-02-12
V36 installed date | 2019-03-06 |  |  | 2019-03-06 |  |  | 2019-03-06 |  |  | 2019-03-06