## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 2 IB*2.0*577 Defect Log
September 2017
Version 2.0

## Revision History
Revision History
Date | Version | Description | Author
May 2017 | 0.1 | Draft version | Lisa Bruno
July 2017 | 1 | Draft version edits | Lisa Bruno
September 2017 | 2 | Draft final version | Jane Balchunas

## Defect Log
Defect ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
DE48 | NA | SQA - Error found in TC318: SQA eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Development only) | 2 - High | Closed | 3/23/2017 Found in IB*2.0*577_ T0 | US114: Cloning a Primary Claim (USEB-500) | TC318: SQA eBilling TS11 COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | 4/6/2017 Fixed in IB*2.0*577_T1
DE64 | NA | SQA Error found: in US114: TS9 COB Data in CLON'd Claims | 2 - High | Closed | 4/6/2017 Found in IB*2.0*576_T6 | US114: Cloning a Primary Claim (USEB-500) | TC317: SQA eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | 4/6/2017 Fixed in IB*2.0*577_T1
DE79 | NA | SQA Error found in TC599: TS14 P&C Number Truncated in 837-P | 3 - Medium | Closed | 5/3/2017 Found in IB*2.0*577_T3 | US127: Field Length Adjustments (TSEB-1) | TC599: SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | 5/10/2017 Fixed in IB*2.0*577_T4
DE80 | NA | SQA Error found in TC605: TS19 Code Set Not Correct | 3 - Medium | Closed | 5/3/2017 Found in IB*2.0*577_T4 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 5/10/2017 Fixed in IB*2.0*577_T5
DE81 | NA | SQA Error found in TC605: TS19 Unit or Basis for Measurement Code Not Transmitted | 3 - Medium | Closed | 5/10/2017 Found in IB*2.0*577_T4 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 5/10/2017 Fixed in IB*2.0*577_T6
DE82 | NA | SQA Error found in TC605: TS19 – Unit or Basis for Measurement Code Not on CMS1500 | 3 - Medium | Closed | 5/3/2017 Found in IB*2.0*577_T4 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 5/10/2017 Fixed in IB*2.0*577_T6
DE83 | NA | SQA Error found in TC606: TS20 – Qualifers Not Printing UB04 FL43 | 3 - Medium | Closed | 5/4/2017 Found in IB*2.0*577_T4 | US1166: Print NDC Number on UB04 | TC606: : SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | 5/10/2017 Fixed in IB*2.0*577_T6
DE84 | NA | SQA Error found in TC606: TS20 – Decimal Transmitting in INS | 3 - Medium | Closed | 5/4/2017 Found in IB*2.0*577_T4 | US1166: Print NDC Number on UB04 | TC606: SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | 5/10/2017 Fixed in IB*2.0*577_T6
DE85 | NA | CIT Error Found: Low issue on NDC .75 amount on CMS1500 and UB04 in CIT - US 127 | 4 - Low | Closed | 5/8/2017 Found in IB*2.0*577_T6 | US127: Field Length Adjustments (TSEB-1) | TC621: CIT eBilling TS13 – Lab or Service Facility Field Lengths US 127 | 5/9/2017 Fixed in IB*2.0*577_T7
DE86 | NA | SQA Error found in TC595: SQA TS13 – CLIA Number Not Moved to SUB2 | 2 - High | Closed | 5/9/2017 Found in IB*2.0*577_T7 | US127: Field Length Adjustments (TSEB-1) | TC595: SQA eBilling TS13 – Lab or Service Facility Field Lengths - US127 | 5/9/2017 Fixed in IB*2.0*577_T8
DE129 | NA | HCCH Payer ID Report - Incorrect Date | 3 - Medium | Closed | 6/5/2017 Found in IB*2.0*577_T5 | US976: Payer ID Report | TC805: SQA eBilling TS25 Payer ID Report - US976 | 6/7/2017 Fixed in IB*2.0*577_T6
DE152 | NA | Error found in TC805: Display More than Payer Address Line 1 | 3 - Medium | Closed | 6/13/2017 Found in IB*2.0*577_T9 | US976: Payer ID Report | TC805: SQA eBilling TS25 Payer ID Report - US976 | 6/14/2017 Fixed in IB*2.0*577_T10
DE197 | NA | UAT - TS19 PRF Piece 23 Missing | 2 - High | Closed | 6/26/2017 Found in IB*2.0*576_T10 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | TC 629: CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 6/27/2017 Fixed in IB*2.0*577_T11
DE211 | NA | New field not added to IBCCC2_Duplicate Error Message | 3 - Medium | Closed | 7/20/2017 Found in IB*2.0*577_T11 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 8/30/2017 Fixed in IB*2.0*577_T12
DE233 | NA | Warranty - eBilling IB*576 - Hyphen no longer displays on ZIP with 9 digit code | 3 - Medium | Closed | 8/16/2017 Found in IB*2.0*576_T10 | US15: Payer Zip Code Field Adjustment (USEB-1) | TC355: SQA eBilling TAS US15 Payer Zip Code - TS8 | 8/30/2017 Fixed in IB*2.0*577_T13