## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eInsurance Build 2 IB*2.0*577 Requirements Traceability Matrix
October 2017
Version 4.0

## Revision History
Revision History
Date | Version | Description | Author
July 2017 | 0.1 | Draft version | Lisa Bruno
July 2017 | 1 | Edits needed | Lisa Bruno
September 2017 | 2 | Draft final version | Jane Balchunas
October 2017 | 3 | Final version | Jane Balchunas
October 2017 | 4 | Fixed date on DE211 | Jane Balchunas

## RTM
Bus Req Doc | Epic ID | Epic Summary | Req Doc | User Story ID | User Story Summary | Testable | Accptance Criteria (for Not Testable US) | Release to be Implemented | Build | Test Case ID (for Testable US) | Pass/Fail/Not Tested | Build Last Tested | Comments Failed US- Defect ID Not Testable Comment, Not Tested Comment
US114: Cloning a Primary Claim (USEB-500)
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC297 - SQA eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC298 - CIT eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC301 - SQA eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC303 - SQA eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC304 - SQA eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC306 - SQA eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC308 - SQA eBilling TS8 COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC313 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Medicare) - Prof - TS21 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC314 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Medicare) - Inst - TS22 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC317 - SQA eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC318 - SQA eBilling TS11 COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | Pass | IB*2.0*577_T13 | DE48
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC415 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Developmnt only) | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC573: SQA eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC574: SQA eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC599: SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC600: SQA eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC602: SQA eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC603 - SQA eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC604 - SQA eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC607 - CIT eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC610 - SQA eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC611 - CIT eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC612 - CIT eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC613: CIT eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 Regression | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC614 - CIT eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC615 - CIT eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC616 - CIT eBilling TS8 - COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC617 - CIT eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | Pass | IB*2.0*577_T13 | DE64
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC618 - CIT eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC619 - CIT eBilling TS11 - COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US114 | US114: Cloning a Primary Claim (USEB-500) | Yes | NA | IB*2.0*577 | 2 | TC1160 - SQA eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | Pass | IB*2.0*577_T13 | NA
US127: Field Length Adjustments (TSEB-1)
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC594 - SQA eBilling TS12 – Ambulance Field Lengths - US 127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC595 - SQA eBilling TS13 – Lab or Service Facility Field Lengths - US127 | Pass | IB*2.0*577_T13 | DE86
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC596 - SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths - US 127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC599 - SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | Pass | IB*2.0*577_T13 | DE79
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC600 - SQA eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC602 - SQA eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC603 - SQA eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC604 - SQA eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC620 - CIT eBilling TS12 – Ambulance Field Lengths - US 127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC621 - CIT eBilling TS13 – Lab or Service Facility Field Lengths US 127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC622 - CIT eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC623 - CIT eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC624 - CIT eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC625 - CIT eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US127 | US127: Field Length Adjustments (TSEB-1) | Yes | NA | IB*2.0*577 | 2 | TC628 - CIT eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | Pass | IB*2.0*577_T13 | NA
US129: Process Payer ID - Store HCCH Payer ID (TSEB-2)
NA | US1187 | EPIC - Update eBilling Functionality | NA | US129 | US129: Process Payer ID - Store HCCH Payer ID (TSEB-2) | Yes | NA | IB*2.0*577 | 2 | TC800 - SQA eBilling TS21 Store Payer IDs (Prof) - US129 | Pass | IB*2.0*577_T13 | NA
NA | US1187 | EPIC - Update eBilling Functionality | NA | US129 | US129: Process Payer ID - Store HCCH Payer ID (TSEB-2) | Yes | NA | IB*2.0*577 | 2 | TC801 - SQA eBilling TS22 Store Payer IDs (Prof) - US129 | Pass | IB*2.0*577_T13 | NA
NA | US1187 | EPIC - Update eBilling Functionality | NA | US129 | US129: Process Payer ID - Store HCCH Payer ID (TSEB-2) | Yes | NA | IB*2.0*577 | 2 | TC803 - SQA eBilling TS23 Store Payer IDs (Inst) - US129 | Pass | IB*2.0*577_T13 | NA
NA | US1187 | EPIC - Update eBilling Functionality | NA | US129 | US129: Process Payer ID - Store HCCH Payer ID (TSEB-2) | Yes | NA | IB*2.0*577 | 2 | TC804 - SQA eBilling TS24 Store Payer IDs (Inst) - US129 | Pass | IB*2.0*577_T13 | NA
NA | US1187 | EPIC - Update eBilling Functionality | NA | US129 | US129: Process Payer ID - Store HCCH Payer ID (TSEB-2) | Yes | NA | IB*2.0*577 | 2 | TC807 - CIT eBilling TS21 Store Payer IDs (Prof) - US129 | Pass | IB*2.0*577_T13 | NA
NA | US1187 | EPIC - Update eBilling Functionality | NA | US129 | US129: Process Payer ID - Store HCCH Payer ID (TSEB-2) | Yes | NA | IB*2.0*577 | 2 | TC808 - CIT eBilling TS22 Store Payer IDs (Prof) - US129 | Pass | IB*2.0*577_T13 | NA
NA | US1187 | EPIC - Update eBilling Functionality | NA | US129 | US129: Process Payer ID - Store HCCH Payer ID (TSEB-2) | Yes | NA | IB*2.0*577 | 2 | TC811 - CIT eBilling TS24 Store Payer IDs (Inst) - US129 | Pass | IB*2.0*577_T13 | NA
NA | US1187 | EPIC - Update eBilling Functionality | NA | US129 | US129: Process Payer ID - Store HCCH Payer ID (TSEB-2) | Yes | NA | IB*2.0*577 | 2 | TC812 - CIT eBilling TS23 Store Payer IDs (Inst) - US129 | Pass | IB*2.0*577_T13 | NA
US11: Unit or Basis for Measurements Codes for Drugs (USEB-15)
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US11 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | Yes | NA | IB*2.0*577 | 2 | TC605 - SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | Pass | IB*2.0*577_T13 | DE80
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US11 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | Yes | NA | IB*2.0*577 | 2 | TC605 - SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | Pass | IB*2.0*577_T13 | DE211 - Warranty Defect
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US11 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | Yes | NA | IB*2.0*577 | 2 | TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | Pass | IB*2.0*577_T13 | DE81
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US11 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | Yes | NA | IB*2.0*577 | 2 | TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | Pass | IB*2.0*577_T13 | DE85
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US11 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | Yes | NA | IB*2.0*577 | 2 | TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | Pass | IB*2.0*577_T13 | DE197 UAT
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US11 | US11: Unit or Basis for Measurements Codes for Drugs (USEB-15) | Yes | NA | IB*2.0*577 | 2 | TC630 - CIT eBilling TS20 – Unit or Basis for Measurements Code (Inst) US11 | Pass | IB*2.0*577_T13 | DE82
US976: Payer ID Report
NA | US1187 | EPIC - Update eBilling Functionality | NA | US976 | US976: Payer ID Report | Yes | NA | IB*2.0*577 | 2 | TC805 - SQA eBilling TS25 Payer ID Report - US976 | Pass | IB*2.0*577_T13 | DE129
NA | US1187 | EPIC - Update eBilling Functionality | NA | US976 | US976: Payer ID Report | Yes | NA | IB*2.0*577 | 2 | TC810 - CIT eBilling TS25 Payer ID Report - US976 | Pass | IB*2.0*577_T13 | DE152
US1166: Print NDC Number on UB04
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US1166 | US1166: Print NDC Number on UB04 | Yes | NA | IB*2.0*577 | 2 | TC606 - SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | Pass | IB*2.0*577_T13 | DE83
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US1166 | US1166: Print NDC Number on UB04 | Yes | NA | IB*2.0*577 | 2 | TC606 - SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) | Pass | IB*2.0*577_T13 | DE84
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US1166 | US1166: Print NDC Number on UB04 | Yes | NA | IB*2.0*577 | 2 | TC742 - SQA eBilling - TS20b – Unit or Basis for Measurements Code (Inst) US1166 | Pass | IB*2.0*577_T13 | NA
NA | US1168 | EPIC - Maintain eBilling Compliance | NA | US1166 | US1166: Print NDC Number on UB04 | Yes | NA | IB*2.0*577 | 2 | TC743 - CIT eBilling - TS20b – Unit or Basis for Measurements Code (Inst) US1166 | Pass | IB*2.0*577_T13 | NA