## Slide 1
Medical Care Collections Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite Phase 1 Health Administrative Product Enhancements (HAPE)
Critical Decision Point 2
Pilot Build
12/16/2016
Notes: CD 2 Briefing is to request Approval to Deploy a specific product or Build.
As you move through the slides, provide the level of information appropriate for this decision briefing and for the specific capabilities being deployed as a result of this briefing. Do not focus on past increments or older project history unless it is directly relevant to the deployment decision you are seeking for this briefing.
When going through this presentation, please do not read the slides, draw the senior leaders attention to any questions or issues that you have. Please present this template at a high level.

## Slide 2: Project Information
Full Project Name: | Medical Care Collections Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite Phase 1
OI&T Portfolio Name: | Health Administrative Product Enhancements (HAPE)
OI&T Program Name: | Medical Care Collection Fund (MCCF)
OIT Project Manager Name: | Curtis Cota-Robles
OI&T Program Manager Name: | Toby Rudik
OI&T Portfolio Manager Name: | Chris Minardi
Account Manager: | Alan Constantian
Product Owner: | Ruth-Ann Phelps, PhD
Receiving / Sustainment Organization: | Health Product Support
Project ID: | VIPR # V16-00159-000
Release Agent: | Wayne Ledford
ISO: | Randy Jackson
VA Exhibit 300 Name: | Medical Legacy
OIT Budget Operating Plan Number: | 16-MED-273;
Enterprise Project Structure Number: | FY17-08-03-02-05-01-004; FY16-01-02-03-20-11-009
Notes: If you had a different EPS number in a previous Fiscal Year please list the previous EPS number and current EPS number.

## Slide 3: Purpose
Curtis Cota-Robles for Medical Care Collection Fund Electronic Data Interchange (EDI) Transaction Applications Suite Phase is requesting VIP Critical Decision 2 Approval to deploy VistA patch PRCA*4.5*317 to IOC production. The patch has completed CIT testing.
The project is using the IOC model.
Notes: This slide should identify the project name, nature of the CD2 request (IOC evaluation or full release) and a statement that the project has competed the requirements to request deployment.

## Slide 4: Release(s)
Release Name | Start Date | End Date | Resources Needed in order to Deploy | Resources Assigned to Deployment | Total number of sites to which this Build is deploying
Medical Care Collection Fund (MCCF) eBilling Compliance Phase 3 (IB*2*547) | 8/31/2016 | 11/30/2016 | 1 | 1 | All VistA locations
Medical Care Collection Fund (MCCF) eBilling Compliance Phase 3 (IB*2*574) | 12/1/2016 | 2/6/2017 | 1 | 1 | All VistA locations
What is the capability being deployed into the production environment? This is a patch to patch IB*2.0*547. It corrects a reported issue. End Users reported that they are not able to enter a professional alternate payer ID on Bill Screen 10 when the charge type is institutional and the form type is a CMS-1500. This patch modifies screen 10 screening logic to be consistent; Screen 10 will now use form-type instead of charge type.
Notes: Release Name: The title of the Release Name.
Start Date: Date planned to start Release.
End Date: Date planned to complete Release.
Resources Needed: Required manpower to complete the Release.
Resources Assigned: Manpower that is assigned to the Release.
Site Count: Total number of sites you are deploying to.

## Slide 5: Release Dependencies
      Are there any concerns with your dependencies that will keep the project from deploying? No known dependencies.
Release Dependency | Description | Status of Dependency | Notes or Concerns (availability, funding, resources, etc)
NONE |  |  | 
Notes: List the current project or product deployment dependencies—these can be technical, h/w, s/w resources, training, schedule-- or any level or type of deployment dependency.
Provide information on all projects that have a dependency related to the success of this project and all projects upon which this project depends.
Upstream dependencies: other projects that impact the success of the projects under review. This includes deliverables, software, hardware, or infrastructure components' that another project will be providing the project under review.
Downstream dependencies: other projects that are impacted the success of the projects under review. This includes deliverables, software, hardware, or infrastructure components' that this project will provide other projects.

## Slide 6: CD 2 Checklist
Requirements | Yes | No | Notes
Is all applicable data and documentation entered into the Rational Tool Suite? | X |  | https://clm.rational.oit.va.gov/jts/dashboards/6205
Does the Release Team recommend release into IOC / Production? | X |  | Recommend release to IOC Production
Are all hardware or software contracts and licenses documented and ready to transfer to the appropriate support entity? |  | X | N/A VistA Maintenance
What is the status of your Section 508 Compliance? If you have a waiver when does it expire? | X |  | There is a 508 Exception for this project. http://tspr.vista.med.va.gov/warboard/ProjectDocs/MCCF_eBilling_Compliance_Phase3/MCCF%20Program%20FY15%20508%20Exception%20Request-signed.pdf
Are there outstanding security issues? If so, what is the remediation plan? Security Impact Assessment (SIA) complete? |  | X | No.
Notes: List the status of the documentation. VIP artifacts should be stored in RTC (for PD projects) or the standard repository for the organization (i.e., Workload Resource Tracking (WRT) for SDE projects).
POLARIS entries driven by the Veterans Focused Integration Process (VIP), may first be submitted at any time after Critical Decision #2, with the goal of meeting the two-to-four week request. This occurs during the Release Preparation phase of VIP. Final review occurs at the semi-weekly calendar meetings, in the week prior to the scheduled release.
It is suggested that a POLARIS entry be conducted as early as possible.

## Slide 7: CD 2 Checklist
Requirements | Yes | No | Notes
Does you project have any open Severity 1 or 2 Defects? |  | X | .
Did you address all of the high and critical findings in Risk Vision? |  | X | N/A
Pick one of the 3 scenarios: Using a system with an existing ATO & do not need to modify it Using a system with an existing ATO & had to modify the ATO Created a new ATO | X |  | Using a system with an existing ATO & do not need to modify it
Notes: List the status of the documentation. VIP artifacts should be stored in RTC (for PD projects) or the standard repository for the organization (i.e., Workload Resource Tracking (WRT) for SDE projects).

## Slide 8: CD 2 Decision
Decision | Yes | No | Comments
Portfolio Manager approves the product to deploy into IOC/ Production or National Release |  |  | 
Product Owner approves the product to deploy into IOC/ Production or National Release |  |  | 
Receiving / Sustainment Organization approves the product to deploy into IOC/ Production or National Release |  |  | 
Notes: Fill out this slide after the decision is made during your CD Event.