## RTM eBilling Build 1
RTM (Requirements Traceability Matrix) MCCF EDI TAS eBilling Build 1
US1 Onset Date Of Current Illness or Symptoms (USEB-11) - ( Plan Estimate:3 ) - Accepted
Task ID - Name | State | Defect ID - Name | State | Test ID - Name | State
TA28 - Code/Unit Test User Story | Completed | DE23 - Error found in TC296: SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 4 TS6 | Closed | TC221 - CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 2 TS4 | Pass
TA29 - Create CIT Scripts for User Story | Completed |  |  | TC224 - CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 4 TS6 | Pass
TA30 - Perform CIT Test | Completed |  |  | TC288 - SQA eBilling TAS US1 Test Case - Date of Onset Printed | Pass
TA2265 - Create SQA Scripts for User Story | Completed |  |  | TC289 - SQA eBilling TAS US1 Test Case - Date of Onset Printed - TS2 | Pass
TA2266 - Perform SQA Test | Completed |  |  | TC291 - SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 1 - TS3 | Pass
|  |  |  | TC293 - SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 2 TS4 | Pass
|  |  |  | TC294 - SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 3 TS5 | Pass
|  |  |  | TC296 - SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 4 TS6 | Pass
|  |  |  | TC386 - CIT eBilling TAS US1 Test Case - Onset Date - Fatal Error - TS24 | Pass
|  |  |  | TC387 - SQA eBilling TAS US1 Test Case - Onset Date - Fatal Error - TS24 | Pass
|  |  |  | TC215 - CIT eBilling TAS US1 Test Case - Date of Onset Printed | Pass
|  |  |  | TC216 - CIT eBilling TAS US1 Test Case - Date of Onset Printed - TS2 | Pass
|  |  |  | TC217 - CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 1 - TS3 | Pass
|  |  |  | TC222 - CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 3 TS5 | Pass
US15 Payer Zip Code Field Adjustment (USEB-1) - ( Plan Estimate:3 ) - Accepted
Task ID - Name | State | Defect ID - Name | State | Test ID - Name | State
TA40 - Code/Unit Test User Story | Completed | DE45 - Error found in TC348: CIT eBilling TAS US15 Payer Zip Code - TS7 | Closed | TC348 - CIT eBilling TAS US15 Payer Zip Code - TS7 | Pass
TA41 - Create CIT Scripts for User Story | Completed |  |  | TC349 - CIT eBilling TAS US15 Payer Zip Code - TS8 | Pass
TA42 - Perform CIT Test | Completed |  |  | TC350 - CIT eBilling TAS US15 Payer Zip Code - TS9 | Pass
TA2269 - Create SQA Scripts for User Story | Completed |  |  | TC354 - SQA eBilling TAS US15 Payer Zip Code - TS7 | Pass
TA2270 - Perform SQA Test | Completed |  |  | TC355 - SQA eBilling TAS US15 Payer Zip Code - TS8 | Pass
|  |  |  | TC356 - SQA eBilling TAS US15 Payer Zip Code - TS9 | Pass
US12 Printing of CMS 1500 (USEB-12) - ( Plan Estimate:2 ) - Accepted
Task ID - Name | State | Defect ID - Name | State | Test ID - Name | State
TA1278 - Code/Unit Test User Story | Completed | DE 25- TC363: CIT eBilling TAS US12 Print CMS Form/Replacement - TS11 | Closed | TC363 - CIT eBilling TAS US12 Print CMS Form/Replacement - TS11 | Pass
TA1279 - Create CIT Scripts for User Story | Completed |  |  | TC364 - SQA eBilling TAS US12 Print CMS Form/Replacement - TS11 | Pass
TA1280 - Perform CIT Test | Completed |  |  | TC365 - CIT eBilling TAS US12 Print CMS Form/Replacement - TS12 | Pass
TA2271 - Create SQA Scripts for User Story | Completed |  |  | TC366 - SQA eBilling TAS US12 Print CMS Form/Replacement - TS12 | Pass
TA2272 - Perform SQA Test | Completed
US8 Missing MRW Legend Indicator (USEB-13) - ( Plan Estimate:1 ) - Accepted
Task ID - Name | State | Defect ID - Name | State | Test ID - Name | State
TA50 - Code/Unit Test User Story | Completed |  |  | TC351 - CIT eBilling TAS US8 MRW Legend - TS10 | Pass
TA51 - Create CIT Scripts for User Story | Completed
TA52 - Perform CIT Test | Completed
TA2273 - Create SQA Scripts for User Story | Completed
TA2274 - Perform SQA Test | Completed