## Defect Log
MCCF EDI TAS eBilling Build 1 Defect Log
Defect ID | Name | Requirement | Reported By | Severity | Priority | State | Found In | Fixed In | Resolution
DE23 | SQA - Error found in TC296: SQA eBilling TAS US1 Test Case - Date of Onset Printed Regresstion Test 4 TS6 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 3 - Minor Problem | 2 - High Attention | Closed | IB*2.0*576 T3 | IB*2.0*576 T4 | Code Modification
DE25 | CIT - Error found in TC363: CIT eBilling TAS US12 Print CMS Form/Replacement - TS11 | US12: Printing of CMS 1500 (USEB-12) | Melanie Windsor | 2 - Major Problem | 3 - Normal | Closed | IB*2.0*576 T3 | IB*2.0*576 T4 | Code Modification
DE45 | CIT - Error found in TC348: CIT eBilling TAS US15 Payer Zip Code - TS7 | US15: Payer Zip Code Field Adjustment (USEB-1) | Melanie Windsor | 3 - Minor Problem | 3 - Normal | Closed | IB*2.0*576 T5 | IB*2.0*576 T6 | Code Modification
DE46 | CIT - Error found in TC415: CIT eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Developmnt only) | N/A - not asscoiated with a Requirement | Melanie Windsor | 3 - Minor Problem | 3 - Normal | Closed | IB*2.0*576 T5 | IB*2.0*576 T6 | Code Modification
DE48 | SQA - Error found in TC318: SQA eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Developmnt only) | US114: Cloning a Primary Claim (USEB-500) | Mary Simons | 2 - Major Problem | 1 - Resolve Immediately | Closed | IB*2*576 T6 | Deferred to future build | Deferred to future build
DE64 | SQA - Error found in US114: SQA eBilling TAS US114 COB Data in CLON'd Claims | US114: Cloning a Primary Claim (USEB-500) | Mary Simons | 2 - Major Problem | 2 - High Attention | Closed | IB*2*576 T6 | Deferred to future build | Deferred to future build