## IB_2_0_576 Execution Log.csv
MCCF EDI TAS Billing Build 1 Test Execution Log
Test Case ID | Name | Requirement/User Story | Owner | Date Executed | Pass/ Fail | Build Id / Patch # | Defect ID | Regression
TC215 | CIT eBilling TAS US1 Test Case - Date of Onset Printed | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-02-22 | Pass | IB*2.0*576 T1
TC215 | CIT eBilling TAS US1 Test Case - Date of Onset Printed | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-01 | Pass | IB*2.0*576 T2
TC215 | CIT eBilling TAS US1 Test Case - Date of Onset Printed | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-30 | Pass | IB*2.0*576 T10 |  | R
TC216 | CIT eBilling TAS US1 Test Case - Date of Onset Printed - TS2 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-02-22 | Pass | IB*2.0*576 T1
TC216 | CIT eBilling TAS US1 Test Case - Date of Onset Printed - TS2 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-01 | Pass | IB*2.0*576 T2
TC216 | CIT eBilling TAS US1 Test Case - Date of Onset Printed - TS2 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-04-03 | Pass | IB*2.0*576 T10 |  | R
TC217 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 1 - TS3 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-02-23 | Pass | IB*2.0*576 T1
TC217 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 1 - TS3 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-01 | Pass | IB*2.0*576 T2
TC217 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 1 - TS3 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-04-03 | Pass | IB*2.0*576 T10 |  | R
TC221 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 2 TS4 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-02-23 | Pass | IB*2.0*576 T1
TC221 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 2 TS4 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-01 | Pass | IB*2.0*576 T2
TC221 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 2 TS4 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-30 | Pass | IB*2.0*576 T10 |  | R
TC222 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 3 TS5 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-02-23 | Pass | IB*2.0*576 T1
TC222 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 3 TS5 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-01 | Pass | IB*2.0*576 T2
TC222 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 3 TS5 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-04-03 | Pass | IB*2.0*576 T10 |  | R
TC224 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 4 TS6 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-02-23 | Pass | IB*2.0*576 T1
TC224 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 4 TS6 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-01 | Pass | IB*2.0*576 T2
TC224 | CIT eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 4 TS6 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-04-03 | Pass | IB*2.0*576 T10 |  | R
TC348 | CIT eBilling TAS US15 Payer Zip Code - TS7 | US15: Payer Zip Code Field Adjustment (USEB-1) | Melanie Windsor | 2017-03-08 | Pass | IB*2.0*576 T3
TC348 | CIT eBilling TAS US15 Payer Zip Code - TS7 | US15: Payer Zip Code Field Adjustment (USEB-1) | Melanie Windsor | 2017-03-22 | Fail | IB*2.0*576 T5 | DE45
TC348 | CIT eBilling TAS US15 Payer Zip Code - TS7 | US15: Payer Zip Code Field Adjustment (USEB-1) | Melanie Windsor | 2017-03-23 | Pass | IB*2.0*576 T6
TC348 | CIT eBilling TAS US15 Payer Zip Code - TS7 | US15: Payer Zip Code Field Adjustment (USEB-1) | Melanie Windsor | 2017-03-30 | Pass | IB*2.0*576 T10 |  | R
TC349 | CIT eBilling TAS US15 Payer Zip Code - TS8 | US15: Payer Zip Code Field Adjustment (USEB-1) | Melanie Windsor | 2017-03-08 | Pass | IB*2.0*576 T3
TC349 | CIT eBilling TAS US15 Payer Zip Code - TS8 | US15: Payer Zip Code Field Adjustment (USEB-1) | Melanie Windsor | 2017-03-30 | Pass | IB*2.0*576 T10 |  | R
TC350 | CIT eBilling TAS US15 Payer Zip Code - TS9 | US15: Payer Zip Code Field Adjustment (USEB-1) | Melanie Windsor | 2017-03-08 | Pass | IB*2.0*576 T3
TC350 | CIT eBilling TAS US15 Payer Zip Code - TS9 | US15: Payer Zip Code Field Adjustment (USEB-1) | Melanie Windsor | 2017-03-31 | Pass | IB*2.0*576 T10 |  | R
TC351 | CIT eBilling TAS US8 MRW Legend - TS10 | US670: US8 (Parent) Missing MRW Legend Indicator | Melanie Windsor | 2017-03-08 | Pass | IB*2.0*576 T3
TC351 | CIT eBilling TAS US8 MRW Legend - TS10 | US670: US8 (Parent) Missing MRW Legend Indicator | Melanie Windsor | 2017-03-30 | Pass | IB*2.0*576 T10 |  | R
TC363 | CIT eBilling TAS US12 Print CMS Form/Replacement - TS11 | US12: Printing of CMS 1500 (USEB-12) | Melanie Windsor | 2017-03-09 | Fail | IB*2.0*576 T3 | DE25
TC363 | CIT eBilling TAS US12 Print CMS Form/Replacement - TS11 | US12: Printing of CMS 1500 (USEB-12) | Melanie Windsor | 2017-03-13 | Pass | IB*2.0*576 T4
TC363 | CIT eBilling TAS US12 Print CMS Form/Replacement - TS11 | US12: Printing of CMS 1500 (USEB-12) | Melanie Windsor | 2017-04-03 | Pass | IB*2.0*576 T10 |  | R
TC365 | CIT eBilling TAS US12 Print CMS Form/Replacement - TS12 | US12: Printing of CMS 1500 (USEB-12) | Melanie Windsor | 2017-03-13 | Pass | IB*2.0*576 T4
TC365 | CIT eBilling TAS US12 Print CMS Form/Replacement - TS12 | US12: Printing of CMS 1500 (USEB-12) | Melanie Windsor | 2017-04-03 | Pass | IB*2.0*576 T10 |  | R
TC386 | CIT eBilling TAS US1 Test Case - Onset Date - Fatal Error - TS24 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-02-22 | Pass | IB*2.0*576 T1
TC386 | CIT eBilling TAS US1 Test Case - Onset Date - Fatal Error - TS24 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-01 | Pass | IB*2.0*576 T2
TC386 | CIT eBilling TAS US1 Test Case - Onset Date - Fatal Error - TS24 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-08 | Pass | IB*2.0*576 T3
TC386 | CIT eBilling TAS US1 Test Case - Onset Date - Fatal Error - TS24 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Melanie Windsor | 2017-03-30 | Pass | IB*2.0*576 T10 |  | R
TC288 | SQA eBilling TAS US1 Test Case - Date of Onset Printed | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-03-16 | Pass | IB*2.0*576 T4
TC288 | SQA eBilling TAS US1 Test Case - Date of Onset Printed | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC289 | SQA eBilling TAS US1 Test Case - Date of Onset Printed - TS2 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-03-15 | Pass | IB*2.0*576 T3
TC289 | SQA eBilling TAS US1 Test Case - Date of Onset Printed - TS2 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC291 | SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 1 - TS3 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-03-15 | Pass | IB*2.0*576 T3
TC291 | SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 1 - TS3 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC293 | SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 2 TS4 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-03-15 | Pass | IB*2.0*576 T3
TC293 | SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 2 TS4 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC294 | SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 3 TS5 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-03-15 | Pass | IB*2.0*576 T3
TC294 | SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 3 TS5 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC296 | SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 4 TS6 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-02-28 | Fail | IB*2.0*576 T3 | DE23
TC296 | SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 4 TS6 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-03-13 | Pass | IB*2.0*576 T4
TC296 | SQA eBilling TAS US1 Test Case - Date of Onset Printed Regression Test 4 TS6 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC318 | SQA eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Development only) | US114: Cloning a Primary Claim (USEB-500) | Mary Simons | 2017-03-22 | Fail | IB*2.0*576 T5 | DE48 ( Deferred to later build)
TC318 | SQA eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Development only) | US114: Cloning a Primary Claim (USEB-500) | Mary Simons | 2017-03-23 | Fail | IB*2.0*576 T5 | DE48 ( Deferred to later build) | R
TC354 | SQA eBilling TAS US15 Payer Zip Code - TS7 | US15: Payer Zip Code Field Adjustment (USEB-1) | Mary Simons | 2017-03-16 | Pass | IB*2.0*576 T4
TC354 | SQA eBilling TAS US15 Payer Zip Code - TS7 | US15: Payer Zip Code Field Adjustment (USEB-1) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC355 | SQA eBilling TAS US15 Payer Zip Code - TS8 | US15: Payer Zip Code Field Adjustment (USEB-1) | Mary Simons | 2017-03-16 | Pass | IB*2.0*576 T4
TC355 | SQA eBilling TAS US15 Payer Zip Code - TS8 | US15: Payer Zip Code Field Adjustment (USEB-1) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC356 | SQA eBilling TAS US15 Payer Zip Code - TS9 | US15: Payer Zip Code Field Adjustment (USEB-1) | Mary Simons | 2017-03-16 | Pass | IB*2.0*576 T4
TC356 | SQA eBilling TAS US15 Payer Zip Code - TS9 | US15: Payer Zip Code Field Adjustment (USEB-1) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC357 | SQA eBilling TAS US8 MRW Legend - TS10 | US670: US8 (Parent) Missing MRW Legend Indicator | Mary Simons | 2017-03-16 | Pass | IB*2.0*576 T4
TC357 | SQA eBilling TAS US8 MRW Legend - TS10 | US670: US8 (Parent) Missing MRW Legend Indicator | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC364 | SQA eBilling TAS US12 Print CMS Form/Replacement - TS11 | US12: Printing of CMS 1500 (USEB-12) | Mary Simons | 2017-03-16 | Pass | IB*2.0*576 T3
TC364 | SQA eBilling TAS US12 Print CMS Form/Replacement - TS11 | US12: Printing of CMS 1500 (USEB-12) | Mary Simons | 2017-03-16 | Fail | IB*2.0*576 T3 | Not related to current enhancements, Only printing 17 Characters instead of the 18 allowed by the NUCC Guide
TC364 | SQA eBilling TAS US12 Print CMS Form/Replacement - TS11 | US12: Printing of CMS 1500 (USEB-12) | Mary Simons | 2017-03-16 | Pass | IB*2.0*576 T4
TC364 | SQA eBilling TAS US12 Print CMS Form/Replacement - TS11 | US12: Printing of CMS 1500 (USEB-12) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC366 | SQA eBilling TAS US12 Print CMS Form/Replacement - TS12 | US12: Printing of CMS 1500 (USEB-12) | Mary Simons | 2017-03-16 | Pass | IB*2.0*576 T4
TC366 | SQA eBilling TAS US12 Print CMS Form/Replacement - TS12 | US12: Printing of CMS 1500 (USEB-12) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R
TC387 | SQA eBilling TAS US1 Test Case - Onset Date - Fatal Error - TS24 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-03-15 | Pass | IB*2.0*576 T3
TC387 | SQA eBilling TAS US1 Test Case - Onset Date - Fatal Error - TS24 | US1: Onset Date Of Current Illness or Symptoms (USEB-11) | Mary Simons | 2017-04-05 | Pass | IB*2.0*576 T10 |  | R