## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 5 and Build 6 IB*2.0*608 Test Execution Log
October 2018
Version 3.0

## Revision History
Revision History
Date | Version | Description | Author
April 2018 | 1 | Initial Version for MOU review | Jane Balchunas
June 2018 | 2 | Initial Version for IOC review | Jane Balchunas
October 2018 | 3 | Removed TC1260 | Jane Balchunas

## Test Execution Log
Test Case ID | Build 5 & 6 | Build Exectued | Date Executed | Tested By | Test Results (P/F) | Defect ID (Failed Tests)
TC2179: CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | 5&6 | IB*2.0*608_T1 | 2018-01-09 | Jane Balchunas | Fail | DE463
TC2179: CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | 5&6 | IB*2.0*608_T1 | 2018-01-09 | Jane Balchunas | Fail | DE464
TC2179: CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | 5&6 | IB*2.0*608_T3 | 2018-01-16 | Jane Balchunas | Pass | NA
TC2179: CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | 5&6 | IB*2.0*608_T9 | 2018-02-22 | Jane Balchunas | Pass | NA
TC2179: CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | 5&6 | IB*2.0*608_T27 | 2018-05-14 | Jane Balchunas | Pass | NA
TC2179: CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | 5&6 | IB*2.0*608_T29 | 2018-05-22 | Jane Balchunas | Pass | NA
TC2179: CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | 5&6 | IB*2.0*608_T30 | 2018-05-23 | Jane Balchunas | Pass | NA
TC2179: CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | Jane Balchunas | Pass | NA
TC2180: CIT eBilling TS1 - RCB Header Displays T for Test Claims – Printed Claims US1908 | 5&6 | IB*2.0*608_T1 | 2018-01-09 | Jane Balchunas | Pass | NA
TC2180: CIT eBilling TS1 - RCB Header Displays T for Test Claims – Printed Claims US1908 | 5&6 | IB*2.0*608_T3 | 2018-01-17 | Jane Balchunas | Pass | NA
TC2180: CIT eBilling TS1 - RCB Header Displays T for Test Claims – Printed Claims US1908 | 5&6 | IB*2.0*608_T9 | 2018-02-22 | Jane Balchunas | Pass | NA
TC2180: CIT eBilling TS1 - RCB Header Displays T for Test Claims – Printed Claims US1908 | 5&6 | IB*2.0*608_T27 | 2018-05-14 | Jane Balchunas | Pass | NA
TC2180: CIT eBilling TS1 - RCB Header Displays T for Test Claims – Printed Claims US1908 | 5&6 | IB*2.0*608_T29 | 2018-05-22 | Jane Balchunas | Pass | NA
TC2180: CIT eBilling TS1 - RCB Header Displays T for Test Claims – Printed Claims US1908 | 5&6 | IB*2.0*608_T30 | 2018-05-23 | Jane Balchunas | Pass | NA
TC2180: CIT eBilling TS1 - RCB Header Displays T for Test Claims – Printed Claims US1908 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | Jane Balchunas | Pass | NA
TC2229: CIT eBilling TS2 - RCB Legend Displays Explanation for T – Report US1908 - Regression | 5&6 | IB*2.0*608_T11 | 2018-03-14 | Jane Balchunas | Pass | NA
TC2229: CIT eBilling TS2 - RCB Legend Displays Explanation for T – Report US1908 - Regression | 5&6 | IB*2.0*608_T27 | 2018-05-15 | Jane Balchunas | Pass | NA
TC2229: CIT eBilling TS2 - RCB Legend Displays Explanation for T – Report US1908 - Regression | 5&6 | IB*2.0*608_T29 | 2018-05-22 | Jane Balchunas | Pass | NA
TC2229: CIT eBilling TS2 - RCB Legend Displays Explanation for T – Report US1908 - Regression | 5&6 | IB*2.0*608_T30 | 2018-05-23 | Jane Balchunas | Pass | NA
TC2229: CIT eBilling TS2 - RCB Legend Displays Explanation for T – Report US1908 - Regression | 5&6 | IB*2.0*608_T31 | 2018-05-24 | Jane Balchunas | Pass | NA
TC2233: CIT eBilling TS1 - Re-generate Unbilled Amounts Reports to Sort by Non-MCCF or MCCF Claim Types US142 | 5&6 | IB*2.0*608_T4 | 2018-01-30 | Jane Balchunas | Fail | DE487
TC2233: CIT eBilling TS1 - Re-generate Unbilled Amounts Reports to Sort by Non-MCCF or MCCF Claim Types US142 | 5&6 | IB*2.0*608_T5 | 2018-02-02 | Jane Balchunas | Pass | NA
TC2233: CIT eBilling TS1 - Re-generate Unbilled Amounts Reports to Sort by Non-MCCF or MCCF Claim Types US142 | 5&6 | IB*2.0*608_T8 | 2018-02-21 | Jane Balchunas | Fail | DE527
TC2233: CIT eBilling TS1 - Re-generate Unbilled Amounts Reports to Sort by Non-MCCF or MCCF Claim Types US142 | 5&6 | IB*2.0*608_T8 | 2018-02-21 | Jane Balchunas | Fail | DE528
TC2233: CIT eBilling TS1 - Re-generate Unbilled Amounts Reports to Sort by Non-MCCF or MCCF Claim Types US142 | 5&6 | IB*2.0*608_T8 | 2018-02-21 | Jane Balchunas | Fail | DE530
TC2233: CIT eBilling TS1 - Re-generate Unbilled Amounts Reports to Sort by Non-MCCF or MCCF Claim Types US142 | 5&6 | IB*2.0*608_T10 | 2018-03-04 | Jane Balchunas | Pass | NA
TC2233: CIT eBilling TS1 - Re-generate Unbilled Amounts Reports to Sort by Non-MCCF or MCCF Claim Types US142 | 5&6 | IB*2.0*608_T27 | 2018-05-15 | Jane Balchunas | Fail | DE748
TC2233: CIT eBilling TS1 - Re-generate Unbilled Amounts Reports to Sort by Non-MCCF or MCCF Claim Types US142 | 5&6 | IB*2.0*608_T30 | 2018-05-23 | Jane Balchunas | Pass | NA
TC2233: CIT eBilling TS1 - Re-generate Unbilled Amounts Reports to Sort by Non-MCCF or MCCF Claim Types US142 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | Jane Balchunas | Pass | NA
TC2234: CIT eBilling TS2 – Re-generate Unbilled Amounts Reports to Sort by Both MCCF and Non-MCCF Claims US142_Regression | 5&6 | IB*2.0*608_T11 | 2018-03-12 | Jane Balchunas | Pass | NA
TC2234: CIT eBilling TS2 – Re-generate Unbilled Amounts Reports to Sort by Both MCCF and Non-MCCF Claims US142_Regression | 5&6 | IB*2.0*608_T30 | 2018-05-23 | Jane Balchunas | Pass | NA
TC2234: CIT eBilling TS2 – Re-generate Unbilled Amounts Reports to Sort by Both MCCF and Non-MCCF Claims US142_Regression | 5&6 | IB*2.0*608_T31 | 2018-05-24 | Jane Balchunas | Pass | NA
TC2236: CIT eBilling TS1 Removal of EDI-Transmit option NO US1909_Regression | 5&6 | IB*2.0*608_T11 | 2018-03-12 | Jane Balchunas | Pass | NA
TC2236: CIT eBilling TS1 Removal of EDI-Transmit option NO US1909_Regression | 5&6 | IB*2.0*608_T13 | 2018-03-27 | Jane Balchunas | Pass | NA
TC2236: CIT eBilling TS1 Removal of EDI-Transmit option NO US1909_Regression | 5&6 | IB*2.0*608_T27 | 2018-05-15 | Jane Balchunas | Pass | NA
TC2236: CIT eBilling TS1 Removal of EDI-Transmit option NO US1909_Regression | 5&6 | IB*2.0*608_T29 | 2018-05-22 | Jane Balchunas | Pass | NA
TC2236: CIT eBilling TS1 Removal of EDI-Transmit option NO US1909_Regression | 5&6 | IB*2.0*608_T30 | 2018-05-23 | Jane Balchunas | Pass | NA
TC2236: CIT eBilling TS1 Removal of EDI-Transmit option NO US1909_Regression | 5&6 | IB*2.0*608_T31 | 2018-05-24 | Jane Balchunas | Pass | NA
TC2432: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 5&6 | IB*2.0*608_T6 | 2018-02-11 | Jane Balchunas | Fail | DE502
TC2432: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 5&6 | IB*2.0*608_T7 | 2018-02-12 | Jane Balchunas | Pass | NA
TC2432: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 5&6 | IB*2.0*608_T7 | 2018-02-13 | Jane Balchunas | Fail | DE503
TC2432: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 5&6 | IB*2.0*608_T8 | 2018-02-15 | Jane Balchunas | Pass | NA
TC2432: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 5&6 | IB*2.0*608_T7 | 2018-02-14 | Jane Balchunas | Fail | DE509
TC2432: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 5&6 | IB*2.0*608_T8 | 2018-02-15 | Jane Balchunas | Pass | NA
TC2432: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 5&6 | IB*2.0*608_T29 | 2018-05-22 | Jane Balchunas | Pass | NA
TC2432: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | Jane Balchunas | Pass | NA
TC2510: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214_Regression | 5&6 | IB*2.0*608_T9 | 2018-02-22 | Jane Balchunas | Pass | NA
TC2510: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214_Regression | 5&6 | IB*2.0*608_T11 | 2018-03-15 | Jane Balchunas | Pass | NA
TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 | 5&6 | IB*2.0*608_T7 | 2018-02-09 | CJ Minch | Fail | DE526
TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 | 5&6 | IB*2.0*608_T8 | 2018-02-20 | CJ Minch | Pass | NA
TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 | 5&6 | IB*2.0*608_T11 | 2018-03-15 | CJ Minch | Pass | NA
TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | CJ Minch | Pass | NA
TC2620: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 | 5&6 | IB*2.0*608_T9 | 2018-02-23 | CJ Minch | Fail | DE536
TC2620: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 | 5&6 | IB*2.0*608_T10 | 2018-03-04 | CJ Minch | Pass | NA
TC2620: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 | 5&6 | IB*2.0*608_T11 | 2018-03-08 | CJ Minch | Fail | DE570
TC2620: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 | 5&6 | IB*2.0*608_T11 | 2018-03-08 | CJ Minch | Fail | DE572
TC2620: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 | 5&6 | IB*2.0*608_T12 | 2018-03-14 | CJ Minch | Pass | NA
TC2620: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | CJ Minch | Pass | NA
TC2621: CIT - 6.2 Non-MCCF Pay-to Address Rate Types – CMS1500 US2599 | 5&6 | IB*2.0*608_T11 | 2018-03-08 | CJ Minch | Pass | NA
TC2621: CIT - 6.2 Non-MCCF Pay-to Address Rate Types – CMS1500 US2599 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | CJ Minch | Pass | NA
TC2622: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – UB04 - US2599 | 5&6 | IB*2.0*608_T9 | 2018-02-23 | CJ Minch | Fail | DE535
TC2622: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – UB04 - US2599 | 5&6 | IB*2.0*608_T10 | 2018-03-04 | CJ Minch | Pass | NA
TC2622: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – UB04 - US2599 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | CJ Minch | Pass | NA
TC2623: CIT - Non-MCCF Pay-to Address Rate Types – J430D - US2599 | 5&6 | IB*2.0*608_T9 | 2018-02-26 | CJ Minch | Fail | DE537
TC2623: CIT - Non-MCCF Pay-to Address Rate Types – J430D - US2599 | 5&6 | IB*2.0*608_T10 | 2018-03-07 | CJ Minch | Pass | NA
TC2623: CIT - Non-MCCF Pay-to Address Rate Types – J430D - US2599 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | CJ Minch | Pass | NA
TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral - US3 | 5&6 | IB*2.0*608_T15 | 2018-04-10 | CJ Minch | Fail | DE633
TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral - US3 | 5&6 | IB*2.0*608_T16 | 2018-04-12 | CJ Minch | Pass | NA
TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral - US3 | 5&6 | IB*2.0*608_T19 | 2018-04-23 | CJ Minch | Fail | DE667
TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral - US3 | 5&6 | IB*2.0*608_T20 | 2018-04-23 | CJ Minch | Pass | NA
TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral - US3 | 5&6 | IB*2.0*608_T20 | 2018-04-26 | CJ Minch | Fail | DE674
TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral - US3 | 5&6 | IB*2.0*608_T20 | 2018-04-26 | CJ Minch | Fail | DE675
TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral - US3 | 5&6 | IB*2.0*608_T20 | 2018-04-26 | CJ Minch | Fail | DE678
TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral - US3 | 5&6 | IB*2.0*608_T22 | 2018-04-27 | CJ Minch | Pass | NA
TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral - US3 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | CJ Minch | Pass | NA
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T10 | 2018-03-07 | CJ Minch | Fail | DE560
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T11 | 2018-03-11 | CJ Minch | Pass | NA
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T10 | 2018-03-07 | CJ Minch | Fail | DE565
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T12 | 2018-03-14 | CJ Minch | Pass | NA
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T12 | 2018-03-14 | CJ Minch | Fail | DE589
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T13 | 2018-03-27 | CJ Minch | Pass | NA
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T12 | 2018-03-20 | CJ Minch | Fail | DE603
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T13 | 2018-03-28 | CJ Minch | Pass | NA
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T12 | 2018-03-21 | CJ Minch | Fail | DE607
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T13 | 2018-03-27 | CJ Minch | Pass | NA
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T13 | 2018-03-28 | CJ Minch | Fail | DE619
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T14 | 2018-04-05 | CJ Minch | Pass | NA
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T14 | 2018-04-09 | CJ Minch | Fail | DE631
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T15 | 2018-04-12 | CJ Minch | Pass | NA
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T26 | 2018-05-03 | CJ Minch | Fail | DE683
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T26 | 2018-05-08 | CJ Minch | Fail | DE698
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T27 | 2018-05-10 | CJ Minch | Pass | NA
TC2764: CIT-CMN Oxygen - US3 | 5&6 | IB*2.0*608_T31 | 2018-05-24 | CJ Minch | Pass | NA
TC2789: CIT eBilling TAS US2486-TS3 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev only_Regression | 5&6 | IB*2.0*608_T27 | 2018-05-15 | Jane Balchunas | Pass | NA
TC2789: CIT eBilling TAS US2486-TS3 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev only_Regression | 5&6 | IB*2.0*608_T29 | 2018-05-22 | Jane Balchunas | Pass | NA
TC2789: CIT eBilling TAS US2486-TS3 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev only_Regression | 5&6 | IB*2.0*608_T30 | 2018-05-23 | Jane Balchunas | Pass | NA
TC2789: CIT eBilling TAS US2486-TS3 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev only_Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | Jane Balchunas | Pass | NA
TC2790: eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | 5&6 | IB*2.0*608_T13 | 2018-04-03 | Jane Balchunas | Fail | DE624
TC2790: eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | 5&6 | IB*2.0*608_T14 | 2018-04-04 | Jane Balchunas | Pass | NA
TC2790: eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | 5&6 | IB*2.0*608_T14 | 2018-04-05 | Jane Balchunas | Fail | DE630
TC2790: eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | 5&6 | IB*2.0*608_T15 | 2018-04-09 | Jane Balchunas | Pass | NA
TC2790: eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | 5&6 | IB*2.0*608_T15 | 2018-04-11 | Jane Balchunas | Fail | DE638
TC2790: eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | 5&6 | IB*2.0*608_T16 | 2018-04-13 | Jane Balchunas | Pass | NA
TC2790: eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | 5&6 | IB*2.0*608_T31 | 2018-05-30 | Jane Balchunas | Pass | NA
TC2791: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message - US2486 | 5&6 | IB*2.0*608_T13 | 2018-03-29 | Jane Balchunas | Fail | DE618
TC2791: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message - US2486 | 5&6 | IB*2.0*608_T14 | 2018-04-09 | Jane Balchunas | Pass | NA
TC2791: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message - US2486 | 5&6 | IB*2.0*608_T18 | 2018-04-19 | Jane Balchunas | Fail | DE659
TC2791: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message - US2486 | 5&6 | IB*2.0*608_T19 | 2018-04-23 | Jane Balchunas | Pass | NA
TC2791: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message - US2486 | 5&6 | IB*2.0*608_T20 | 2018-04-30 | Jane Balchunas | Fail | DE681
TC2791: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message - US2486 | 5&6 | IB*2.0*608_T21 | 2018-05-01 | Jane Balchunas | Pass | NA
TC2791: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message - US2486 | 5&6 | IB*2.0*608_T31 | 2018-05-29 | Jane Balchunas | Pass | NA
TC2792: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message_Regression | 5&6 | IB*2.0*608_T27 | 2018-05-15 | Jane Balchunas | Pass | NA
TC2792: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message_Regression | 5&6 | IB*2.0*608_T29 | 2018-05-22 | Jane Balchunas | Pass | NA
TC2792: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message_Regression | 5&6 | IB*2.0*608_T30 | 2018-05-23 | Jane Balchunas | Pass | NA
TC2792: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message_Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | Jane Balchunas | Pass | NA
TC2895: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 Regression | 5&6 | IB*2.0*608_T8 | 2018-02-16 | CJ Minch | Pass | NA
TC2895: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA
TC2896: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 Regression | 5&6 | IB*2.0*608_T10 | 2018-03-12 | CJ Minch | Pass | NA
TC2896: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA
TC2897: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – UB04 - US2599 Regression | 5&6 | IB*2.0*608_T10 | 2018-03-30 | CJ Minch | Pass | NA
TC2897: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – UB04 - US2599 Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA
TC2898: CIT - CMN Enteral and Parenteral Nutrition Both_Regression | 5&6 | IB*2.0*608_T27 | 2018-05-15 | CJ Minch | Pass | NA
TC2898: CIT - CMN Enteral and Parenteral Nutrition Both_Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA
TC2901: CIT - 6.2 Non-MCCF Pay-to Address Rate Types – CMS1500 Regression | 5&6 | IB*2.0*608_T10 | 2018-03-13 | CJ Minch | Pass | NA
TC2901: CIT - 6.2 Non-MCCF Pay-to Address Rate Types – CMS1500 Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA
TC2904: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Parenteral | 5&6 | IB*2.0*608_T26 | 2018-05-07 | CJ Minch | Pass | NA
TC2904: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Parenteral | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA
TC2905: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Both | 5&6 | IB*2.0*608_T26 | 2018-05-07 | CJ Minch | Fail | DE682
TC2905: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Both | 5&6 | IB*2.0*608_T27 | 2018-05-10 | CJ Minch | Pass | NA
TC2905: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Both | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA
TC2906: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Parenteral - Regression | 5&6 | IB*2.0*608_T27 | 2018-05-30 | CJ Minch | Pass | NA
TC2906: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Parenteral - Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA
TC2925: CIT - Non-MCCF Pay-to Address Rate Types – J430D - US2599_Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA
TC2927: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral_Regression | 5&6 | IB*2.0*608_T26 | 2018-05-07 | CJ Minch | Pass | NA
TC2927: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral_Regression | 5&6 | IB*2.0*608_T27 | 2018-05-30 | CJ Minch | Pass | NA
TC2927: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral_Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA
TC2928: CIT -CMN Oxgyen_Regression | 5&6 | IB*2.0*608_T31 | 2018-05-29 | CJ Minch | Pass | NA