## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 3 and Build 4 IB*3.0&4.0*592 Requirements Traceability Matrix
December 2017
Version 3.0

## Revision History
Revision History
Date | Version | Description | Author
November 2017 | 1 | Initial Draft Version for review | Jane Balchunas
November 2017 | 2 | Deleted Section 8 for US2503 and Sections 5.5 through 5.9 for US2487, per eBiz changing the functionality of Blds. 3&4 to only send the NPI for Dental transactions. | Jane Balchunas
December 2017 | 3 | Updated with results of final build testing. | Jane Balchunas

## RTM
Bus Req Doc | Epic ID | Epic Summary | Req Doc | User Story ID | User Story Summary | Testable | Accptance Criteria (for Not Testable US) | Release to be Implemented | Build(s) | Test Case ID (for Testable US0 | Pass/Fail/Not Tested | Build Last Tested | Comments Failed US- Defect ID Not Testable Comment, Not Tested Comment
US 14 - TPJI Indicator (USEB-14)
N/A | US1187 | Epic - Update eBilling functionality | N/A | US14 - TPJI Indicator (USEB-14) | As a staff member at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able see a dental claim indicator within Third Party Joint Inquiry (TPJI) when I view the Active and/or Inactive list of claim entries. | Yes | N/A | IB*2.0*592 | 3&4 | TC1221 - CIT eBilling TS9 Validate the new ‘Dental’ claim indicator displays on the TPJI screen when there is an Active Outpatient Dental Claim (O/D). US14 | Pass | IB*2.0*592_T10 | N/A
N/A | US1187 | Epic - Update eBilling functionality | N/A | US14 - TPJI Indicator (USEB-14) | As a staff member at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able see a dental claim indicator within Third Party Joint Inquiry (TPJI) when I view the Active and/or Inactive list of claim entries. | Yes | N/A | IB*2.0*592 | 3&4 | TC1222 - CIT eBilling TS9 TPJI_Dental Indicator US14 | Pass | IB*2.0*592_T10 | N/A
US 1108/US131 - Enter/Edit Dental Claims
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC - created for 2017 eBilling Maintain Compliance stories and activities | N/A | US 1108 - Enter/Edit Dental Claims US 131 - Create 837D Transaction | US1108 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim transaction compliant with the X12n 00501-X224 Health Care claim: Dental (837) standard to the HCCH for submission to third party payers. US131 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim compliant with the X12n 00501-X224 Health Care claim: Dental (837D) standard to the HCCH for submission to third party payers. | Yes | N/A | IB*2.0*592 | 3&4 | TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | Pass | IB*2.0*592_T10 | DE269, DE292, DE293, DE336, DE338, DE350, DE351, DE359, DE365, DE374, DE379, DE381
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC - created for 2017 eBilling Maintain Compliance stories and activities | N/A | US 1108 - Enter/Edit Dental Claims US 131 - Create 837D Transaction | US1108 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim transaction compliant with the X12n 00501-X224 Health Care claim: Dental (837) standard to the HCCH for submission to third party payers. US131 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim compliant with the X12n 00501-X224 Health Care claim: Dental (837D) standard to the HCCH for submission to third party payers. | Yes | N/A | IB*2.0*592 | 3&4 | TC1250 - CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | Pass | IB*2.0*592_T10 | DE295, DE296, DE357
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC - created for 2017 eBilling Maintain Compliance stories and activities | N/A | US 1108 - Enter/Edit Dental Claims US 131 - Create 837D Transaction | US1108 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim transaction compliant with the X12n 00501-X224 Health Care claim: Dental (837) standard to the HCCH for submission to third party payers. US131 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim compliant with the X12n 00501-X224 Health Care claim: Dental (837D) standard to the HCCH for submission to third party payers. | Yes | N/A | IB*2.0*592 | 3&4 | TC1251 - CIT eBilling TS4 Fatal Error Rend/AsstSurg - US1108 and US131 | Pass | IB*2.0*592_T10 | DE294
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC - created for 2017 eBilling Maintain Compliance stories and activities | N/A | US 1108 - Enter/Edit Dental Claims US 131 - Create 837D Transaction | US1108 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim transaction compliant with the X12n 00501-X224 Health Care claim: Dental (837) standard to the HCCH for submission to third party payers. US131 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim compliant with the X12n 00501-X224 Health Care claim: Dental (837D) standard to the HCCH for submission to third party payers. | Yes | N/A | IB*2.0*592 | 3&4 | TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | Pass | IB*2.0*592_T10 | DE304, DE305, DE314, DE358, DE363, DE373, DE380, DE411
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC - created for 2017 eBilling Maintain Compliance stories and activities | N/A | US 1108 - Enter/Edit Dental Claims US 131 - Create 837D Transaction | US1108 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim transaction compliant with the X12n 00501-X224 Health Care claim: Dental (837) standard to the HCCH for submission to third party payers. US131 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim compliant with the X12n 00501-X224 Health Care claim: Dental (837D) standard to the HCCH for submission to third party payers. | Yes | N/A | IB*2.0*592 | 3&4 | TC1258 - CIT eBilling TS5 Medicare Error for Dental US1108 and US131 | Pass | IB*2.0*592_T10 | N/A
NA | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US 1108 - Enter/Edit Dental Claims US 131 - Create 837D Transaction | US1108 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim transaction compliant with the X12n 00501-X224 Health Care claim: Dental (837) standard to the HCCH for submission to third party payers. US131 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim compliant with the X12n 00501-X224 Health Care claim: Dental (837D) standard to the HCCH for submission to third party payers. | Yes | N/A | IB*2.0*592 | 3&4 | TC1260 - CIT eBilling TS8 Complete Dental Claim US1108 and US131 | Pass | IB*2.0*592_T10 | DE282, DE291, DE384
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC - created for 2017 eBilling Maintain Compliance stories and activities | N/A | US 1108 - Enter/Edit Dental Claims US 131 - Create 837D Transaction | US1108 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim transaction compliant with the X12n 00501-X224 Health Care claim: Dental (837) standard to the HCCH for submission to third party payers. US131 - As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need to be able to electronically transmit the data for a dental claim to the Financial Services Center (FSC) so they can then submit a dental claim compliant with the X12n 00501-X224 Health Care claim: Dental (837D) standard to the HCCH for submission to third party payers. | Yes | N/A | IB*2.0*592 | 3&4 | TC1342 - CIT eBilling TS6 Copy New Dental Fields 1108 and US131 | Pass | IB*2.0*592_T10 | N/A
US1109 - Create Dental Form/Update Autobiller
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US1109 - Create Dental Form/Update Autobiller | As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I need the Autobiller to create claims for billable dental services using the American Dental Association (ADA) claim form (J430D) for dental appointments in Claims Tracking so that I can access those claims and complete them. I also want the ability to prevent the creation of J430D claims for dental services by both the Autobiller and manual entry. | Yes | N/A | IB*2.0*592 | 3&4 | TC1259 - CIT eBilling TS7 Dental Claim Creation - AutoBiller US1109 | Pass | IB*2.0*592_T10 | DE316, DE318
US2487 - Insurance Company Entry/Edit - Dental
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2487 - Insurance Company Entry/Edit - Dental | As a billing or insurance clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to define, by payer, the primary payer ID used by the clearinghouse to route dental claims to the correct processing entity. I also want to be able to assign Provider IDs that are assigned by Form Type, to the additional J430D Form Type and to defined which provider IDs are defaulted/required for the J430D Form Type. I also want to be able to define an insurance company mailing address for Dental claims. If there is no dental specific mailing address, then I want the software to use the Main Mailing Address. | Yes | N/A | IB*2.0*592 | 3&4 | TC1346 - CIT eBilling TS10 Insurance Co Editor (1) US2487 | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2487 - Insurance Company Entry/Edit - Dental | As a billing or insurance clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to define, by payer, the primary payer ID used by the clearinghouse to route dental claims to the correct processing entity. I also want to be able to assign Provider IDs that are assigned by Form Type, to the additional J430D Form Type and to defined which provider IDs are defaulted/required for the J430D Form Type. I also want to be able to define an insurance company mailing address for Dental claims. If there is no dental specific mailing address, then I want the software to use the Main Mailing Address. | Yes | N/A | IB*2.0*592 | 3&4 | TC1349 - CIT eBilling TS11 Insurance Co Editor (2) US2487 | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2487 - Insurance Company Entry/Edit - Dental | As a billing or insurance clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to define, by payer, the primary payer ID used by the clearinghouse to route dental claims to the correct processing entity. I also want to be able to assign Provider IDs that are assigned by Form Type, to the additional J430D Form Type and to defined which provider IDs are defaulted/required for the J430D Form Type. I also want to be able to define an insurance company mailing address for Dental claims. If there is no dental specific mailing address, then I want the software to use the Main Mailing Address. | Yes | N/A | IB*2.0*592 | 3&4 | TC1350 - CIT eBilling TS12 Dental Payer ID/Dental US2487 | Pass | IB*2.0*592_T10 | DE412
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2487 - Insurance Company Entry/Edit - Dental | As a billing or insurance clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to define, by payer, the primary payer ID used by the clearinghouse to route dental claims to the correct processing entity. I also want to be able to assign Provider IDs that are assigned by Form Type, to the additional J430D Form Type and to defined which provider IDs are defaulted/required for the J430D Form Type. I also want to be able to define an insurance company mailing address for Dental claims. If there is no dental specific mailing address, then I want the software to use the Main Mailing Address. | Yes | N/A | IB*2.0*592 | 3&4 | TC1351 - CIT eBilling TS13 No Dental Payer ID/No Dental Address US2487 | Pass | IB*2.0*592_T10 | DE319, DE320
US2488 - Update Reports - Form Type J430D
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2488 - Update Reports - Form Type J430D | As a member of the billing staff at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to see the additional Form Type, J430D, on Integrated Billing reports. I also want to be able to specify the Form Type of J430D when an option or report uses the Form Type as search criteria. | Yes | N/A | IB*2.0*592 | 3&4 | TS21 - TC1621 - CIT eBilling TS21 EDI Claim Status Report_Dental US2488 | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2488 - Update Reports - Form Type J430D | As a member of the billing staff at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to see the additional Form Type, J430D, on Integrated Billing reports. I also want to be able to specify the Form Type of J430D when an option or report uses the Form Type as search criteria. | Yes | N/A | IB*2.0*592 | 3&4 | TC1622 - CIT eBilling TS22 RCB - View/Resubmit Claims_Dental US2488 | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2488 - Update Reports - Form Type J430D | As a member of the billing staff at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to see the additional Form Type, J430D, on Integrated Billing reports. I also want to be able to specify the Form Type of J430D when an option or report uses the Form Type as search criteria. | Yes | N/A | IB*2.0*592 | 3&4 | TC1623 - CIT eBilling TS23 RCB - REX – Ready for Extract Report_Dental US2488 | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2488 - Update Reports - Form Type J430D | As a member of the billing staff at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to see the additional Form Type, J430D, on Integrated Billing reports. I also want to be able to specify the Form Type of J430D when an option or report uses the Form Type as search criteria. | Yes | N/A | IB*2.0*592 | 3&4 | TC1624 - CIT eBilling TS24 RCB - VPE - View/Print EDI Bill Extract Data_Dental US2488 | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2488 - Update Reports - Form Type J430D | As a member of the billing staff at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to see the additional Form Type, J430D, on Integrated Billing reports. I also want to be able to specify the Form Type of J430D when an option or report uses the Form Type as search criteria. | Yes | N/A | IB*2.0*592 | 3&4 | TC1626 - CIT eBilling TS26 - HCCH Payer ID Report US2488 | Pass | IB*2.0*592_T10 | DE383
US2489 - System Errors - MRW_CSA
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2489 - System Errors - MRW_CSA | Fixing Pre-existing defects. | Yes | N/A | IB*2.0*592 | 3&4 | TC1618 - CIT eBilling TS18 MRW - Print MRA US2489 | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US2489 - System Errors - MRW_CSA | Fixing Pre-existing defects. | Yes | N/A | IB*2.0*592 | 3&4 | TC1619 - CIT eBilling TS19 CSA - Print EOB/MRA US2489 | Pass | IB*2.0*592_T10 | N/A
US3528 - Provider ID Maintenance_Dental_Removal
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS14 – Regression Insurance Co ID Default | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS15 – Regression Ins Co ID Parameters | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS16 – Regression Billing Provider Secondary IDs | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS17 – Regression Additional Billing Provider Secondary IDs | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS34 – Regression Ins Co VA Lab/Facilitiy ID | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS27 – Regression VA Provider’s Own IDs | Pass | IB*2.0*592_T10 | DE418
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS28 – Regression VA Provider’s Insurance IDs | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS29 – Regression Care Units | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS30 – Regression Non-VA Provider’s Own IDs | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS31 – Regression Non-VA Provider’s Ins IDs | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS32 – Regression Non-VA Facility’s Own IDs | Pass | IB*2.0*592_T10 | N/A
N/A | US1168 - EPIC - Maintain eBilling Compliance | EPIC created for 2017 eBilling Maintain Compliance stories and activities | N/A | US3528 - Provider ID Maintenance_Dental_Removal | As a member of the eBilling Team, I have determined during User Acceptance Testing (UAT) that I no longer want to be able to define either human or facility Secondary Provider IDs to be used on Dental claim. | Yes | N/A | IB*2.0*592 | 3&4 | TS33 – Regression Non-VA Facility’s Ins IDs | Pass | IB*2.0*592_T10 | N/A