## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 5 and Build 6 IB*2.0*608 Defect Log
June 2018
Version 1.0

## Revision History
Revision History
Date | Version | Description | Author
June 2018 | 1 | Initial Version | Jane Balchunas

## Defect Log
Defect ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
DE463 | NA | CIT Property/Casualty Number Missing | 3 - Medium | Closed | 1/9/2018 Found in B*2.0*608_T1 | US 1909 - Remove Ability to Define Insurance Company as non-EDI | TC2179: CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | 1/16/2018 Verified in IB*2.0*608_T3
DE464 | NA | CIT - Inconsistencies Found with Report for US1909 | 3 - Medium | Closed | 1/9/2018 Found in B*2.0*608_T1 | US 1909 - Remove Ability to Define Insurance Company as non-EDI | TC2179: CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | 1/10/2018 Verified in IB*2.0*608_T2
DE487 | NA | CIT - MCCF and Non-MCCF Needs to be Incl in Title Of Summary Report US142 | 3 - Medium | Closed | 1/30/2018 Found in B*2.0*608_T4 | US 142 - non-MCCF Unbilled Amounts Report | TC2234: CIT eBilling TS2 – Re-generate Unbilled Amounts Reports to Sort by Both MCCF and Non-MCCF Claims US142_Regression | 2/2/2018 Verified in IB*2.0*608_T5
DE502 | NA | CIT - Erroneous Fatal Error Displaying US3214 | 3 - Medium | Closed | 2/11/2018 Found in B*2.0*608_T6 | US3214 - Remove Fatal Error - Rendering Provider CMS 1500 | TC2432: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 2/12/2018 Verified in IB*2.0*608_T7
DE503 | NA | CIT - Help Text Needs to be Updated to Coincide with US3214 | 4 - Low | Closed | 2/13/2018 Found in B*2.0*608_T7 | US3214 - Remove Fatal Error - Rendering Provider CMS 1500 | TC2432: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 2/15/2018 Verified in IB*2.0*608_T8
DE509 | NA | CIT - RENDERING Provider Displays as Required on Another Help Screen US3214 | 3 - Medium | Closed | 2/13/2018 Found in B*2.0*608_T7 | US3214 - Remove Fatal Error - Rendering Provider CMS 1500 | TC2342: CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | 2/15/2018 Verified in IB*2.0*608_T8
DE526 | NA | CIT - 2nd INS loop not created | 2 - High | Closed | 2/20/2018 Found in IB*2.0*608_T7 | US9: Transmitting SNF Claims with Appropriate Revenue (USEB-16) | TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 | 2/20/2018 Verified in IB*2.0*608_T8
DE527 | NA | CIT - UB085 Error Message Text - US142 | 3 - Medium | Closed | 2/21/2018 Found in B*2.0*608_T8 | US142 - non-MCCF Unbilled Amounts Report | TC2233: CIT eBilling TS2 – Re-generate Unbilled Amounts Reports to Sort by Both MCCF or Non-MCCF Claims US142 | 2/23/2018 Verified in IB*2.0*608_T9
DE528 | NA | CIT - UBIL Report Header Needs to be Updated US142 | 3 - Medium | Closed | 2/21/2018 Found in B*2.0*608_T8 | US142 - non-MCCF Unbilled Amounts Report | TC2234: CIT eBilling TS2 – Re-generate Unbilled Amounts Reports to Sort by All Types of MCCF and Non-MCCF Claims US142_Regression | 2/23/2018 Verified in IB*2.0*608_T9
DE530 | NA | CIT - Claims NOT Being Generated to NON-MCCF Report US142 | 3 - Medium | Closed | 2/21/2018 Found in B*2.0*608_T8 | US142 - non-MCCF Unbilled Amounts Report | TC2233: CIT eBilling TS2 – Re-generate Unbilled Amounts Reports to Sort by Both MCCF or Non-MCCF Claims US142 | 3/4/2018 Verified in IB*2.0*608_T10
DE535 | NA | CIT - US2599 - No key associated with Rate type type editer under not Non_MCCF pay-to provider | 2 - High | Closed | 2/23/2018 Found in B*2.0*608_T9 | US2599 - non-MCCF Pay-to Provider | TC2622: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – UB04 - US2599 | 3/4/2018 Verified in IB*2.0*608_T10
DE536 | NA | CIT - US2599 - System Freezes after entering AR - for add rate type | 2 - High | Closed | 2/23/2018 Found in B*2.0*608_T9 | US2599 - non-MCCF Pay-to Provider | TC2620: CIT - 6.2 Non-MCCF Pay-to Address Rate Types – CMS1500 | 3/4/2018 Verified in IB*2.0*608_T10
DE537 | NA | CIT - US2599 - Non-MCCF address is not coming over on the claim | 2 - High | Closed | 2/26/2018 Found in B*2.0*608_T9 | US2599 - non-MCCF Pay-to Provider | TC2623: CIT - Non-MCCF Pay-to Address Rate Types – J430D - US2599 | 3/11/2018 Verified in IB*2.0*608_T10
DE560 | NA | CIT - Oxgen CMN - Segments not transmiting | 2 - High | Closed | 3/7/2018 Found in IB*2.0*592_T11 | US3 - CMN Oxygen and EPN Nutrition | TC2764: CIT -CMN Oxgyen | 3/12/2018 Verified in IB*2.0*608_T12
DE565 | NA | UAT - CMN error given when completing claim when it is not required US3 | 4 - Low | Closed | 3/7/2018 Found in IB*2.0*592_T10 | US3 - CMN Oxygen and EPN Nutrition | TC2764: CIT -CMN Oxgyen | 3/14/2018 Verified in IB*2.0*608_T12
DE570 | NA | CIT - Making the selections for the rate table smart | 4 - Low | Closed | 3/8/2018 Found in IB*2.0*592_T11 | US2599 - non-MCCF Pay-to Provider | TC2620: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 | 3/14/2018 Verified in IB*2.0*608_T12
DE572 | NA | CIT - System Loops when adding a rate type | 3 - Medium | Closed | 3/8/2018 Found in IB*2.0*592_T11 | US2599 - non-MCCF Pay-to Provider | TC2620: CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 | 3/14/2018 Verified in IB*2.0*608_T12
DE589 | NA | CIT - CMN OX - date question for ABG | 4 - Low | Closed | 3/14/2018 Found in IB*2.0*592_T12 | US3 - CMN Oxygen and EPN Nutrition | TC2764: CIT -CMN Oxgyen | 3/27/2018 Verified in IB*2.0*608_T13
DE603 | NA | CIT - Claim Files to FSC are incorrect namespace | 3 - Medium | Closed | 3/20/2018 Found in IB*2.0*592_T12 | US3 - CMN Oxygen and EPN Nutrition | TC2764: CIT -CMN Oxgyen | 3/28/2018 Verified in IB*2.0*608_T13
DE607 | NA | CIT - There needs to be a space in the FRM record to include a space | 3 - Medium | Closed | 3/21/2018 Found in IB*2.0*592_T12 | US3 - CMN Oxygen and EPN Nutrition | TC2764: CIT -CMN Oxgyen | 3/27/2018 Verified in IB*2.0*608_T13
DE618 | NA | CIT - Add space between skipped claims numbers for message displayed US2486 | 3 - Medium | Closed | 3/28/2018 Found in IB_2.0*608_T13 | US2486 - RCB - Match COB Data to Payer Sequence | TC2791: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message | 4/5/2018 Verified in IB*2.0*608_T14
DE619 | NA | CIT - Weight tranmitted in MEA and needs to be in PT1 | 3 - Medium | Closed | 3/29/2018 Found in IB_2.0*608_T13 | US3 - CMN Oxygen and EPN Nutrition | TC2764: CIT -CMN Oxgyen | 4/9/2018 Verified in IB*2.0*608_T14
DE624 | NA | CIT - EOBS Should not be Sent for Secondary & Tertiary Claims US2486 | 3 - Medium | Closed | 4/3/2018 Found in IB_2.0*608_T13 | US2486 - RCB - Match COB Data to Payer Sequence | TC2790: eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | 4/4/2018 Verified in IB*2.0*608_T14
DE630 | NA | CIT - Claim Level COB1 Piece 2 is Missing-US2486 | 3 - Medium | Closed | 4/5/2018 Found in IB_2.0*608_T14 | US2486 - RCB - Match COB Data to Payer Sequence | TC2790: eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | 4/9/2018 Verified in IB*2.0*608_T15
DE631 | NA | CIT - CMN with Multi procedures - the LQ can only be used once per loop | 2 - High | Closed | 4/9/2018 Found in IB_2.0*608_T14 | US3 - CMN Oxygen and EPN Nutrition | TC2764: CIT -CMN Oxgyen | 4/12/2018 Verified in IB*2.0*608_T16
DE633 | NA | CIT-The DME portion should be removed in the LQ | 4 - Low | Closed | 4/10/2018 Found in IB_2.0*608_T15 | US3 - CMN Oxygen and EPN Nutrition | TC2762: CIT - CMN Enteral and Parenteral Nutrition | 4/12/2018 Verified in IB*2.0*608_T16
DE638 | NA | CIT - Line Level LCOB 2 Pieces are Missing Data-US2486 | 2 - High | Closed | 4/11/2018 Found in IB_2.0*608_T15 | US2486 - RCB - Match COB Data to Payer Sequence | TC2790: eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | 4/13/2018 Verified in IB*2.0*608_T16
DE659 | NA | CIT - Message displays incorrect number of skipped claims - US2486 | 3 - Medium | Closed | 4/19/2018 Found in IB_2.0*608_T18 | US2486 - RCB - Match COB Data to Payer Sequence | TC2791: eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message | 4/23/2018 Verified in IB*2.0*608_T19
DE667 | NA | CIT - when Procedure on Line level is not the same as the Claim level | 3 - Medium | Closed | 4/23/2018 Found in IB_2.0*608_T19 | US3 - CMN Oxygen and EPN Nutrition | TC2762: CIT - CMN Enteral and Parenteral Nutrition | 4/27/2018 Verified in IB*2.0*608_T20
DE674 | NA | CIT - Mixing of Enteral and Parenteral prompts | 3 - Medium | Closed | 4/26/2018 Found in IB*2.0*608_T20 | US3 - CMN Oxygen and EPN Nutrition | TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral | 4/27/2018 Verified in IB*2.0*608_T22
DE675 | NA | CIT - If changing forms old fields aren't cleaned up | 3 - Medium | Closed | 4/26/2018 Found in IB*2.0*608_T20 | US3 - CMN Oxygen and EPN Nutrition | TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral | 4/27/2018 Verified in IB*2.0*608_T22
DE678 | NA | CIT - If Procedure A has no calories then prompt for B should not display | 3 - Medium | Closed | 4/27/2018 Found in IB*2.0*608_T19 | US3 - CMN Oxygen and EPN Nutrition | TC2762: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Enteral | 4/27/2018 Verified in IB*2.0*608_T20
DE682 | NA | UAT - Form Type list needs to change | 4 - Low | Closed | 5/3/2018 Found in IB*2.0*608_T26 | US3 - CMN Oxygen and EPN Nutrition | TC2905: CIT - 1.1 CMN Enteral and Parenteral Nutrition – Both | 5/10/2018 Verified in IB*2.0*608_T27
DE683 | NA | UAT - ABG PO2 prompt should not be required | 4 - Low | Closed | 5/3/2018 Found in IB*2.0*608_T26 | US3 - CMN Oxygen and EPN Nutrition | TC2764: CIT -CMN Oxgyen | 5/10/2018 Verified in IB*2.0*608_T27
DE698 | NA | UAT - CMN Ox question 4 - piece 4 now holds piece 4 and 5 | 4 - Low | Closed | 5/8/2018 Found in IB*2.0*608_T26 | US3 - CMN Oxygen and EPN Nutrition | TC2764: CIT -CMN Oxgyen | 5/10/2018 Verified in IB*2.0*608_T27
DE748 | NA | DEV - "SHARING AGREEMENT" needs to be included as non-MCFF Rate Type | 4 - Low | Closed | 5/23/2018 Found in IB*2.0*608_T29 | US 142 - non-MCCF Unbilled Amounts Report | TC2234: CIT eBilling TS2 – Re-generate Unbilled Amounts Reports to Sort by Both MCCF and Non-MCCF Claims US142_Regression | 5/30/2018 Verified in IB*2.0*608_T31