## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 2 IB*2*577 Requirements Traceability Matrix (RTM)
July 6, 2017
Version 1.0

## Revision History
Revision History
Date | Version | Description | Author
2017-07-06 | 0.1 | Draft version | Lisa Bruno
2017-07-07 | 1 | Final version | Lisa Bruno

## RTM
US114 Cloning a Primary Claim (USEB-500) - ( Plan Estimate:8 ) - Accepted
Task ID - Name | State | Defect ID - Name | State | Test ID - Name | State
TA2267 - Create SQA Scripts for User Story | Completed | DE48 - SQA - Error found in TC318: SQA eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Development only) | Closed | TC297 - SQA eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | Pass
TA2268 - Perform SQA Test | Completed | DE64 - SQA Error found: in US114: TS9 COB Data in CLON'd Claims | Closed | TC298 - CIT eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | Pass
TA2299 - Redesign User Story (Support) | Completed |  |  | TC303 - SQA eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 | Pass
TA2732 - Analyze issue with payments | Completed |  |  | TC304 - SQA eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 | Pass
TA2733 - Code/Unit Test User Story (address payments) | Completed |  |  | TC306 - SQA eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 | Pass
TA2739 - Create SQA Scripts for User Story (address payments) | Completed |  |  | TC317 - SQA eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | Pass
TA2740 - Perform SQA Test (address payments, regression) | Completed |  |  | TC318 - SQA eBilling TS11 COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | Pass
TA998 - Code/Unit Test User Story | Completed |  |  | TC225 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary Medicare) - Inst TS13 | Pass
TA999 - Create CIT Scripts for User Story | Completed |  |  | TC226 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary Medicare) - Prof TS14 | Pass
TA1000 - Perform CIT Test | Completed |  |  | TC227 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary) - Prof TS15 | Pass
|  |  |  | TC231 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondary Medicare) - Prof TS17 | Pass
|  |  |  | TC232 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondary Medicare) - Inst TS18 | Pass
|  |  |  | TC233 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondar) - Prof TS19 | Pass
|  |  |  | TC234 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondar) - Inst TS20 | Pass
|  |  |  | TC301 - SQA eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | Pass
|  |  |  | TC308 - SQA eBilling TS8 COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 | Pass
|  |  |  | TC415 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Developmnt only) | Pass
|  |  |  | TC230 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary) - Inst TS16 | Pass
|  |  |  | TC607 - CIT eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | Pass
|  |  |  | TC610 - SQA eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | Pass
|  |  |  | TC611 - CIT eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | Pass
|  |  |  | TC612 - CIT eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | Pass
|  |  |  | TC614 - CIT eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 | Pass
|  |  |  | TC615 - CIT eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 | Pass
|  |  |  | TC616 - CIT eBilling TS8 - COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 | Pass
|  |  |  | TC617 - CIT eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | Pass
|  |  |  | TC619 - CIT eBilling TS11 - COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | Pass
|  |  |  | TC559 - CIT SQA eBilling TAS US114 COB Data in CLON'd Claims (Medicare) - Prof - TS21 | Pass
|  |  |  | TC573 - SQA eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | Pass
|  |  |  | TC574 - SQA eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | Pass
|  |  |  | TC607 - CIT eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | Pass
|  |  |  | TC613 - CIT eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 | Pass
|  |  |  | TC618 - CIT eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | Pass
US127 Field Length Adjustments (TSEB-1) - ( Plan Estimate:21 ) - Accepted
Task ID - Name | State | Defect ID - Name | State | Test ID - Name | State
TA1013 - Code/Unit Test User Story | Completed | DE79 - SQA Error found in TC599: TS14 P&C Number Truncated in 837-P | Closed | TC594 - SQA eBilling TS12 – Ambulance Field Lengths - US 127 | Pass
TA1014 - Create CIT Scripts for User Story | Completed | DE86 - SQA Error found in TC595: SQA TS13 – CLIA Number Not Moved to SUB2 | Closed | TC599 - SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | Pass
TA1015 - Perform CIT Test | Completed |  |  | TC600 - SQA eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | Pass
TA2375 - Create SQA Scripts for User Story | Completed |  |  | TC602 - SQA eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | Pass
TA2376 - Perform SQA Test | Completed |  |  | TC603 - SQA eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | Pass
|  |  |  | TC604 - SQA eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | Pass
|  |  |  | TC620 - CIT eBilling TS12 – Ambulance Field Lengths - US 127 | Pass
|  |  |  | TC623 - CIT eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | Pass
|  |  |  | TC624 - CIT eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | Pass
|  |  |  | TC628 - CIT eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | Pass
|  |  |  | TC595 - SQA eBilling TS13 – Lab or Service Facility Field Lengths - US127 | Pass
|  |  |  | TC596 - SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths - US 127 | Pass
|  |  |  | TC621 - CIT eBilling TS13 – Lab or Service Facility Field Lengths US 127 | Pass
|  |  |  | TC622 - CIT eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | Pass
|  |  |  | TC625 - CIT eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | Pass
US129 Process Payer ID - Store HCCH Payer ID (TSEB-2) - ( Plan Estimate:8 ) - Accepted
Task ID - Name | State | Defect ID - Name | State | Test ID - Name | State
TA2377 - Code/Unit Test User Story | Completed |  |  | TC800 - SQA eBilling TS21 Store Payer IDs (Prof) - US129 | Pass
TA2378 - Create CIT Scripts for User Story | Completed |  |  | TC801 - SQA eBilling TS22 Store Payer IDs (Prof) - US129 | Pass
TA2379 - Perform CIT Test | Completed |  |  | TC803 - SQA eBilling TS23 Store Payer IDs (Inst) - US129 | Pass
TA2380 - Create SQA Scripts for User Story | Completed |  |  | TC804 - SQA eBilling TS24 Store Payer IDs (Inst) - US129 | Pass
TA2381 - Perform SQA Test | Completed |  |  | TC807 - CIT eBilling TS21 Store Payer IDs (Prof) - US129 | Pass
|  |  |  | TC808 - CIT eBilling TS22 Store Payer IDs (Prof) - US129 | Pass
|  |  |  | TC811 - CIT eBilling TS24 Store Payer IDs (Inst) - US129 | Pass
|  |  |  | TC812 - CIT eBilling TS23 Store Payer IDs (Inst) - US129 | Pass
|  |  |  | TC1153: CIT eBilling TS24 Store Payer IDs (Inst) - US129 - Regression Not Applcable - New Functionality | N/A
US11 Unit or Basis for Measurements Codes for Drugs (USEB-15) - ( Plan Estimate:3 ) - Accepted
Task ID - Name | State | Defect ID - Name | State | Test ID - Name | State
TA2382 - Code/Unit Test User Story | Completed | DE80 - SQA Error found in TC605: TS19 Code Set Not Correct | Closed | TC605 - SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | Pass
TA2383 - Create CIT Scripts for User Story | Completed | DE81 - SQA Error found in TC605: TS19 Unit or Basis for Measurement Code Not Transmitted | Closed | TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | Pass
TA2384 - Perform CIT Test | Completed | DE82 - SQA Error found in TC605: TS19 – Unit or Basis for Measurement Code Not on CMS1500 | Closed | TC630 - CIT eBilling TS20 – Unit or Basis for Measurements Code (Inst) US11 | Pass
TA2385 - Create SQA Scripts for User Story | Completed | DE85 - CIT Error Found: Low issue on NDC .75 amount on CMS1500 and UB04 in CIT - US127 | Closed | TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | Pass
TA2386 - Perform SQA Test | Completed | DE197 - UAT - TS19 PRF Piece 23 Missing | Closed
US976 Payer ID Report - ( Plan Estimate:13 ) - Accepted
Task ID - Name | State | Defect ID - Name | State | Test ID - Name | State
TA2387 - Code/Unit Test User Story | Completed | DE129 - HCCH Payer ID Report - Incorrect Date | Closed | TC805 - SQA eBilling TS25 Payer ID Report - US976 | Pass
TA2388 - Create CIT Scripts for User Story | Completed | DE152 - Error found in TC805: Display More than Payer Address Line 1 | Closed | TC810 - CIT eBilling TS25 Payer ID Report - US976 | Pass
TA2389 - Perform CIT Test | Completed |  |  | TC1152: CIT eBilling TS25 Payer ID Report - US976 - Regression Test Not Applcable - New Functionality | N/A
TA2390 - Create SQA Scripts for User Story | Completed
TA2391 - Perform SQA Test | Completed
US1166 Print NDC Number on UB04 - ( Plan Estimate:5 ) - Accepted
Task ID - Name | State | Defect ID - Name | State | Test ID - Name | State
TA2392 - Code/Unit Test User Story | Completed | DE83 - SQA Error found in TC606: TS20 – Qualifers Not Printing UB04 FL43 | Closed | TC606 - SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | Pass
TA2393 - Create CIT Scripts for User Story | Completed | DE84 - SQA Error found in TC606: TS20 – Decimal Transmitting in INS | Closed | TC606 - SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) | Pass
TA2394 - Perform CIT Test | Completed
TA2395 - Create SQA Scripts for User Story | Completed
TA2396 - Perform SQA Test | Completed