## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 7, Build 8, and Build 9 IB*2.0*623 Test Execution Log
July 2019
Version 3.0

## Revision History
Revision History
Date | Version | Description | Author
May 2019 | 1 | Initial Version for review | Jane Balchunas
January 2019 | 2 | Version for IOC review | Jane Balchunas
July 2019 | 3 | Updated with test results from final build testing | Jane Balchunas

## Test Execution Log
Test Case ID | Build 7 & 8 | Build Exectued | Date Executed | Tested By | Test Results (P/F) | Defect ID (Failed Tests)
TC1250: CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 7&8&9 | B*2.0*623_T7 | 2018-07-31 | CJ Minch | Fail | DE883
TC1250: CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 7&8&9 | B*2.0*623_T8 | 2018-08-07 | CJ Minch | Pass | NA
TC1250: CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 7&8&9 | B*2.0*623_T21 | 2019-03-28 | CJ Minch | Pass | NA
TC1250: CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 7&8&9 | B*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 | 7&8&9 | B*2.0*623_T5 | 2018-07-19 | CJ Minch | Fail | UAT-DE871
TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 | 7&8&9 | B*2.0*623_T7 | 2018-08-02 | CJ Minch | Pass | NA
TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US10 | 7&8&9 | B*2.0*623_T8 | 2019-03-25 | CJ Minch | Pass | NA
TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US11 | 7&8&9 | B*2.0*623_T21 | 2019-03-28 | CJ Minch | Pass | NA
TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US11 | 7&8&9 | B*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC3404 - CIT - eBilling - Transmit 837 Transactions Through New Platform- Outpatient CMS 1500– US3346 | 7&8&9 | IB*2.0*623_T14 | 2018-12-20 | CJ Minch | Pass | NA
TC3404 - CIT - eBilling - Transmit 837 Transactions Through New Platform- Outpatient CMS 1500– US3346 | 7&8&9 | IB*2.0*623_T21 | 2019-04-24 | CJ Minch | Pass | NA
TC3404 - CIT - eBilling - Transmit 837 Transactions Through New Platform- Outpatient CMS 1500– US3346 | 7&8&9 | B*2.0*623_T23 | 2019-07-09 | CJ Minch | Pass | NA
TC3405 CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7&8&9 | IB*2.0*623_T16 | 2019-01-14 | CJ Minch | Fail | DE1075
TC3405 CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7&8&9 | IB*2.0*623_T16 | 2019-01-16 | CJ Minch | Fail | DE1076
TC3405 CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7&8&9 | IB*2.0*623_T21 | 2019-04-24 | CJ Minch | Pass | NA
TC3405 CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7&8&9 | IB*2.0*623_T21 | 2019-07-01 | CJ Minch | Fail | DE1305, DE1440, DE1441, DE1476, DE1483, DE1495, DE1497, DE1499
TC3405 CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7&8&9 | IB*2.0*623_T23 | 2019-07-09 | CJ Minch | Pass | NA
TC3406 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Dental Claim US3346 | 7&8&9 | IB*2.0*623_T14 | 2018-12-17 | CJ Minch | Pass | NA
TC3406 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Dental Claim US3346 | 7&8&9 | IB*2.0*623_T21 | 2019-04-24 | CJ Minch | Pass | NA
TC3406 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Dental Claim US3346 | 7&8&9 | IB*2.0*623_T23 | 2019-07-09 | CJ Minch | Pass | NA
TC3407 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient CMN Oxgen Claim-US3346 | 7&8&9 | IB*2.0*623_T14 | 2018-12-19 | CJ Minch | Pass | NA
TC3407 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient CMN Oxgen Claim-US3346 | 7&8&9 | IB*2.0*623_T21 | 2019-04-24 | CJ Minch | Pass | NA
TC3407 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient CMN Oxgen Claim-US3346 | 7&8&9 | IB*2.0*623_T23 | 2019-07-09 | CJ Minch | Pass | NA
TC3408 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient CMN Enteral & Parenteral -US3346 | 7&8&9 | IB*2.0*623_T14 | 2018-12-21 | CJ Minch | Pass | NA
TC3408 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient CMN Enteral & Parenteral -US3346 | 7&8&9 | IB*2.0*623_T21 | 2019-04-24 | CJ Minch | Pass | NA
TC3408 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient CMN Enteral & Parenteral -US3346 | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC3409 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Pharmacy Claim -US3346 | 7&8&9 | IB*2.0*623_T14 | 2018-12-18 | CJ Minch | Pass | NA
TC3409 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Pharmacy Claim -US3346 | 7&8&9 | IB*2.0*623_T21 | 2019-04-24 | CJ Minch | Pass | NA
TC3409 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Pharmacy Claim -US3346 | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC3410 - CIT - eBilling - Transmit 837 Transactions Through New Platform–Inpatient CMS 1500 Professional - US3346 | 7&8&9 | IB*2.0*623_T14 | 2018-12-17 | CJ Minch | Pass | NA
TC3410 - CIT - eBilling - Transmit 837 Transactions Through New Platform–Inpatient CMS 1500 Professional - US3346 | 7&8&9 | IB*2.0*623_T21 | 2019-04-24 | CJ Minch | Pass | NA
TC3410 - CIT - eBilling - Transmit 837 Transactions Through New Platform–Inpatient CMS 1500 Professional - US3346 | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC3411 - CIT - eBilling - Transmit 837 Transactions Through New Platform–Inpatient UB04 Institutional Claim- US3346 | 7&8&9 | IB*2.0*623_T14 | 2018-12-20 | CJ Minch | Pass | NA
TC3411 - CIT - eBilling - Transmit 837 Transactions Through New Platform–Inpatient UB04 Institutional Claim- US3346 | 7&8&9 | IB*2.0*623_T21 | 2019-04-24 | CJ Minch | Pass | NA
TC3411 - CIT - eBilling - Transmit 837 Transactions Through New Platform–Inpatient UB04 Institutional Claim- US3346 | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC3415 - CIT-eBilling TAS US3994-TS1–SYS Updates Claim Office ID When One Does Not Exist_US3994_Prod Only | 7&8&9 | IB*2.0*623_T1 | 2018-07-09 | Jane Balchunas | Fail | DE842
TC3415 - CIT-eBilling TAS US3994-TS1–SYS Updates Claim Office ID When One Does Not Exist_US3994_Prod Only | 7&8&9 | IB*2.0*623_T2 | 2018-07-10 | Jane Balchunas | Pass | NA
TC3415 - CIT-eBilling TAS US3994-TS1–SYS Updates Claim Office ID When One Does Not Exist_US3994_Prod Only | 7&8&9 | IB*2.0*623_T20 | 2019-03-26 | Jane Balchunas | Pass | NA
TC3415 - CIT-eBilling TAS US3994-TS1–SYS Updates Claim Office ID When One Does Not Exist_US3994_Prod Only | 7&8&9 | IB*2.0*623_T21 | 2019-03-29 | Jane Balchunas | Pass | NA
TC3415 - CIT-eBilling TAS US3994-TS1–SYS Updates Claim Office ID When One Does Not Exist_US3994_Prod Only | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | Jane Balchunas | Pass | NA
TC3416 - CIT-eBilling-TS2–SYS Displays Original Claim Office ID When One Exists–Prod Only_US3994 | 7&8&9 | IB*2.0*623_T3 | 2018-07-12 | Jane Balchunas | Fail | DE854
TC3416 - CIT-eBilling-TS2–SYS Displays Original Claim Office ID When One Exists–Prod Only_US3994 | 7&8&9 | IB*2.0*623_T4 | 2018-07-17 | Jane Balchunas | Pass | NA
TC3416 - CIT-eBilling-TS2–SYS Displays Original Claim Office ID When One Exists–Prod Only_US3994 | 7&8&9 | IB*2.0*623_T20 | 2019-03-26 | Jane Balchunas | Pass | NA
TC3416 - CIT-eBilling-TS2–SYS Displays Original Claim Office ID When One Exists–Prod Only_US3994 | 7&8&9 | IB*2.0*623_T21 | 2019-03-29 | Jane Balchunas | Pass | NA
TC3416 - CIT-eBilling-TS2–SYS Displays Original Claim Office ID When One Exists–Prod Only_US3994 | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | Jane Balchunas | Pass | NA
TC3417 - CIT-eBilling-TS3–SYS Updates Claim Office ID When One Does Not Exist-Prod Only-US3994_Regression | 7&8&9 | IB*2.0*623_T5 | 2018-07-20 | Jane Balchunas | Pass | NA
TC3417 - CIT-eBilling-TS3–SYS Updates Claim Office ID When One Does Not Exist-Prod Only-US3994_Regression | 7&8&9 | IB*2.0*623_T20 | 2019-03-26 | Jane Balchunas | Pass | NA
TC3417 - CIT-eBilling-TS3–SYS Updates Claim Office ID When One Does Not Exist-Prod Only-US3994_Regression | 7&8&9 | IB*2.0*623_T21 | 2019-03-29 | Jane Balchunas | Pass | NA
TC3417 - CIT-eBilling-TS3–SYS Updates Claim Office ID When One Does Not Exist-Prod Only-US3994_Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | Jane Balchunas | Pass | NA
TC3418 - CIT-eBilling-TS4–SYS Displays Original Claim Office ID When One Exists–Prod Only__US3994_Regression | 7&8&9 | IB*2.0*623_T5 | 2018-07-19 | Jane Balchunas | Pass | NA
TC3418 - CIT-eBilling-TS4–SYS Displays Original Claim Office ID When One Exists–Prod Only__US3994_Regression | 7&8&9 | IB*2.0*623_T20 | 2019-03-26 | Jane Balchunas | Pass | NA
TC3418 - CIT-eBilling-TS4–SYS Displays Original Claim Office ID When One Exists–Prod Only__US3994_Regression | 7&8&9 | IB*2.0*623_T21 | 2019-03-29 | Jane Balchunas | Pass | NA
TC3418 - CIT-eBilling-TS4–SYS Displays Original Claim Office ID When One Exists–Prod Only__US3994_Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | Jane Balchunas | Pass | NA
TC3419 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only_US3995 | 7&8&9 | IB*2.0*623_T1 | 2018-06-25 | Jane Balchunas | Pass | NA
TC3419 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only_US3995 | 7&8&9 | B*2.0*623_T6 | 2018-08-01 | Jane Balchunas | Fail (req chg) | UAT-DE896
TC3419 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only_US3995 | 7&8&9 | B*2.0*623_T8 | 2018-08-07 | Jane Balchunas | Pass | NA
TC3419 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only_US3995 | 7&8&9 | B*2.0*623_T20 | 2019-03-27 | Jane Balchunas | Pass | NA
TC3419 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only_US3995 | 7&8&9 | B*2.0*623_T21 | 2019-04-01 | Jane Balchunas | Pass | NA
TC3419 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only_US3995 | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | Jane Balchunas | Pass | NA
TC3420 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only-US3995_Regression | 7&8&9 | IB*2.0*623_T5 | 2018-07-17 | Jane Balchunas | Pass | NA
TC3420 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only-US3995_Regression | 7&8&9 | IB*2.0*623_T7 | 2018-08-06 | Jane Balchunas | Pass | DE894
TC3420 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only-US3995_Regression | 7&8&9 | IB*2.0*623_T8 | 2018-08-07 | Jane Balchunas | Pass | NA
TC3420 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only-US3995_Regression | 7&8&9 | IB*2.0*623_T20 | 2019-03-27 | Jane Balchunas | Pass | NA
TC3420 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only-US3995_Regression | 7&8&9 | IB*2.0*623_T21 | 2019-04-01 | Jane Balchunas | Pass | NA
TC3420 - CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only-US3995_Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | Jane Balchunas | Pass | NA
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | IB*2.0*623_T6 | 2018-07-30 | CJ Minch | Fail | DE884
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | IB*2.0*623_T6 | 2018-07-30 | CJ Minch | Fail | DE885
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | IB*2.0*623_T6 | 2018-07-31 | CJ Minch | Fail | DE891
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | IB*2.0*623_T7 | 2018-08-06 | CJ Minch | Fail | DE907
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | IB*2.0*623_T7 | 2018-08-07 | CJ Minch | Fail | DE908
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T8 | 2018-08-07 | CJ Minch | Pass | NA
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T8 | 2018-08-15 | CJ Minch | Fail | DE915
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T9 | 2018-08-28 | CJ Minch | Pass | NA
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T8 | 2018-08-20 | CJ Minch | Fail | DE918
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T14 | 2018-09-19 | CJ Minch | Pass | NA
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T11 | 2018-09-10 | CJ Minch | Fail | DE934
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T12 | 2018-09-13 | CJ Minch | Fail | DE940
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T12 | 2018-09-13 | CJ Minch | Fail | DE941
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T12 | 2018-09-13 | CJ Minch | Fail | DE944
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T14 | 2018-09-19 | CJ Minch | Pass | NA
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | B*2.0*623_T21 | 2019-03-28 | CJ Minch | Pass | NA
TC3437 - CIT - eBilling - Dental Claim Mock up US4055 | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | CJ Minch | Pass | NA
TC3493 - CIT-eBilling-TS1-Alternate Inst Payer IDs-US4100 | 7&8&9 | IB*2.0*623_T6 | 2018-08-08 | Jane Balchunas | Fail | DE892
TC3493 - CIT-eBilling-TS1-Alternate Inst Payer IDs-US4100 | 7&8&9 | IB*2.0*623_T8 | 2018-08-21 | Jane Balchunas | Pass | NA
TC3493 - CIT-eBilling-TS1-Alternate Inst Payer IDs-US4100 | 7&8&9 | IB*2.0*623_T20 | 2019-03-25 | Jane Balchunas | Pass | NA
TC3493 - CIT-eBilling-TS1-Alternate Inst Payer IDs-US4100 | 7&8&9 | IB*2.0*623_T21 | 2019-03-28 | Jane Balchunas | Pass | NA
TC3493 - CIT-eBilling-TS1-Alternate Inst Payer IDs-US4100 | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | Jane Balchunas | Pass | NA
TC3494 - CIT-eBilling-TS2-Alternate Prof Payer IDs-US4100 | 7&8&9 | IB*2.0*623_T8 | 2018-08-20 | Jane Balchunas | Fail | DE920
TC3494 - CIT-eBilling-TS2-Alternate Prof Payer IDs-US4100 | 7&8&9 | IB*2.0*623_T9 | 2018-08-22 | Jane Balchunas | Pass | NA
TC3494 - CIT-eBilling-TS2-Alternate Prof Payer IDs-US4100 | 7&8&9 | IB*2.0*623_T20 | 2019-03-25 | Jane Balchunas | Pass | NA
TC3494 - CIT-eBilling-TS2-Alternate Prof Payer IDs-US4100 | 7&8&9 | IB*2.0*623_T21 | 2019-03-28 | Jane Balchunas | Pass | NA
TC3494 - CIT-eBilling-TS2-Alternate Prof Payer IDs-US4100 | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | Jane Balchunas | Pass | NA
TC3495 - CIT-eBilling-TS3-Alternate Inst Payer IDs - US4100_Regression | 7&8&9 | IB*2.0*623_T14 | 2018-09-24 | Jane Balchunas | Pass | NA
TC3495 - CIT-eBilling-TS3-Alternate Inst Payer IDs - US4100_Regression | 7&8&9 | IB*2.0*623_T20 | 2019-03-25 | Jane Balchunas | Pass | NA
TC3495 - CIT-eBilling-TS3-Alternate Inst Payer IDs - US4100_Regression | 7&8&9 | IB*2.0*623_T21 | 2019-03-28 | Jane Balchunas | Pass | NA
TC3495 - CIT-eBilling-TS3-Alternate Inst Payer IDs - US4100_Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-12 | Jane Balchunas | Pass | NA
TC3496 - CIT-eBilling-TS4-Alternate Prof Payer IDs - US4100_Regression | 7&8&9 | IB*2.0*623_T14 | 2018-09-24 | Jane Balchunas | Pass | NA
TC3496 - CIT-eBilling-TS4-Alternate Prof Payer IDs - US4100_Regression | 7&8&9 | IB*2.0*623_T20 | 2019-03-25 | Jane Balchunas | Pass | NA
TC3496 - CIT-eBilling-TS4-Alternate Prof Payer IDs - US4100_Regression | 7&8&9 | IB*2.0*623_T21 | 2019-03-28 | Jane Balchunas | Pass | NA
TC3496 - CIT-eBilling-TS4-Alternate Prof Payer IDs - US4100_Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-12 | Jane Balchunas | Pass | NA
TC3967 - CIT - eBilling Implement Release of Information – Outpatient 1500 Professional Claim_US4995 | 7&8&9 | IB*2.0*623_T15 | 2019-01-07 | CJ Minch | Fail | DE1071
TC3967 - CIT - eBilling Implement Release of Information – Outpatient 1500 Professional Claim_US4995 | 7&8&9 | IB*2.0*623_T16 | 2019-01-10 | CJ Minch | Pass | NA
TC3967 - CIT - eBilling Implement Release of Information – Outpatient 1500 Professional Claim_US4995 | 7&8&9 | IB*2.0*623_T21 | 2019-04-01 | CJ Minch | Pass | NA
TC3967 - CIT - eBilling Implement Release of Information – Outpatient 1500 Professional Claim_US4995 | 7&8&9 | IB*2.0*623_T23 | 2019-07-12 | CJ Minch | Pass | NA
TC3968 - CIT-eBilling Implement Release of Information – Outpatient UB04 Institutional Claim_US4995 | 7&8&9 | IB*2.0*623_T15 | 2019-01-07 | CJ Minch | Fail | DE1071
TC3968 - CIT-eBilling Implement Release of Information – Outpatient UB04 Institutional Claim_US4995 | 7&8&9 | IB*2.0*623_T16 | 2019-01-11 | CJ Minch | Pass | NA
TC3968 - CIT-eBilling Implement Release of Information – Outpatient UB04 Institutional Claim_US4995 | 7&8&9 | IB*2.0*623_T21 | 2019-04-02 | CJ Minch | Pass | NA
TC3968 - CIT-eBilling Implement Release of Information – Outpatient UB04 Institutional Claim_US4995 | 7&8&9 | IB*2.0*623_T23 | 2019-07-12 | CJ Minch | Pass | NA
TC4102 - CIT-eBilling-TS1- Generate CSA Worklists by Non-MCCF, MCCF or Both Rate Types_US141 | 7&8&9 | IB*2.0*623_T16 | 2019-01-07 | Jane Balchunas | Fail | DE1074
TC4102 - CIT-eBilling-TS1- Generate CSA Worklists by Non-MCCF, MCCF or Both Rate Types_US141 | 7&8&9 | IB*2.0*623_T16 | 2019-01-23 | Jane Balchunas | Pass | NA
TC4102 - CIT-eBilling-TS1- Generate CSA Worklists by Non-MCCF, MCCF or Both Rate Types_US141 | 7&8&9 | IB*2.0*623_T20 | 2019-03-25 | Jane Balchunas | Pass | NA
TC4102 - CIT-eBilling-TS1- Generate CSA Worklists by Non-MCCF, MCCF or Both Rate Types_US141 | 7&8&9 | IB*2.0*623_T21 | 2019-04-02 | Jane Balchunas | Pass | NA
TC4102 - CIT-eBilling-TS1- Generate CSA Worklists by Non-MCCF, MCCF or Both Rate Types_US141 | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | Jane Balchunas | Pass | NA
TC4103 - CIT-eBilling-TS2-SITE Parameters Will Pre-Populate Non-MCCF Rate Types List_US141 | 7&8&9 | IB*2.0*623_T16 | 2019-01-09 | Jane Balchunas | Pass | NA
TC4103 - CIT-eBilling-TS2-SITE Parameters Will Pre-Populate Non-MCCF Rate Types List_US141 | 7&8&9 | IB*2.0*623_T16 | 2019-01-23 | Jane Balchunas | Pass | NA
TC4103 - CIT-eBilling-TS2-SITE Parameters Will Pre-Populate Non-MCCF Rate Types List_US141 | 7&8&9 | IB*2.0*623_T20 | 2019-03-25 | Jane Balchunas | Pass | NA
TC4103 - CIT-eBilling-TS2-SITE Parameters Will Pre-Populate Non-MCCF Rate Types List_US141 | 7&8&9 | IB*2.0*623_T21 | 2019-04-02 | Jane Balchunas | Pass | NA
TC4103 - CIT-eBilling-TS2-SITE Parameters Will Pre-Populate Non-MCCF Rate Types List_US141 | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | Jane Balchunas | Pass | NA
TC4104 - CIT-eBilling-TS3-Generate CSA Worklists by Non-MCCF, MCCF or Both Rate Types_US141_Regression | 7&8&9 | IB*2.0*623_T16 | 2019-01-30 | Jane Balchunas | Pass | NA
TC4104 - CIT-eBilling-TS3-Generate CSA Worklists by Non-MCCF, MCCF or Both Rate Types_US141_Regression | 7&8&9 | IB*2.0*623_T20 | 2019-03-25 | Jane Balchunas | Pass | NA
TC4104 - CIT-eBilling-TS3-Generate CSA Worklists by Non-MCCF, MCCF or Both Rate Types_US141_Regression | 7&8&9 | IB*2.0*623_T21 | 2019-04-02 | Jane Balchunas | Pass | NA
TC4104 - CIT-eBilling-TS3-Generate CSA Worklists by Non-MCCF, MCCF or Both Rate Types_US141_Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-12 | Jane Balchunas | Pass | NA
TC4105 - CIT-eBilling-TS4-SITE Parameters Will Pre-Populate Non-MCCF Rate Types List_US141_Regression | 7&8&9 | IB*2.0*623_T16 | 2019-01-28 | Jane Balchunas | Pass | NA
TC4105 - CIT-eBilling-TS4-SITE Parameters Will Pre-Populate Non-MCCF Rate Types List_US141_Regression | 7&8&9 | IB*2.0*623_T20 | 2019-03-25 | Jane Balchunas | Pass | NA
TC4105 - CIT-eBilling-TS4-SITE Parameters Will Pre-Populate Non-MCCF Rate Types List_US141_Regression | 7&8&9 | IB*2.0*623_T21 | 2019-04-02 | Jane Balchunas | Pass | NA
TC4105 - CIT-eBilling-TS4-SITE Parameters Will Pre-Populate Non-MCCF Rate Types List_US141_Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-12 | Jane Balchunas | Pass | NA
TC4140 - CIT - ebilling Implement Release of Information – Outpatient 1500 Professional Claim - - Claim prior to date_US4995 | 7&8&9 | IB*2.0*623_T16 | 2019-01-17 | CJ Minch | Pass | NA
TC4140 - CIT - ebilling Implement Release of Information – Outpatient 1500 Professional Claim - - Claim prior to date_US4995 | 7&8&9 | IB*2.0*623_T21 | 2019-04-02 | CJ Minch | Pass | NA
TC4140 - CIT - ebilling Implement Release of Information – Outpatient 1500 Professional Claim - - Claim prior to date_US4995 | 7&8&9 | IB*2.0*623_T23 | 2019-07-12 | CJ Minch | Pass | NA
TC4141 - CIT - ebilling Implement Release of Information – Outpatient UB04 Professional Claim - - Claim prior to date_US4995 | 7&8&9 | IB*2.0*623_T16 | 2019-01-17 | CJ Minch | Pass | NA
TC4141 - CIT - ebilling Implement Release of Information – Outpatient UB04 Professional Claim - - Claim prior to date_US4995 | 7&8&9 | IB*2.0*623_T21 | 2019-04-02 | CJ Minch | Pass | NA
TC4141 - CIT - ebilling Implement Release of Information – Outpatient UB04 Professional Claim - - Claim prior to date_US4995 | 7&8&9 | IB*2.0*623_T23 | 2019-07-12 | CJ Minch | Pass | NA
TC4146 - CIT - ebilling Implement Release of Information – Outpatient 1500 Professional Claim - - Claim prior to date - Regression_US4995 | 7&8&9 | IB*2.0*623_T16 | 2019-01-17 | CJ Minch | Pass | NA
TC4146 - CIT - ebilling Implement Release of Information – Outpatient 1500 Professional Claim - - Claim prior to date - Regression_US4995 | 7&8&9 | IB*2.0*623_T21 | 2019-04-01 | CJ Minch | Pass | NA
TC4146 - CIT - ebilling Implement Release of Information – Outpatient 1500 Professional Claim - - Claim prior to date - Regression_US4995 | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC4147 - CIT - ebilling Implement Release of Information – Outpatient UB04 Professional Claim - - Claim prior to date - - Regression_US4995 | 7&8&9 | IB*2.0*623_T16 | 2019-01-17 | CJ Minch | Pass | NA
TC4147 - CIT - ebilling Implement Release of Information – Outpatient UB04 Professional Claim - - Claim prior to date - - Regression_US4995 | 7&8&9 | IB*2.0*623_T21 | 2019-04-01 | CJ Minch | Pass | NA
TC4147 - CIT - ebilling Implement Release of Information – Outpatient UB04 Professional Claim - - Claim prior to date - - Regression_US4995 | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC4707 - CIT - ebilling-Transmitting SNF Claims with Appropriate Revenue Codes after 10/1/2019 Production Only US8323 | 7&8&9 | IB*2.0*623_T21 | 2019-04-02 | CJ Minch | Pass | NA
TC4707 - CIT - ebilling-Transmitting SNF Claims with Appropriate Revenue Codes after 10/1/2019 Production Only US8323 | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC5130 - CIT - eBilling - Transmit 837 Transactions Through New Platform- Outpatient CMS 1500– US3346 - Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5130 - CIT - eBilling - Transmit 837 Transactions Through New Platform- Outpatient CMS 1500– US3346 - Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC5131 - CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 - Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5131 - CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 - Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC5134 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Dental Claim US3346 - Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5134 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Dental Claim US3346 - Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-10 | CJ Minch | Pass | NA
TC5135 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient CMN Oxgen Claim-US3346 - Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5135 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient CMN Oxgen Claim-US3346 - Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | CJ Minch | Pass | NA
TC5136 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient CMN Enteral & Parenteral -US3346 - Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5136 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient CMN Enteral & Parenteral -US3346 - Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | CJ Minch | Pass | NA
TC5137 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Pharmacy Claim -US3346 Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5137 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Pharmacy Claim -US3346 Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | CJ Minch | Pass | NA
TC5138 - CIT - eBilling - Transmit 837 Transactions Through New Platform–Inpatient CMS 1500 Professional - US3346 -Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5138 - CIT - eBilling - Transmit 837 Transactions Through New Platform–Inpatient CMS 1500 Professional - US3346 -Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | CJ Minch | Pass | NA
| 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | CJ Minch | Pass | NA
TC5139 - CIT - eBilling - Transmit 837 Transactions Through New Platform–Inpatient UB04 Institutional Claim- US3346 - Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5139 - CIT - eBilling - Transmit 837 Transactions Through New Platform–Inpatient UB04 Institutional Claim- US3346 - Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | CJ Minch | Pass | NA
TC5140 - CIT - eBilling - Dental Claim Mock up US4055 - Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5140 - CIT - eBilling - Dental Claim Mock up US4055 - Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | CJ Minch | Pass | NA
TC5141 - CIT eBilling-Transmitting SNF Claims with Appropriate Revenue Codes after 10/1/2019 Production Only -US8323 - Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5141 - CIT eBilling-Transmitting SNF Claims with Appropriate Revenue Codes after 10/1/2019 Production Only -US8323 - Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | CJ Minch | Pass | NA
TC5142 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Dental Claim US3346 - Regression | 7&8&9 | IB*2.0*623_T21 | 2019-05-01 | CJ Minch | Pass | NA
TC5142 - CIT - eBilling - Transmit 837 Transactions Through New Platform– Outpatient Dental Claim US3346 - Regression | 7&8&9 | IB*2.0*623_T23 | 2019-07-11 | CJ Minch | Pass | NA