## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 10 and Build 13 IB*2.0*641 Defect Log
July 2019
Version 1.0

## Revision History
Revision History
Date | Version | Description | Author
July 2019 | 1 | Initial Version | Jane Balchunas

## Defect Log
Defect ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
DE1141 | NA | CIT - US3380 - Unable to Return RPN Report in VistA | 2 - High | Closed | 3/5/2019 Found in IB*2.0*641_T1 | US3380 - Secondary Review before Resubmission/Printing Claims without Changes | TC4510: CIT eBilling-TS2-CSA-Secondary Review before Resubmission/Printing Claims without Changes_Report Details_US3380 | 3/11/2019 Verified in IB*2.0*641_T2
DE1174 | NA | CIT - US3380 - Print Bill Results Not Returned on RPN Report | 3 - Medium | Closed | 3/11/2019 Found in IB*2.0*641_T2 | US3380 - Secondary Review before Resubmission/Printing Claims without Changes | TC4510: CIT eBilling-TS2-CSA-Secondary Review before Resubmission/Printing Claims without Changes_Report Details_US3380 | 3/20/2019 Verified in IB*2.0*641_T3