## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 2 IB*2.0*577 Test Execution Log
October 2017
Version 4.0

## Revision History
Revision History
Date | Version | Description | Author
September 2017 | 0.1 | Draft version - for preparation for MOU request | Lisa Bruno
July 2017 | 1 | Needs additional edits | Lisa Bruno
July 2017 | 2 | More edits | Lisa Bruno
September 2017 | 3 | Draft Final Version | Jane Balchunas
October 2017 | 4 | Final Version | Jane Balchunas

## Test Execution Log
Test Case ID | Build | Build Exectued | Date Executed | Tested By | Test Results (P/F) | Defect ID (Failed Tests)
TC225 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary Medicare) - Inst TS13 | 2 | IB*2.0*576_T4 | 2017-03-16 | Mary Simons | Pass | NA
TC225 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary Medicare) - Inst TS13 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC225 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary Medicare) - Inst TS13 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC226 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary Medicare) - Prof TS14 | 2 | IB*2.0*576_T10 | 2017-03-16 | Mary Simons | Pass | NA
TC226 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary Medicare) - Prof TS14 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC226 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary Medicare) - Prof TS14 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC227 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary) - Prof TS15 | 2 | IB*2.0*576_T4 | 2017-03-16 | Mary Simons | Pass | NA
TC227 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary) - Prof TS15 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC227 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary) - Prof TS15 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC230 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary) - Inst TS16 | 2 | IB*2.0*576_T4 | 2017-03-16 | Mary Simons | Pass | NA
TC230 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary) - Inst TS16 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC230 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Primary) - Inst TS16 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC231 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondary Medicare) - Prof TS17 | 2 | IB*2.0*576_T4 | 2017-03-16 | Mary Simons | Pass | NA
TC231 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondary Medicare) - Prof TS17 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC231 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondary Medicare) - Prof TS17 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC232 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondary Medicare) - Inst TS18 | 2 | IB*2.0*576_T5 | 2017-03-16 | Mary Simons | Pass | NA
TC232 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondary Medicare) - Inst TS18 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC232 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondary Medicare) - Inst TS18 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC233 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondar) - Prof TS19 | 2 | IB*2.0*576_T4 | 2017-03-16 | Mary Simons | Pass | NA
TC233 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondar) - Prof TS19 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC233 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondar) - Prof TS19 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC234 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondar) - Inst TS20 | 2 | IB*2.0*576_T4 | 2017-03-16 | Mary Simons | Pass | NA
TC234 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondar) - Inst TS20 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC234 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Secondar) - Inst TS20 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC297: SQA eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Lisa Bruno | Pass | NA
TC297: SQA eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-11 | Lisa Bruno | Pass | NA
TC297: SQA eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC298: CIT eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Lisa Bruno | Pass | NA
TC298: CIT eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-07 | Lisa Bruno | Pass | NA
TC298: CIT eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC301: SQA eBilling TS3 - COB Data in CLON’d Claims (Prim) - DE64Prof - TAS US114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Mary Simons | Pass | NA
TC301: SQA eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC301: SQA eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC303: SQA eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Mary Simons | Pass | NA
TC303: SQA eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC303: SQA eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC304: SQA eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 Regression | 2 | IB*2.0*577_T1 | 2017-04-28 | Mary Simons | Pass | NA
TC304: SQA eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 Regression | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC304: SQA eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 Regression | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC306: SQA eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Mary Simons | Pass | NA
TC306: SQA eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC306: SQA eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC308: SQA eBilling TS8 COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Lisa Bruno | Pass | NA
TC308: SQA eBilling TS8 COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-11 | Lisa Bruno | Pass | NA
TC308: SQA eBilling TS8 COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC313 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Medicare) - Prof - TS21 | 2 | IB*2.0*576_T4 | 2017-03-20 | Mary Simons | Pass | NA
TC313 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Medicare) - Prof - TS21 | 2 | IB*2.0*577_T11 | 2017-07-11 | Lisa Bruno | Pass | NA
TC313 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Medicare) - Prof - TS21 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC314 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Medicare) - Inst - TS22 | 2 | IB*2.0*576_T4 | 2017-03-20 | Mary Simons | Pass | NA
TC314 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Medicare) - Inst - TS22 | 2 | IB*2.0*577_T11 | 2017-07-11 | Lisa Bruno | Pass | NA
TC314 - CIT eBilling TAS US114 COB Data in CLON'd Claims (Medicare) - Inst - TS22 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC317: SQA eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T0 | 2017-04-06 | Mary Simons | Fail | DE64
TC317: SQA eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T1 | 2017-04-06 | Mary Simons | Pass | NA
TC317: SQA eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC317: SQA eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC318: SQA eBilling TS11 COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | 2 | IB*2.0*577_T0 | 2017-03-23 | Mary Simons | Fail | DE48
TC318: SQA eBilling TS11 COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Mary Simons | Pass | NA
TC318: SQA eBilling TS11 COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC318: SQA eBilling TS11 COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC355: SQA eBilling TAS US15 Payer Zip Code - TS8 | 2 | IB*2.0*576_ T10 | 2017-08-16 | Mary Simons | Fail | DE233 Warranty Defect
TC355: SQA eBilling TAS US15 Payer Zip Code - TS8 | 2 | IB*2.0*577_ T11 | 2017-08-30 | Mary Simons | Pass | NA
TC355: SQA eBilling TAS US15 Payer Zip Code - TS8 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC415: CIT eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Developmnt only) | 2 | IB*2.0*576_ T10 | 2017-08-16 | Mary Simons | Pass | NA
TC415: CIT eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Developmnt only) | 2 | IB*2.0*577_ T11 | 2017-08-16 | Mary Simons | Pass | NA
TC415: CIT eBilling TAS US114 COB Data in CLON'd Claims (Tertiary Medicare) - Prof - TS23 (Developmnt only) | 2 | IB*2.0*577_ T13 | 2017-09-20 | CJ Minch | Pass | NA
TC573: SQA eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Mary Simons | Pass | NA
TC573: SQA eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC573: SQA eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC574: SQA eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Mary Simons | Pass | NA
TC574: SQA eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC574: SQA eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC594: SQA eBilling TS12 – Ambulance Field Lengths - US 127 | 2 | IB*2.0*577_T7 | 2017-05-09 | Mary Simons | Pass | NA
TC594: SQA eBilling TS12 – Ambulance Field Lengths - US 127 | 2 | IB*2.0*577_T11 | 2017-07-11 | Lisa Bruno | Pass | NA
TC594: SQA eBilling TS12 – Ambulance Field Lengths - US 127 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC595: SQA eBilling TS13 – Lab or Service Facility Field Lengths - US127 | 2 | IB*2.0*577_T7 | 2017-05-09 | Mary Simons | Fail | DE86
TC595: SQA eBilling TS13 – Lab or Service Facility Field Lengths - US127 | 2 | IB*2.0*577_T8 | 2017-07-05 | Mary Simons | Pass | NA
TC595: SQA eBilling TS13 – Lab or Service Facility Field Lengths - US127 | 2 | IB*2.0*577_T11 | 2017-07-05 | Mary Simons | Pass | NA
TC595: SQA eBilling TS13 – Lab or Service Facility Field Lengths - US127 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC599: SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | 2 | IB*2.0*577_T3 | 05/03/20179 | Mary Simons | Fail | DE79
TC599: SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | 2 | IB*2.0*577_T7 | 2017-05-09 | Mary Simons | Pass | NA
TC599: SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | 2 | IB*2.0*577_T11 | 2017-07-11 | Lisa Bruno | Pass | NA
TC599: SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC600: SQA eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | 2 | IB*2.0*577_T7 | 2017-05-09 | Mary Simons | Pass | NA
TC600: SQA eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | 2 | IB*2.0*577_T11 | 2017-07-11 | Lisa Bruno | Pass | NA
TC600: SQA eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC602: SQA eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | 2 | IB*2.0*577_T7 | 2017-05-09 | Mary Simons | Pass | NA
TC602: SQA eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | 2 | IB*2.0*577_T11 | 2017-07-11 | Lisa Bruno | Pass | NA
TC602: SQA eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC603 - SQA eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_T7 | 2017-05-09 | Mary Simons | Pass | NA
TC603 - SQA eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_T11 | 2017-07-05 | Mary Simons | Pass | NA
TC603 - SQA eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC604 - SQA eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_T7 | 2017-05-11 | Lisa Bruno | Pass | NA
TC604 - SQA eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_T11 | 2017-07-11 | Lisa Bruno | Pass | NA
TC604 - SQA eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T4 | 2017-05-04 | Mary Simons | Fail | DE81
TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Fail | DE211
TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T5 | 2017-05-03 | Mary Simons | Fail | DE80
TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T6 | 2017-05-04 | Mary Simons | Fail | DE82
TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T7 | 2017-05-04 | Mary Simons | Pass | NA
TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T11 | 2017-07-11 | Lisa Bruno | Pass | NA
TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC606: SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_T4 | 2017-05-03 | Mary Simons | Fail | DE83
TC606: SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_T4 | 2017-05-04 | Mary Simons | Fail | DE84
TC606: SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_T6 | 2017-05-09 | Mary Simons | Pass | NA
TC606: SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_T7 | 2017-05-09 | Mary Simons | Pass | NA
TC606: SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_T11 | 2017-07-07 | Lisa Bruno | Pass | NA
TC606: SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC607: CIT eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Lisa Bruno | Pass | NA
TC607: CIT eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-07 | Lisa Bruno | Pass | NA
TC607: CIT eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC607: CIT eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC610: SQA eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Lisa Bruno | Pass | NA
TC610: SQA eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-07 | Lisa Bruno | Pass | NA
TC610: SQA eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC611: CIT eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | 2 | IB*2.0*577_ T1 | 2017-04-28 | Mary Simons | Pass | NA
TC611: CIT eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | 2 | IB*2.0*577_ T11 | 2017-07-13 | Mary Simons | Pass | NA
TC611: CIT eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC612: CIT eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | 2 | IB*2.0*577_ T1 | 2017-04-28 | Mary Simons | Pass | NA
TC612: CIT eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | 2 | IB*2.0*577_ T11 | 2017-07-07 | Mary Simons | Pass | NA
TC612: CIT eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC613: CIT eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 Regression | 2 | IB*2.0*577_ T1 | 2017-04-28 | Lisa Bruno | Pass | NA
TC613: CIT eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 Regression | 2 | IB*2.0*577_ T11 | 2017-07-07 | Lisa Bruno | Pass | NA
TC613: CIT eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 Regression | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC614: CIT eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 Regression | 2 | IB*2.0*577_ T1 | 2017-04-28 | Mary Simons | Pass | NA
TC614: CIT eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 Regression | 2 | IB*2.0*577_ T11 | 2017-07-07 | Mary Simons | Pass | NA
TC614: CIT eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 Regression | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC615: CIT eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 Regression | 2 | IB*2.0*577_ T1 | 2017-04-28 | Mary Simons | Pass | NA
TC615: CIT eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 Regression | 2 | IB*2.0*577_ T11 | 2017-07-07 | Mary Simons | Pass | NA
TC615: CIT eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 Regression | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC616: CIT eBilling TS8 - COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 Regression | 2 | IB*2.0*577_ T1 | 2017-04-28 | Mary Simons | Pass | NA
TC616: CIT eBilling TS8 - COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 Regression | 2 | IB*2.0*577_ T11 | 2017-07-07 | Mary Simons | Pass | NA
TC616: CIT eBilling TS8 - COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 Regression | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC617: CIT eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | 2 | IB*2.0*577_ T1 | 2017-04-28 | Mary Simons | Pass | NA
TC617: CIT eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | 2 | IB*2.0*577_ T11 | 2017-07-07 | Mary Simons | Pass | NA
TC617: CIT eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC618: CIT eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | 2 | IB*2.0*577_ T1 | 2017-04-28 | Mary Simons | Pass | NA
TC618: CIT eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | 2 | IB*2.0*577_ T11 | 2017-07-07 | Mary Simons | Pass | NA
TC618: CIT eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC619: CIT eBilling TS11 - COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | 2 | IB*2.0*577_T1 | 2017-04-28 | Mary Simons | Pass | NA
TC619: CIT eBilling TS11 - COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | 2 | IB*2.0*577_T11 | 2017-07-07 | Mary Simons | Pass | NA
TC619: CIT eBilling TS11 - COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC620: CIT eBilling TS12 – Ambulance Field Lengths - US 127 | 2 | IB*2.0*577_T7 | 2017-05-11 | Lisa Bruno | Pass | NA
TC620: CIT eBilling TS12 – Ambulance Field Lengths - US 127 | 2 | IB*2.0*577_T11 | 2017-06-30 | Lisa Bruno | Pass | NA
TC620: CIT eBilling TS12 – Ambulance Field Lengths - US 127 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC621 - CIT eBilling TS13 – Lab or Service Facility Field Lengths US 127 | 2 | IB*2.0*577_ T7 | 2017-05-17 | Lisa Bruno | Pass | NA
TC621: CIT eBilling TS13 – Lab or Service Facility Field Lengths US 127 | 2 | IB*2.0*577_T11 | 2017-06-30 | Lisa Bruno | Pass | NA
TC621: CIT eBilling TS13 – Lab or Service Facility Field Lengths US 127 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC622: CIT eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | 2 | IB*2.0*577_T9 | 2017-06-06 | Lisa Bruno | Pass | NA
TC621: CIT eBilling TS13 – Lab or Service Facility Field Lengths US 127 | 2 | IB*2.0*577_T11 | 2017-06-30 | Lisa Bruno | Pass | NA
TC621: CIT eBilling TS13 – Lab or Service Facility Field Lengths US 127 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC623 - CIT eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | 2 | IB*2.0*577_ T1 | 2017-06-13 | Mary Simons | Pass | NA
TC623 - CIT eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | 2 | IB*2.0*577_ T11 | 2017-06-30 | Mary Simons | Pass | NA
TC623 - CIT eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC624: CIT eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | 2 | IB*2.0*577_ T1 | 2017-04-28 | Mary Simons | Pass | NA
TC624: CIT eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | 2 | IB*2.0*577_ T11 | 2017-06-30 | Mary Simons | Pass | NA
TC624: CIT eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC625: CIT eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_ T1 | 2017-04-28 | Mary Simons | Pass | NA
TC625: CIT eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_ T11 | 2017-06-30 | Mary Simons | Pass | NA
TC625: CIT eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC628: CIT eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_ T1 | 2017-04-28 | Mary Simons | Pass | NA
TC628: CIT eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_ T11 | 2017-06-30 | Mary Simons | Pass | NA
TC628: CIT eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T7 | 2017-05-17 | Lisa Bruno | Fail | DE85
TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T7 | 2017-05-17 | Lisa Bruno | Pass | NA
TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T11 | 2017-06-27 | Lisa Duncan | Fail | DE197 UAT
TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T11 | 2017-06-27 | Lisa Duncan | Pass | NA
TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T11 | 2017-06-26 | Mary Simons | Pass | NA
TC629 - CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC630 - CIT eBilling TS20 – Unit or Basis for Measurements Code (Inst) US11 | 2 | IB*2.0*577_T7 | 2017-05-17 | Lisa Bruno | Pass | NA
TC630: CIT eBilling TS20 – Unit or Basis for Measurements Code (Inst) US11 | 2 | IB*2.0*577_T11 | 2017-07-05 | Lisa Bruno | Pass | NA
TC630: CIT eBilling TS20 – Unit or Basis for Measurements Code (Inst) US11 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC742: SQA eBilling - TS20b – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_T7 | 2017-05-17 | Mary Simons | Pass | NA
TC742: SQA eBilling - TS20b – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_ T11 | 2017-07-05 | Mary Simons | Pass | NA
TC743: CIT eBilling - TS20b – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_ T7 | 2017-05-16 | Lisa Bruno | Pass | NA
TC743: CIT eBilling - TS20b – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_ T11 | 2017-07-05 | Lisa Bruno | Pass | NA
TC743: CIT eBilling - TS20b – Unit or Basis for Measurements Code (Inst) US1166 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC800 - SQA eBilling TS21 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T9 | 2017-06-13 | Mary Simons | Pass | NA
TC800 - SQA eBilling TS21 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T11 | 2017-07-05 | Mary Simons | Pass | NA
TC800 - SQA eBilling TS21 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC801 - SQA eBilling TS22 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T9 | 2017-06-13 | Mary Simons | Pass | NA
TC801 - SQA eBilling TS22 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T11 | 2017-07-05 | Mary Simons | Pass | NA
TC801 - SQA eBilling TS22 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC803 - SQA eBilling TS23 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T9 | 2017-06-13 | Mary Simons | Pass | NA
TC803 - SQA eBilling TS23 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T11 | 2017-07-05 | Mary Simons | Pass | NA
TC803 - SQA eBilling TS23 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC804 - SQA eBilling TS24 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T9 | 2017-06-13 | Lisa Bruno | Pass | NA
TC804 - SQA eBilling TS24 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T11 | 2017-07-05 | Lisa Bruno | Pass | NA
TC804 - SQA eBilling TS24 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC805: SQA eBilling TS25 Payer ID Report - US976 | 2 | IB*2.0*577_T5 | 2017-06-05 | Mary Simons | Fail | DE129
TC805: SQA eBilling TS25 Payer ID Report - US976 | 2 | IB*2.0*577_T6 | 2017-06-05 | Mary Simons | Pass | NA
TC805: SQA eBilling TS25 Payer ID Report - US976 | 2 | IB*2.0*577_T9 | 2017-06-13 | Mary Simons | Fail | DE152
TC805: SQA eBilling TS25 Payer ID Report - US976 | 2 | IB*2.0*577_T10 | 2017-06-14 | Mary Simons | Pass | NA
TC805: SQA eBilling TS25 Payer ID Report - US976 | 2 | IB*2.0*577_T11 | 2017-07-11 | Mary Simons | Pass | NA
TC805: SQA eBilling TS25 Payer ID Report - US976 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA
TC807 - CIT eBilling TS21 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T10 | 2017-06-21 | Lisa Bruno | Pass | NA
TC807 - CIT eBilling TS21 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T11 | 2017-07-05 | Lisa Bruno | Pass | NA
TC807 - CIT eBilling TS21 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC808 - CIT eBilling TS22 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T10 | 2017-06-23 | Lisa Bruno | Pass | NA
TC808 - CIT eBilling TS22 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T11 | 2017-07-05 | Lisa Bruno | Pass | NA
TC808 - CIT eBilling TS22 Store Payer IDs (Prof) - US129 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC810: CIT eBilling TS25 Payer ID Report - US976 | 2 | IB*2.0*577_T10 | 2017-06-23 | Lisa Bruno | Pass | NA
TC810: CIT eBilling TS25 Payer ID Report - US976 | 2 | IB*2.0*577_T11 | 2017-07-05 | Lisa Bruno | Pass | NA
TC810: CIT eBilling TS25 Payer ID Report - US976 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC811 - CIT eBilling TS24 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T10 | 2017-06-23 | Lisa Bruno | Pass | NA
TC811 - CIT eBilling TS24 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T11 | 2017-07-05 | Lisa Bruno | Pass | NA
TC811 - CIT eBilling TS24 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC812 - CIT eBilling TS23 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T10 | 2017-06-21 | Lisa Bruno | Pass | NA
TC812 - CIT eBilling TS23 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T11 | 2017-07-05 | Lisa Bruno | Pass | NA
TC812 - CIT eBilling TS23 Store Payer IDs (Inst) - US129 | 2 | IB*2.0*577_T13 | 2017-09-20 | CJ Minch | Pass | NA
TC1160 - SQA eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | 2 | IB*2.0*577_T10 | 2017-06-21 | Lisa Bruno | Pass | NA
TC1160 - SQA eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | 2 | IB*2.0*577_T11 | 2017-07-05 | Lisa Bruno | Pass | NA
TC1160 - SQA eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | 2 | IB*2.0*577_T13 | 2017-09-21 | Mary Simons | Pass | NA