## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 7 and Build 8 IB*2.0*623 Defect Log
July 2019
Version 2.0

## Revision History
Revision History
Date | Version | Description | Author
May 2019 | 1 | Initial Version | Jane Balchunas
July 2019 | 2 | Updated with Defect found in IOC testing | Jane Balchunas

## Defect Log
Defect ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
DE842 | NA | CIT - Secondary Payer IDs_Create Both Secondary and Primary Record Correction US 3994 | 3 - Medium | Closed | 7/10/2018 Found in IB*2.0*623_T1 | US 3994 - Secondary Payer IDs | TC3415: CIT-eBilling TAS US3994-TS1–SYS Updates Claim Office ID When One Does Not Exist_US3994_Prod Only | 7/17/2018 Verified in IB*2.0*623_T2
DE854 | NA | CIT-Populate "OldValue" Column when No Room for Claim Office ID US3994 ID | 3 - Medium | Closed | 7/12/2018 Found in IB*2.0*623_T3 | US 3994 - Secondary Payer IDs | TC3416: CIT-eBilling-TS2–SYS Displays Original Claim Office ID When One Exists–Prod Only_US3994 | 7/17/2018 Verified in IB*2.0*623_T4
DE871 | NA | UAT - INS record for SNF -Unit of service | 3 - Medium | Closed | 7/19/2018 Found in IB*2.0*623_T5 | US9 - Transmitting SNF Claims with Appropriate Revenue (USEB-16) | TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 | 8/2/2018 Verified in IB*2.0*623_T7 | UAT defect
DE883 | NA | CIT - Dental Mock up Item 24 not pulling correct date | 3 - Medium | Closed | 7/31/2018 Found in IB*2.0*623_T7 | US1108: Enter/Edit Dental Claims | TC1250: CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 8/7/2018 Verified in IB*2.0*623_T8
DE884 | NA | CIT - Dental Mock up Item 29a is not pulling any data | 3 - Medium | Closed | 7/30/2018 Found in IB*2.0*623_T6 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 8/7/2018 Verified in IB*2.0*623_T8
DE885 | NA | CIT - Mock up Dental Item 35 no number | 3 - Medium | Closed | 7/30/2018 Found in IB*2.0*623_T6 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 8/7/2018 Verified in IB*2.0*623_T8
DE891 | NA | CIT - Rendering needes to be changed to Rendering or Assistant Surgeon | 3 - Medium | Closed | 7/31/2018 Found in IB*2.0*623_T6 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 8/2/2018 Verified in IB*2.0*623_T7
DE892 | NA | CIT-Alternate Payer ID Not Transmitting to Secondary Claim_US4100 | 2 - High | Closed | 7/31/2018 Found in IB*2.0*623_T6 | US4100: Alternate Payer ID | TC3493: CIT-eBilling-TS1-Alternate Inst Payer IDs-US4100 | 8/31/2018 Verified in IB*2.0*623_T9
DE896 | NA | UAT: Add Legend to Report for No Room to Update Data | 3 - Medium | Closed | 8/1/2018 Found in IB*2.0*623_T6 | US3995: Payer ID Report-Secondary Payer ID | TC3419: CIT-eBilling-TC1-HCCH Payer ID Report–Claims Office IDs–Prod Only_US3995 | 8/7/2018 Verified in IB*2.0*623_T8 | UAT defect
DE907 | NA | CIT - Dental Claim Mock up - Column 31 does not display the correct amount | 3 - Medium | Closed | 8/6/2018 Found in IB*2.0*623_T7 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 8/7/2018 Verified in IB*2.0*623_T8
DE908 | NA | CIT - Columns are too close together | 3 - Medium | Closed | 8/7/2018 Found in IB*2.0*623_T7 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 8/28/2018 Verified in IB*2.0*623_T9
DE915 | NA | CIT - Dental Claim Mock up 29A and 34A | 4 - Low | Closed | 8/15/2018 Found in IB*2.0*623_T8 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 8/28/2018 Verified in IB*2.0*623_T9
DE918 | NA | CIT - Dental Mock up the tooth information for print was not get reset between procedure lines | 4 - Low | Closed | 8/20/2018 Found in IB*2.0*623_T8 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 9/19/2018 Verified in IB*2.0*623_T14
DE920 | NA | CIT - Inst Claim Alt Payer ID Not Populated to Sec Claim_US4100 | 3 - Medium | Closed | 8/20/2018 Found in IB*2.0*623_T8 | US4100: Alternate Payer ID | TS3494: CIT-eBilling-TS2-Alternate Prof Payer IDs-US4100 | 8/22/2018 Verified in IB*2.0*623_T9
DE934 | NA | CIT - Dental Mock up display change | 4 - Low | Closed | 9/10/2018 Found in IB*2.0*623_T11 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 9/19/2018 Verified in IB*2.0*623_T14
DE940 | NA | CIT - Dental Mock up - Col 29a | 3 - Medium | Closed | 9/13/2018 Found in IB*2.0*623_T12 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 9/17/2018 Verified in IB*2.0*623_T13
DE941 | NA | CIT - Dental Mock up - General help | 4 - Low | Closed | 9/13/2018 Found in IB*2.0*623_T12 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 9/19/2018 Verified in IB*2.0*623_T14
DE944 | NA | CIT - Dental Mock up A is not displayed in 29a | 3 - Medium | Closed | 9/13/2018 Found in IB*2.0*623_T12 | US4055: Dental Claims Mock-up | TC3437: CIT - eBilling - Dental Claim Mock up US4055 | 9/19/2018 Verified in IB*2.0*623_T14
DE1071 | NA | CIT - ROI bill creates fatal system error when closing bill | 2 - High | Closed | 1/7/2019 Found in IB*2.0*623_T15 | US4995 - Implement Release of Information | TC3967 - CIT - eBilling Implement Release of Information – Outpatient 1500 Professional Claim_US4995 and TC3968: CIT-eBilling Implement Release of Information – Outpatient UB04 Institutional Claim | 1/11/2019 Verified in IB*2.0*623_T16
DE1074 | NA | CIT-CSA Worklist MINIMUM # OF DAYS Not working | 3 - Medium | Closed | 1/7/2019 Found in IB*2.0*623_T15 | US141 - CSA_Separate TRICARE/CHAMPVA (USEB-43) | TC4102: CIT-eBilling-TS1- Generate CSA Worklists by Non-MCCF, MCCF or Both Rate Types_US141 | 1/15/2019 Verified in IB*2.0*623_T16
DE1075 | NA | CIT - Final Bill screen is incorrect | 4 - Low | Closed | 1/14/2019 Found in IB*2.0*623_T16 | US3346 - [Continued] Transmit 837 Transactions Through New Platform | TC3405: CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 3/22/2019 Verified in IB*2.0*623_T20
DE1076 | NA | CIT - system is unable to id the correct Batch number if in a queue for FHIR and the switch is set to off | 3 - Medium | Closed | 1/16/2019 Found in IB*2.0*623_T16 | US3346 - [Continued] Transmit 837 Transactions Through New Platform | TC3405: CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 3/22/2019 Verified in IB*2.0*623_T20
DE1305 | NA | CIT- eBilling -Imprecise dates in claims | 2 - High | Closed | 4/11/2019 Found in IB*2.0*623 T20 | US3346 - [Continued] Transmit 837 Transactions Through New Platform | TC3405: CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 6/20/2019 Verified in IB*2.0*623 T22
DE1440 | NA | IOC - IB*2.0*623 v21 IOC Patch Tracking Message | 3 - Medium | Closed | 5/28/2019 Found in IB*2.0*623 T21 | US3346 - [Continued] Transmit 837 Transactions Through New Platform | TC3405: CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7/9/2019 Verified in IB*2.0*623 T23
DE1441 | NA | IOC - RPC Packaging Error | 3 - Medium | Closed | 5/28/2019 Found in IB*2.0*623 T21 | US3346 - [Continued] Transmit 837 Transactions Through New Platform | TC3405: CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 6/20/2019 Verified in IB*2.0*623 T22
DE1476 | NA | IOC - Claim had structure under procedure code without actual procedure code | 3 - Medium | Closed | 6/26/2019 Found in IB*2.0*623 T21 | US3346 - [Continued] Transmit 837 Transactions Through New Platform | TC3405: CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7/9/2019 Verified in IB*2.0*623 T23
DE1483 | NA | IOC - Error or routine to be matched: IBCEFP | 3 - Medium | Closed | 7/1/2019 Found in IB*2.0*623 T21 | US3346 - [Continued] Transmit 837 Transactions Through New Platform | TC3405: CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7/9/2019 Verified in IB*2.0*623 T23
DE1495 | NA | IOC - lookup by external claim number when getting claims in FHIR bundled format | 3 - Medium | Closed | 7/1/2019 Found in IB*2.0*623 T21 | US3346 - [Continued] Transmit 837 Transactions Through New Platform | TC3405: CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7/9/2019 Verified in IB*2.0*623 T23
DE1497 | NA | IOC - Alow claims to be sent in RCB even if Test | 3 - Medium | Closed | 7/1/2019 Found in IB*2.0*623 T21 | US3346 - [Continued] Transmit 837 Transactions Through New Platform | TC3405: CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7/9/2019 Verified in IB*2.0*623 T23
DE1499 | NA | IOC - When FHIR retransmits live claims as test, EOB information received for payers | 3 - Medium | Closed | 7/1/2019 Found in IB*2.0*623 T21 | US3346 - [Continued] Transmit 837 Transactions Through New Platform | TC3405: CIT - eBilling - Transmit 837 Transactions Through New Platform - Outpatient UB04– US3346 | 7/9/2019 Verified in IB*2.0*623 T23