## TAS Product Risk Report - eBill
Type | Id | Precision | Probability | Impact | Summary | Description | Modified Date | Follow-up Date | Owned By | Filed Against
Risk | 543208 | Medium | 60% - Moderate | 40% - Low | eBilling Build 2 IOC On time Start | If the completion of all the steps from sign off through national release of eBilling Build 1 has an additional delay of even one day, then the planned start of Build 2 IOC in production accounts could be delayed due to the tight time frame created with earlier delay in production and test account installation. | 2017-06-26 11:44 | 2017-07-21 11:00 | Lewis, Heather | eBilling
Risk | 498601 | Medium | 60% - Moderate | 60% - Moderate | eBilling Parallel Activities | If Warranty defects occur on one build and/or IOC defects occur on a second build, then development work on a third build may be temporarily suspended while prioritized defect repair activity monopolizes environment occupancy. | 2017-06-20 20:51 | 2017-09-29 11:00 | Cramblet, Paul | eBilling
Risk | 482213 | Medium | 40% - Low | 80% - High | eBilling Sprint Regression Testing | If CIT and SQA testing is limited to current sprint changes and does not include additional layers of regression to confirm earlier sprint work is unharmed, then the stabilization sprint may provide inadequate time before the build end date to repair and retest defects found as a result of all sprints finally being tested together. | 2017-05-18 15:56 | 2017-12-29 11:00 | Cramblet, Paul | eBilling
Risk | 498627 | Medium | 60% - Moderate | 60% - Moderate | IOC Environment Patch Stack | If TAS VistA patches are installed on IOC production servers where VistA patching is six weeks more current than the servers with which the TAS patch was tested, then interdependent processing flow defects may be found that could not have been found in the delivery environments. | 2017-04-10 18:24 | 2017-12-29 11:00 | Cramblet, Paul | All VistA Products