## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 3 and Build 4 IB*2.0*592 Test Execution Log
December 2017
Version 3.0

## Revision History
Revision History
Date | Version | Description | Author
November 2017 | 1 | Initial Version for MOU review. | Jane Balchunas
November 2017 | 2 | Deleted Defects DE321 and DE410 for US2503, and deleted DE382 for US2487, per eBiz changing the functionality of Blds. 3&4 to only send the NPI for Dental transactions. | Jane Balchunas
December 2017 | 3 | Updated with test results for final build testing. | Jane Balchunas

## Test Execution Log
Test Case ID | Build | Build Exectued | Date Executed | Tested By | Test Results (P/F) | Defect ID (Failed Tests)
TS14 – Regression Insurance Co ID Default US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Anne DeBacker | Pass | NA
TS14 – Regression Insurance Co ID Default US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-06 | Anne DeBacker | Pass | NA
TS15 – Regression Ins Co ID Parameters US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Anne DeBacker | Pass | NA
TS15 – Regression Ins Co ID Parameters US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-07 | Anne DeBacker | Pass | NA
TS16 – Regression Billing Provider Secondary IDs US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Anne DeBacker | Pass | NA
TS16 – Regression Billing Provider Secondary IDs US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-07 | Anne DeBacker | Pass | NA
TS17 – Regression Additional Billing Provider Secondary IDs US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Anne DeBacker | Pass | NA
TS17 – Regression Additional Billing Provider Secondary IDs US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-11 | Anne DeBacker | Pass | NA
TS34 – Regression Ins Co VA Lab/Facilitiy IDs US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Anne DeBacker | Pass | NA
TS34 – Regression Ins Co VA Lab/Facilitiy IDs US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-11 | Anne DeBacker | Pass | NA
TS27 – Regression VA Provider’s Own IDs US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Jane Balchunas | Fail | DE418
TS27 – Regression VA Provider’s Own IDs US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-05 | Jane Balchunas | Pass | NA
TS28 – Regression VA Provider’s Insurance IDs US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Jane Balchunas | Pass | NA
TS28 – Regression VA Provider’s Insurance IDs US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-12 | Jane Balchunas | Pass | NA
TS29 – Regression Care Units US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Jane Balchunas | Pass | NA
TS29 – Regression Care Units US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-12 | Jane Balchunas | Pass | NA
TS30 – Regression Non-VA Provider’s Own IDs US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Jane Balchunas | Pass | NA
TS30 – Regression Non-VA Provider’s Own IDs US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-13 | Jane Balchunas | Pass | NA
TS31 – Regression Non-VA Provider’s Ins IDs US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Jane Balchunas | Pass | NA
TS31 – Regression Non-VA Provider’s Ins IDs US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-13 | Jane Balchunas | Pass | NA
TS32 – Regression Non-VA Facility’s Own IDs US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Jane Balchunas | Pass | NA
TS32 – Regression Non-VA Facility’s Own IDs US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-11 | Jane Balchunas | Pass | NA
TS33 – Regression Non-VA Facility’s Ins IDs US3528 | 3&4 | IB*2.0*592_T9 | 2017-12-01 | Jane Balchunas | Pass | NA
TS33 – Regression Non-VA Facility’s Ins IDs US3528 | 3&4 | IB*2.0*592_T10 | 2017-12-11 | Jane Balchunas | Pass | NA
TC1221 - CIT eBilling TS9 Validate the new ‘Dental’ claim indicator displays on the TPJI screen when there is an Active Outpatient Dental Claim (O/D). US14 | 3&4 | IB*2.0*592_T1 | 2017-09-07 | CJ Minch | Pass | NA
TC1221 - CIT eBilling TS9 Validate the new ‘Dental’ claim indicator displays on the TPJI screen when there is an Active Outpatient Dental Claim (O/D). US14 | 3&4 | IB*2.0*592_T2 | 2017-10-04 | Jane Balchunas | Pass | NA
TC1221 - CIT eBilling TS9 Validate the new ‘Dental’ claim indicator displays on the TPJI screen when there is an Active Outpatient Dental Claim (O/D). US14 | 3&4 | IB*2.0*592_T10 | 2017-12-14 | CJ Minch | Pass | NA
TC1222 - CIT eBilling TS9 TPJI_Dental Indicator US14 | 3&4 | IB*2.0*592_T1 | 2017-09-21 | CJ Minch | Pass | NA
TC1222 - CIT eBilling TS9 TPJI_Dental Indicator US14 | 3&4 | IB*2.0*592_T2 | 2017-10-04 | Jane Balchunas | Pass | NA
TC1222 - CIT eBilling TS9 TPJI_Dental Indicator US14 | 3&4 | IB*2.0*592_T10 | 2017-12-12 | CJ Minch | Pass | NA
TC1227 - CIT eBilling TS eBilling create a CMS 1500 Outpatient Professional Claim - Regression US1108 & US131 | 3&4 | IB*2.0*592_T2 | 2017-10-04 | Jane Balchunas | Pass | NA
TC1227 - CIT eBilling TS eBilling create a CMS 1500 Outpatient Professional Claim - Regression US1108 & US131 | 3&4 | IB*2.0*592_T10 | 2017-12-12 | CJ Minch | Pass | NA
TC1228 - CIT eBilling TS Create a UB04 (Inst) Claim - Regression US1108 & US131 | 3&4 | IB*2.0*592_T2 | 2017-10-04 | CJ Minch | Pass | NA
TC1228 - CIT eBilling TS Create a UB04 (Inst) Claim - Regression US1108 & US131 | 3&4 | IB*2.0*592_T10 | 12/15/207 | Jane Balchunas | Pass | NA
TC1229 - CIT eBilling Create an Institutional Claim via Autobiller - Regression US1109 | 3&4 | IB*2.0*592_T2 | 2017-10-04 | CJ Minch | Pass | NA
TC1229 - CIT eBilling Create an Institutional Claim via Autobiller - Regression US1109 | 3&4 | IB*2.0*592_T10 | 12/18/207 | Jane Balchunas | Pass | NA
TC1237 - CIT eBilling TS Validate the existing claims Still Display on the TPJI screen when there is an active Outpatient Dental Claim (O/D) Regression US14 | 3&4 | IB*2.0*592_T2 | 2017-10-04 | CJ Minch | Pass | NA
TC1237 - CIT eBilling TS Validate the existing claims Still Display on the TPJI screen when there is an active Outpatient Dental Claim (O/D) Regression US14 | 3&4 | IB*2.0*592_T10 | 12/18/207 | Jane Balchunas | Pass | NA
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-08-29 | Mary Simons | Fail | DE269
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-08-31 | Mary Simons | Fail | DE292
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-08-31 | Mary Simons | Fail | DE293
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T3 | 2017-10-03 | Mary Simons | Fail | DE336
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T3 | 2017-10-03 | Mary Simons | Fail | DE337
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T3 | 2017-10-03 | Mary Simons | Fail | DE338
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T4 | 2017-10-18 | Mary Simons | Fail | DE350
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T4 | 2017-10-19 | Jane Balchunas | Fail | DE351
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T5 | 2017-10-30 | Jane Balchunas | Fail | DE359
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T6 | 2017-10-31 | Jane Balchunas | Fail | DE365
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T6 | 2017-11-03 | Mary Simons | Fail | DE374
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T6 | 2017-11-09 | Mary Simons | Fail | DE379
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T7 | 2017-11-09 | Mary Simons | Fail | DE381
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T8 | 2017-11-16 | Jane Balchunas | Pass | NA
TC1249 - CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 3&4 | IB*2.0*592_T10 | 2017-12-13 | CJ Minch | Pass | NA
TC1250 - CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-09-05 | Mary Simons | Fail | DE295
TC1250 - CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-09-05 | Mary Simons | Fail | DE296
TC1250 - CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 3&4 | IB*2.0*592_T4 | 2017-10-26 | Mary Simons | Fail | DE357
TC1250 - CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 3&4 | IB*2.0*592_T5 | 2017-10-26 | Jane Balchunas | Pass | NA
TC1250 - CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 3&4 | IB*2.0*592_T7 | 2017-11-06 | Jane Balchunas | Pass | NA
TC1250 - CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 3&4 | IB*2.0*592_T10 | 12/14/207 | CJ Minch | Pass | NA
TC1251 - CIT eBilling TS4 Fatal Error Rend/AsstSurg - US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-09-01 | Mary Simons | Fail | DE294
TC1251 - CIT eBilling TS4 Fatal Error Rend/AsstSurg - US1108 and US131 | 3&4 | IB*2.0*592_T2 | 2017-09-15 | CJ Minch | Pass | NA
TC1251 - CIT eBilling TS4 Fatal Error Rend/AsstSurg - US1108 and US131 | 3&4 | IB*2.0*592_T4 | 2017-10-19 | Jane Balchunas | Pass | NA
TC1251 - CIT eBilling TS4 Fatal Error Rend/AsstSurg - US1108 and US131 | 3&4 | IB*2.0*592_T10 | 12/18/207 | CJ Minch | Pass | NA
TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-09-07 | Mary Simons | Fail | DE304
TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-09-08 | Mary Simons | Fail | DE305
TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 3&4 | IB*2.0*592_T2 | 2017-09-19 | Mary Simons | Fail | DE314
TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 3&4 | IB*2.0*592_T5 | 2017-10-26 | Mary Simons | Fail | DE358
TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 3&4 | IB*2.0*592_T6 | 2017-10-31 | Mary Simons | Fail | DE363
TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 3&4 | IB*2.0*592_T6 | 2017-10-31 | Mary Simons | Fail | DE373
TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 3&4 | IB*2.0*592_T7 | 2017-11-09 | Mary Simons | Fail | DE380
TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 3&4 | IB*2.0*592_T8 | 2017-11-28 | Mary Simons | Fail | DE411
TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 3&4 | IB*2.0*592_T9 | 2017-11-30 | CJ Minch | Pass | NA
TC1257 - CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 3&4 | IB*2.0*592_T10 | 2017-12-14 | CJ Minch | Pass | NA
TC1258 - CIT eBilling TS5 Medicare Error for Dental US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-09-07 | Mary Simons | Pass | NA
TC1258 - CIT eBilling TS5 Medicare Error for Dental US1108 and US131 | 3&4 | IB*2.0*592_T4 | 2017-10-20 | Jane Balchunas | Pass | NA
TC1258 - CIT eBilling TS5 Medicare Error for Dental US1108 and US131 | 3&4 | IB*2.0*592_T7 | 2017-11-06 | Jane Balchunas | Pass | NA
TC1258 - CIT eBilling TS5 Medicare Error for Dental US1108 and US131 | 3&4 | IB*2.0*592_T10 | 2017-12-05 | CJ Minch | Pass | NA
TC1259 - CIT eBilling TS7 Dental Claim Creation - AutoBiller US1109 | 3&4 | IB*2.0*592_T2 | 2017-09-20 | Mary Simons | Fail | DE316
TC1259 - CIT eBilling TS7 Dental Claim Creation - AutoBiller US1109 | 3&4 | IB*2.0*592_T2 | 2017-09-21 | Mary Simons | Fail | DE318
TC1259 - CIT eBilling TS7 Dental Claim Creation - AutoBiller US1109 | 3&4 | IB*2.0*592_T2 | 2017-09-21 | CJ Minch | Pass | NA
TC1259 - CIT eBilling TS7 Dental Claim Creation - AutoBiller US1109 | 3&4 | IB*2.0*592_T10 | 2017-12-18 | CJ Minch | Pass | NA
TC1260 - CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-08-31 | Mary Simons | Fail | DE282
TC1260 - CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-08-31 | Mary Simons | Fail | DE291
TC1260 - CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 3&4 | IB*2.0*592_T3 | 2017-10-03 | Mary Simons | Fail | DE335
TC1260 - CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 3&4 | IB*2.0*592_T5 | 2017-10-23 | Mary Simons | Fail | DE354
TC1260 - CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 3&4 | IB*2.0*592_T5 | 2017-10-24 | Mary Simons | Fail | DE355
TC1260 - CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 3&4 | IB*2.0*592_T7 | 2017-11-09 | Mary Simons | Fail | DE384
TC1260 - CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 3&4 | IB*2.0*592_T8 | 2017-11-28 | CJ Minch | Pass | NA
TC1260 - CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 3&4 | IB*2.0*592_T10 | 2017-12-05 | CJ Minch | Pass | NA
TC1342 - CIT eBilling TS6 Copy New Dental Fields 1108 and US131 | 3&4 | IB*2.0*592_T1 | 2017-09-07 | CJ Minch | Pass | NA
TC1342 - CIT eBilling TS6 Copy New Dental Fields 1108 and US131 | 3&4 | IB*2.0*592_T7 | 2017-11-06 | Jane Balchunas | Pass | NA
TC1342 - CIT eBilling TS6 Copy New Dental Fields 1108 and US131 | 3&4 | IB*2.0*592_T10 | 2017-12-05 | CJ Minch | Pass | NA
TC1346 - CIT eBilling TS10 Insurance Co Editor (1) US2487 | 3&4 | IB*2.0*592_T1 | 2017-09-07 | CJ Minch | Pass | NA
TC1346 - CIT eBilling TS10 Insurance Co Editor (1) US2487 | 3&4 | IB*2.0*592_T10 | 2017-12-05 | Jane Balchunas | Pass | NA
TC1349 - CIT eBilling TS11 Insurance Co Editor (2) US2487 | 3&4 | IB*2.0*592_T3 | 2017-09-27 | CJ Minch | Pass | NA
TC1349 - CIT eBilling TS11 Insurance Co Editor (2) US2487 | 3&4 | IB*2.0*592_T10 | 2017-12-05 | Jane Balchunas | Pass | NA
TC1350 - CIT eBilling TS12 Dental Payer ID/Dental Address US2487 | 3&4 | IB*2.0*592_T8 | 2017-11-28 | Mary Simons | Fail | DE412
TC1350 - CIT eBilling TS12 Dental Payer ID/Dental Address US2487 | 3&4 | IB*2.0*592_T9 | 2017-11-30 | CJ Minch | Pass | NA
TC1350 - CIT eBilling TS12 Dental Payer ID/Dental Address US2487 | 3&4 | IB*2.0*592_T10 | 2017-12-12 | Jane Balchunas | Pass | NA
TC1351 - CIT eBilling TS13 No Dental Payer ID/No Dental Address US2487 | 3&4 | IB*2.0*592_T2 | 2017-09-21 | Mary Simons | Fail | DE319
TC1351 - CIT eBilling TS13 No Dental Payer ID/No Dental Address US2487 | 3&4 | IB*2.0*592_T2 | 2017-09-21 | Mary Simons | Fail | DE320
TC1351 - CIT eBilling TS13 No Dental Payer ID/No Dental Address US2487 | 3&4 | IB*2.0*592_T3 | 2017-09-27 | CJ Minch | Pass | NA
TC1351 - CIT eBilling TS13 No Dental Payer ID/No Dental Address US2487 | 3&4 | IB*2.0*592_T10 | 2017-12-11 | Jane Balchunas | Pass | NA
TC1618 - CIT eBilling TS18 MRW - Print MRA US2489 | 3&4 | IB*2.0*592_T1 | 2017-09-07 | Jane Balchunas | Pass | NA
TC1618 - CIT eBilling TS18 MRW - Print MRA US2489 | 3&4 | IB*2.0*592_T10 | 2017-12-08 | Jane Balchunas | Pass | NA
TC1619 - CIT eBilling TS19 CSA - Print EOB/MRA US2489 | 3&4 | IB*2.0*592_T1 | 2017-09-07 | Jane Balchunas | Pass | NA
TC1619 - CIT eBilling TS19 CSA - Print EOB/MRA US2489 | 3&4 | IB*2.0*592_T10 | 2017-12-07 | Jane Balchunas | Pass | NA
TC1621 - CIT eBilling TS21 EDI Claim Status Report_Dental US2488 | 3&4 | IB*2.0*592_T1 | 2017-09-07 | Jane Balchunas | Pass | NA
TC1621 - CIT eBilling TS21 EDI Claim Status Report_Dental US2488 | 3&4 | IB*2.0*592_T10 | 2017-12-07 | Jane Balchunas | Pass | NA
TC1622 - CIT eBilling TS22 RCB - View/Resubmit Claims_Dental US2488 | 3&4 | IB*2.0*592_T3 | 2017-09-25 | CJ Minch | Pass | NA
TC1622 - CIT eBilling TS22 RCB - View/Resubmit Claims_Dental US2488 | 3&4 | IB*2.0*592_T10 | 2017-12-13 | Jane Balchunas | Pass | NA
TC1623 - CIT eBilling TS23 RCB - REX – Ready for Extract Report_Dental US2488 | 3&4 | IB*2.0*592_T6 | 2017-10-31 | Jane Balchunas | Pass | NA
TC1623 - CIT eBilling TS23 RCB - REX – Ready for Extract Report_Dental US2488 | 3&4 | IB*2.0*592_T10 | 2017-12-11 | Jane Balchunas | Pass | NA
TC1624 - CIT eBilling TS24 RCB - VPE - View/Print EDI Bill Extract Data_Dental US2488 | 3&4 | IB*2.0*592_T6 | 2017-10-31 | Jane Balchunas | Pass | NA
TC1624 - CIT eBilling TS24 RCB - VPE - View/Print EDI Bill Extract Data_Dental US2488 | 3&4 | IB*2.0*592_T10 | 2017-12-12 | Jane Balchunas | Pass | NA
TC1626 - CIT eBilling TS26 - HCCH Payer ID Report US2488 | 3&4 | IB*2.0*592_T3 | 2017-09-21 | CJ Minch | Pass | NA
TC1626 - CIT eBilling TS26 - HCCH Payer ID Report US2488 | 3&4 | IB*2.0*592_T7 | 2017-11-09 | Mary Simons | Fail | DE383
TC1626 - CIT eBilling TS26 - HCCH Payer ID Report US2488 | 3&4 | IB*2.0*592_T8 | 2017-11-28 | Mary Simons | Pass | NA
TC1626 - CIT eBilling TS26 - HCCH Payer ID Report US2488 | 3&4 | IB*2.0*592_T10 | 2017-12-11 | Jane Balchunas | Pass | NA
TC2230 - CIT eBilling TS18 MRW - Print MRA US2489 - Regression | 3&4 | IB*2.0*592_T2 | 2017-10-04 | Jane Balchunas | Pass | NA
TC2230 - CIT eBilling TS18 MRW - Print MRA US2489 - Regression | 3&4 | IB*2.0*592_T10 | 2017-12-11 | CJ Minch | Pass | NA
TC2231 - CIT eBilling US2488 - Update Reports - Form Type J430D - Regression Not applicable Brand New Dental Form | 3&4 | IB*2.0*592_T10 | NA | NA | NA | NA
TC2232 - CIT eBilling US2487 - Insurance Company Entry/Edit - Dental - Regression Not applicable Defined for the Brand New Dental Form | 3&4 | IB*2.0*592_T10 | NA | NA | NA | NA