## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 3 and Build 4 IB*2.0*592 Defect Log
December 2017
Version 3.0

## Revision History
Revision History
Date | Version | Description | Author
November 2017 | 1 | Initial Draft version for review | Jane Balchunas
November 2017 | 2 | Deleted Defects DE321 and DE410 for US2503, and deleted DE382 for US2487, per eBiz changing the functionality of Blds. 3&4 to only send the NPI for Dental transactions. | Jane Balchunas
December 2017 | 3 | Updated with final build test defect test results | Jane Balchunas

## Defect Log
Defect ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
DE269 | NA | CIT Property/Casualty Number Missing | 3 - Medium | Closed | 8/29/2017 Found in B*2.0*592_T1 | US1108: Enter/Edit Dental Claims | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 9/19/2017 Fixed in IB*2.0*592_T2
DE282 | NA | CIT - Cannot create Batch (US131) | 3 - Medium | Closed | 8/31/2017 Found in B*2.0*592_T1 | US131: Create 837D Transaction | TC1260: CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 9/19/2017 Fixed in IB*2.0*592_T2
DE291 | NA | CIT - eBilling IB*592 -837 Records Record (1131) | 3 - Medium | Closed | 8/31/2017 Found in B*2.0*592_T1 | US131: Create 837D Transaction | TC1260: CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 9/19/2017 Fixed in IB*2.0*592_T2
DE292 | NA | CIT- eBilling IB*592 - Report Type Wrap (US 1108) | 3 - Medium | Closed | 8/31/2017 Found in B*2.0*592_T1 | US1108: Enter/Edit Dental Claims | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 9/19/2017 Fixed in IB*2.0*592_T2
DE293 | NA | CIT - Report Type Missing (US 1108) | 3 - Medium | Closed | 8/31/2017 Found in B*2.0*592_T1 | US1108: Enter/Edit Dental Claims | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 9/19/2017 Fixed in IB*2.0*592_T2
DE294 | NA | CIT -eBilling IB*592 0 Missing Payer ID Warning (US1108) | 3 - Medium | NA | 9/1/2017 Found in B*2.0*592_T1 | US1108: Enter/Edit Dental Claims | TC1251: CIT eBilling TS4 Fatal Error Rend/AsstSurg - US1108 and US131 | 9/15/2017 Not a Defect
DE295 | NA | CIT - Change TX Indicator Display/Answer (US1108) | 3 - Medium | Closed | 9/5/2017 Found in B*2.0*592_T1 | US1108: Enter/Edit Dental Claims | TC1250: CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 9/20/2017 Fixed in IB*2.0*592_T2
DE296 | NA | CIT - Remove 2300 DTP (435) (US131) | 3 - Medium | Closed | 9/5/2017 Found in B*2.0*592_T1 | US131: Create 837D Transaction | TC1250: CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 9/20/2017 Fixed in IB*2.0*592_T2
DE304 | NA | CIT - Tooth Number Field (US1108) | 3- Medium | Closed | 9/6/2017 Found in B*2.0*592_T1 | US1108: Enter/Edit Dental Claims | TC1257: CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 9/20/2017 Fixed in IB*2.0*592_T2
DE305 | NA | CIT - RCB Change Prompt (US2488) | 3 - Medium | Closed | 9/8/2017 Found in B*2.0*592_T1 | US1108: Enter/Edit Dental Claims | TC1257: CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 9/20/2017 Fixed In IB*2.0*592_T2
DE314 | NA | CIT - Form Type Column adjustment | 2 - Low | Closed | 9/19/2017 Found in B*2.0*592_T2 | US2488: Update Reports - Form Type J430D | TC1622: CIT eBilling TS22 RCB - View/Resubmit Claims_Dental US2488 | 9/26/2017 Fixed in IB*2.0*592_T3
DE316 | NA | CIT - AutoBiller Dental Visit Type | 3 - Medium | Closed | 9/20/2017 Found in B*2.0*592_T2 | US1109: Create Dental Form/Update Autobiller | TC1259: CIT eBilling TS7 Dental Claim Creation - AutoBiller US1109 | 9/26/2017 Fixed in IB*2.0*592_T3
DE318 | NA | CIT - AutoBiller Results (US1109) | 3 - Medium | Closed | 9/19/2017 Found in B*2.0*592_T2 | US1109: Create Dental Form/Update Autobiller | TC1259: CIT eBilling TS7 Dental Claim Creation - AutoBiller US1109 | 9/21/2017 Fixed in IB*2.0*592_T2
DE319 | NA | CIT - Dental Addresses Action (US2487) | 3 - Medium | Closed | 9/21/2017 Found in B*2.0*592_T2 | US2487: Insurance Company Entry/Edit - Dental | TC1351: CIT eBilling TS13 No Dental Payer ID/No Dental Address US2487 | 9/27/2017 Fixed in IB*2.0*592_T3
DE320 | NA | CIT - Billing Address Listman Screen (US2487) | 3 - Medium | Closed | 9/21/2017 Found in B*2.0*592_T2 | US2487: Insurance Company Entry/Edit - Dental | TC1351: CIT eBilling TS13 No Dental Payer ID/No Dental Address US2487 | 9/27/2017 Fixed in IB*2.0*592_T3
DE335 | NA | CIT - Store HCCH Payer ID_Dental (US131) | 3 - Medium | Closed | 10/3/2017 Found in IB*2.0*592_T3 | US131: Create 837D Transaction | TC1260: CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 10/24/2017 Fixed in IB*2.0*592_T5
DE336 | NA | CIT - Screen 10 Provider Funtion (US1108) | 3 - Medium | Closed | 10/3/2017 Found in IB*2.0*592_T3 | US1108: Enter/Edit Dental Claims | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 10/18/2017 Fixed in IB*2.0*592_T4
DE337 | NA | CIT - Procedure Description Missing (US1108) | 3 - Medium | Closed | 10/3/2017 Found in IB*2.0*592_T3 | US1108: Enter/Edit Dental Claims | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 10/18/2017 Fixed in IB*2.0*592_T4
DE338 | NA | CIT - Roll Up Procedures (US1108) | 3 - Medium | Closed | 10/6/2017 Found in IB*2.0*592_T3 | US1108: Enter/Edit Dental Claims | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 10/18/2017 Fixed in IB*2.0*592_T4
DE350 | NA | CIT - Missing LICN (LDAT Record) US1108 | 3 - Medium | Closed | 10/18/2017 Found in IB*2.0*592_T4 | US1108: Enter/Edit Dental Claims | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 10/26/2017 Fixed in IB*2.0*592_T5
DE351 | NA | CIT - Dental Claim Note Length off | 3 - Medium | Closed | 10/20/2017 Found in IB*2.0*592_T4 | US1108: Enter/Edit Dental Claims | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 10/31/2017 Fixed in IB*2.0*592_T5
DE354 | NA | CIT - No LL POS if CL POS Present - US131 | 3 - Medium | Closed | 10/23/2017 Found in B*2.0*592_T4 | US131: Create 837D Transaction | TC1260: CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 11/2/2017 Fixed in IB*20*592_T6
DE355 | NA | CIT - Suppress Billing Provider Taxonomy - US131 | 3 - Medium | Closed | 10/23/2017 Found in B*2.0*592_T4 | US131: Create 837D Transaction | TC1260: CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 11/2/2017 Fixed in IB*20*592_T6
DE357 | NA | CIT - Error Message Wrap - US1108 | 3 - Medium | Closed | 10/26/2017 Found in B*2.0*592_T4 | US1108: Enter/Edit Dental Claims | TC1250: CIT eBilling TS2 Manual Dental Claim – Claim Level(1) US1108 and US131 | 10/31/2017 Fixed in IB*2.0*592_T5
DE358 | NA | CIT - Claim Providers Error Conditions - US1108 | 3 - Medium | Closed | 10/26/2017 Found in B*2.0*592_T5 | US1108: Enter/Edit Dental Claims | TC1257: CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 11/2/2017 Fixed in IB*20*592_T6
DE359 | NA | CIT - Dental Claim Note Wrapping Issue - US1108 | 3 - Medium | Closed | 10/26/2017 Found in B*2.0*592_T5 | US1108: Enter/Edit Dental Claims | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 11/7/2017 Fixed in IB*20*592_T6
DE363 | NA | CIT - Disable Outside Facility - US1108 | 3 - Medium | Closed | 11/1/2017 Found in B*2.0*592_T6 | US1108: Enter/Edit Dental Claims | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 11/28/2017 Fixed in IB*20*592_T8
DE365 | NA | CIT - ACN and Transmission Types - US131 | 3 - Medium | Closed | 11/1/2017 Found in B*2.0*592_T6 | US131: Create 837D Transaction | TC1260: CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 11/14/2017 Fixed in IB*20*592_T7
DE373 | NA | CIT - Accident Data - US1108 | 3 - Medium | Closed | 11/3/2017 Found in B*2.0*592_T6 | US1108: Enter/Edit Dental Claims | TC1257: CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 11/14/2017 Fixed in IB*20*592_T7
DE374 | NA | CIT - Transmission Method - US1108 | 4 - Medium | Closed | 11/3/2017 Found in B*2.0*592_T6 | US1108: Enter/Edit Dental Claims | TC1257: CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US132 | 11/9/2017 Fixed in IB*20*592_T7
DE379 | NA | CIT - Insurance Type Code – Medicare Only (US131) | 4 - Medium | Closed | 11/9/2017 Found in IB*2.0*592_T6 | US131: Create 837D Transaction | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 11/13/2017 Fixed in IB*20*592_T7
DE380 | NA | CIT - Other Payer Provider DD (US131) | 4 - Medium | Closed | 11/9/2017 Found in IB*2.0*592_T6 | US131: Create 837D Transaction | TC1257: CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 11/28/2017 Fixed in IB*20*592_T8
DE381 | NA | CIT - Occurrance Code List - US131 | 4 - Medium | Closed | 11/9/2017 Found in IB*2.0*592_T7 | US131: Create 837D Transaction | TC1249: CIT eBilling TS1 Manual Dental Claim – Line Level US1108 and US131 | 11/16/2017 Fixed in IB*20*592_T8
DE383 | NA | CIT - HCCH Report and 277STAT - US2488 | 4 - Medium | Closed | 11/13/2017 Found in IB*2.0*592_T7 | US2488: Update Reports - Form Type J430D | TC1626: CIT eBilling TS26 - HCCH Payer ID Report US2488 | 11/28/2017 Fixed in IB*20*592_T8
DE384 | NA | CIT - COB Management WL - US1108/US131 | 4 - Medium | Closed | 11/13/2017 Found in IB*2.0*592_T7 | US1108: Enter/Edit Dental Claims | TC1260: CIT eBilling TS8 Complete Dental Claim US1108 and US131 | 11/28/2017 Fixed in IB*20*592_T8
DE411 | NA | UAT - Help for Tooth Number - US1108 | 4 - Medium | Closed | 11/28/2017 Found in IB*20*592_T8 | US1108: Enter/Edit Dental Claims | TC1257: CIT eBilling TS3 Manual Dental Claim – Claim Level(2) US1108 and US131 | 11/30/2017 Fixed in IB*20*592_T9
DE412 | NA | UAT - Dental Primary Payer ID Display - US2487 | 4 - Medium | Closed | 11/28/2017 Found in IB*20*592_T8 | US2487: Insurance Company Entry/Edit - Dental | TC1350: CIT eBilling TS12 Dental Payer ID/Dental US2487 | 11/30/2017 Fixed in IB*20*592_T9
DE418 | NA | CIT - Provider ID Maintenance Main Menu Spelling Error | 4 - Medium | Closed | 11/30/2017 Found in IB*20*592_T9 | US3528: Provider ID Maintenance_Dental_Removal | TS27: Regression VA Provider’s Own ID | 12/5/2017 Fixed in IB*20*592_T10