## Slide 1
Medical Care Collections Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite Phase 1 Health Administrative Product Enhancements (HAPE)
Critical Decision Point 2
Build 22 01/23/2018
Notes: CD 2 Briefing is to request Approval to Deploy a specific product or Build.
As you move through the slides, provide the level of information appropriate for this decision briefing and for the specific capabilities being deployed as a result of this briefing. Do not focus on past increments or older project history unless it is directly relevant to the deployment decision you are seeking for this briefing.
When going through this presentation, please do not read the slides, draw the senior leaders attention to any questions or issues that you have. Please present this template at a high level.

## Slide 2: Project Information
Full Project Name: | Medical Care Collections Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite Phase 1
OI&T Portfolio Name: | Health
OI&T Program Name: | Medical Care Collection Fund (MCCF)
OIT Project Manager Name: | Winston Noronha (FMLA); Toby Rudik (Acting)
OI&T Program Manager Name: | Toby Rudik
OI&T Portfolio Director Name: | Katrina Tuisamatatele
Account Manager: | Alan Constantian
Product Owner: | Frank Annecchini
Receiving / Sustainment Organization: | Mary Caulfield (VistA) Steve Levy (Enterprise Cloud)
Project ID: | A605116880 VIPR # V16-00159-000
Release Agent: | Wayne Ledford
ISO: | Michael Lumby
VA Exhibit 300 Name: | Medical Legacy
OIT Budget Operating Plan Number: | 17-Health-192, 17-Health-241, 18-Health-19
Enterprise Project Structure Number: | FY18 & FY17-08-03-02-05-01-004; FY16-01-02-03-20-11-009
Notes: If you had a different EPS number in a previous Fiscal Year please list the previous EPS number and current EPS number.

## Slide 3: Purpose
Winston Noronha, for Medical Care Collection Fund Electronic Data Interchange (EDI) Transaction Applications Suite Phase 1, eBilling, is requesting VIP Critical Decision 2 Approval to deploy VistA patch IB*2*592 Initial Operating Capability (IOC) production at our 5 test sites Tomah, WI, Birmingham, AL, Kansas City, MO, Martinsburg, WV, Albuquerque, NM. The patch has completed Component Integration Testing (CIT), Software Quality Assurance (SQA) Testing, User Acceptance Testing (UAT) and has been Installed in the test account at Birmingham.
The project is using the IOC model.
The National Release is expected on 6/27/2018.
Notes: This slide should identify the project name, nature of the CD2 request (IOC evaluation or full release) and a statement that the project has competed the requirements to request deployment.

## Slide 4: Release(s)
Release Name | Start Date | End Date | Resources Needed in order to Deploy | Resources Assigned to Deployment | Total number of sites to which this Build is deploying
IOC Release for eBilling IB*2.0*592 | 01/31/18 | 05/31/18 | 4 | 4 | 5: Tomah, WI, Birmingham, AL, Kansas City, MO, Martinsburg, WV, Albuquerque, NM
What is the capability being deployed into the production environment?
Support for a new Electronic Dental Claim Transaction:
· Third Party Joint Inquiry Dental Indication
· Create the Dental x12 Claim Transaction (837D)
· Ability to Enter/Edit Dental claims
· Create Dental Claims in Autobiller
· Add Dental to Insurance Company Entry/Edit
· Update Reports to include dental Claim Form (Type J430D)
· Update Provider ID Maintenance to include Dental
· Update printing option on Medicare management Worklist (MRW)
Notes: Release Name: The title of the Release Name.
Start Date: Date planned to start Release.
End Date: Date planned to complete Release.
Resources Needed: Required manpower to complete the Release.
Resources Assigned: Manpower that is assigned to the Release.
Site Count: Total number of sites you are deploying to.

## Slide 5: Release Dependencies
      Are there any concerns with your dependencies that will keep the project from deploying? None known.
Release Dependency | Description | Status of Dependency | Notes or Concerns (availability, funding, resources, etc)
Strategic Alignment Technology Team (STAT) Review Requirements for VistA Maintenance (formerly AERB) | There is an outstanding question about whether the STAT review requirements apply to VistA maintenance patches. Therefore this review has not occurred for this patch. | Escalated to EPMO | Recommend release to IOC while this is resolved.
Notes: List the current project or product deployment dependencies—these can be technical, h/w, s/w resources, training, schedule-- or any level or type of deployment dependency.
Provide information on all projects that have a dependency related to the success of this project and all projects upon which this project depends.
Upstream dependencies: other projects that impact the success of the projects under review. This includes deliverables, software, hardware, or infrastructure components' that another project will be providing the project under review.
Downstream dependencies: other projects that are impacted the success of the projects under review. This includes deliverables, software, hardware, or infrastructure components' that this project will provide other projects.

## Slide 6: CD 2 Checklist
Requirements | Yes | No | Notes
Is all applicable data and documentation entered into the Rational Tool Suite? | X |  | 
Does the Release Agent recommend the release into IOC / Production? | X |  | 
Are all hardware or software contracts and licenses documented and ready to transfer to the appropriate support entity? |  | X | N/A VistA Maintenance
What is the status of your Section 508 Compliance? If you have a waiver when does it expire? |  |  | Exception approved..
Are there outstanding security issues? If so, what is the remediation plan? Security Impact Assessment (SIA) complete? |  | X | N/A VistA
Notes: List the status of the documentation. VIP artifacts should be stored in RTC (for PD projects) or the standard repository for the organization (i.e., Workload Resource Tracking (WRT) for SDE projects).
POLARIS entries driven by the Veterans Focused Integration Process (VIP), may first be submitted at any time after Critical Decision #2, with the goal of meeting the two-to-four week request. This occurs during the Release Preparation phase of VIP. Final review occurs at the semi-weekly calendar meetings, in the week prior to the scheduled release.
It is suggested that a POLARIS entry be conducted as early as possible.

## Slide 7: CD 2 Checklist
Requirements | Yes | No | Notes
Does your project have any open Severity 1 or 2 Defects? |  | X | <If Yes, enter total severity 1 and total severity 2 in Notes.> Be prepared to respond on how you will communicate the severity to the end users.
Did you address all of the high and critical findings in Risk Vision? |  | X | N/A VistA
Pick one of the 3 scenarios: Using a system with an existing ATO & do not need to modify it Using a system with an existing ATO & had to modify the ATO Created a new ATO |  |  | Using a system (VistA) with an existing ATO & do not need to modify it.
Notes: List the status of the documentation. VIP artifacts should be stored in RTC (for PD projects) or the standard repository for the organization (i.e., Workload Resource Tracking (WRT) for SDE projects).

## Slide 8: CD 2 Decision
Decision | Yes | No | Comments
Portfolio Director approves the product to deploy into IOC/ Production or National Release |  |  | Katrina Tuisamatatele
Product Owner approves the product to deploy into IOC/ Production or National Release |  |  | Frank Annecchini
Receiving / Sustainment Organization approves the product to deploy into IOC/ Production or National Release |  |  | Mary Caulfield (VistA)
Notes: Fill out this slide after the decision is made during your CD Event.

## Slide 9: Version Tracking
Version 1 – Initial Version
Version 2 – Slide 1: Added Portfolio name
Slide 2: Added Receiving / Sustainment Organization name
Changed Business Owner to Product Owner.
Slide 5&6: CD2 Checklist: Removed POLARIS requirement
Version 3 - Slide 5: Changed the word “Approve” to “Recommend” for the
Release Team
Version 3.5 - Slide 5: Removed OIS check list, it is not a requirement.
Version 4.0 - Slide 5: Changed “Release Team” to Release Agent” To clarify
who/what this question is.
Version 4.1 - Added instructions for filling out Slides One & Three.
Slides Two & Seven: Changed “Portfolio Manager” to “Portfolio
Director”
Notes: Please remove this slide after review and before submitting for your CD Event.