## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eInsurance Build 5 and Build 6 IB*5.0&6.0*608 Requirements Traceability Matrix
October 2018
Version 2.0

## Revision History
Revision History
Date | Version | Description | Author
June 2018 | 1 | Initial Version | Jane Balchunas
October 2018 | 2 | Updated to include retesting of Blds 3/4 | Jane Balchunas

## RTM
Bus Req Doc | Epic ID | Epic Summary | Req Doc | User Story ID | User Story Summary | Testable | Accptance Criteria (for Not Testable US) | Release to be Implemented | Build(s) | Test Case ID (for Testable US0) | Pass/Fail/Not Tested | Build Last Tested | Comments Failed US- Defect ID Not Testable Comment, Not Tested Comment
US3 - CMN Oxygen and EPN Nutrition
N/A | US3 | EPIC - Maintain eBilling Compliance | N/A | US3 - CMN Oxygen and EPN Nutrition | As a biller, I need the ability to enter the required data for an Oxygen Certificate of Medical Necessity (CMN) (CMS-484.3) or an Enteral and Parenteral Nutrition CMN (CMS-10126) when completing a professional bill for Durable Medical Equipment (DME). I then need the ability to transmit the professional claim with the CMN data in the proprietary 837-P transaction to the Financial Services Center (FSC). | Yes | N/A | IB*2.0*608 | 5&6 | TC2762 - CIT - CMN Enteral and Parenteral Nutrition – Enteral | Pass | IB*2.0*608_T31 | DE633, DE667, DE674, DE675, DE678
N/A | US3 | EPIC - Maintain eBilling Compliance | N/A | US3 - CMN Oxygen and EPN Nutrition | As a biller, I need the ability to enter the required data for an Oxygen Certificate of Medical Necessity (CMN) (CMS-484.3) or an Enteral and Parenteral Nutrition CMN (CMS-10126) when completing a professional bill for Durable Medical Equipment (DME). I then need the ability to transmit the professional claim with the CMN data in the proprietary 837-P transaction to the Financial Services Center (FSC). | Yes | N/A | IB*2.0*608 | 5&6 | TC2764 - CIT eBilling – CMN Oxygen | Pass | IB*2.0*608_T31 | DE560, DE565, DE589, DE603, DE607, DE619, DE631, DE683, DE698
N/A | US3 | EPIC - Maintain eBilling Compliance | N/A | US3 - CMN Oxygen and EPN Nutrition | As a biller, I need the ability to enter the required data for an Oxygen Certificate of Medical Necessity (CMN) (CMS-484.3) or an Enteral and Parenteral Nutrition CMN (CMS-10126) when completing a professional bill for Durable Medical Equipment (DME). I then need the ability to transmit the professional claim with the CMN data in the proprietary 837-P transaction to the Financial Services Center (FSC). | Yes | N/A | IB*2.0*608 | 5&6 | TC2898 - CIT - CMN Enteral and Parenteral Nutrition - Both_Regression | Pass | IB*2.0*608_T31 | NA
N/A | US3 | EPIC - Maintain eBilling Compliance | N/A | US3 - CMN Oxygen and EPN Nutrition | As a biller, I need the ability to enter the required data for an Oxygen Certificate of Medical Necessity (CMN) (CMS-484.3) or an Enteral and Parenteral Nutrition CMN (CMS-10126) when completing a professional bill for Durable Medical Equipment (DME). I then need the ability to transmit the professional claim with the CMN data in the proprietary 837-P transaction to the Financial Services Center (FSC). | Yes | N/A | IB*2.0*608 | 5&6 | TC2904 - CIT - 1.1 CMN Enteral and Parenteral Nutrition – Parenteral | Pass | IB*2.0*608_T31 | NA
N/A | US3 | EPIC - Maintain eBilling Compliance | N/A | US3 - CMN Oxygen and EPN Nutrition | As a biller, I need the ability to enter the required data for an Oxygen Certificate of Medical Necessity (CMN) (CMS-484.3) or an Enteral and Parenteral Nutrition CMN (CMS-10126) when completing a professional bill for Durable Medical Equipment (DME). I then need the ability to transmit the professional claim with the CMN data in the proprietary 837-P transaction to the Financial Services Center (FSC). | Yes | N/A | IB*2.0*608 | 5&6 | TC2905 - CIT - 1.1 CMN Enteral and Parenteral Nutrition – Both | Pass | IB*2.0*608_T31 | NA
N/A | US3 | EPIC - Maintain eBilling Compliance | N/A | US3 - CMN Oxygen and EPN Nutrition | As a biller, I need the ability to enter the required data for an Oxygen Certificate of Medical Necessity (CMN) (CMS-484.3) or an Enteral and Parenteral Nutrition CMN (CMS-10126) when completing a professional bill for Durable Medical Equipment (DME). I then need the ability to transmit the professional claim with the CMN data in the proprietary 837-P transaction to the Financial Services Center (FSC). | Yes | N/A | IB*2.0*608 | 5&6 | TC2906 - CIT - CMN Enteral and Parenteral Nutrition – Parenteral - Regression | Pass | IB*2.0*608_T31 | NA
N/A | US3 | EPIC - Maintain eBilling Compliance | N/A | US3 - CMN Oxygen and EPN Nutrition | As a biller, I need the ability to enter the required data for an Oxygen Certificate of Medical Necessity (CMN) (CMS-484.3) or an Enteral and Parenteral Nutrition CMN (CMS-10126) when completing a professional bill for Durable Medical Equipment (DME). I then need the ability to transmit the professional claim with the CMN data in the proprietary 837-P transaction to the Financial Services Center (FSC). | Yes | N/A | IB*2.0*608 | 5&6 | TC2927 - CIT - CMN Enteral and Parenteral Nutrition – Enteral - Regression | Pass | IB*2.0*608_T31 | NA
N/A | US3 | EPIC - Maintain eBilling Compliance | N/A | US3 - CMN Oxygen and EPN Nutrition | As a biller, I need the ability to enter the required data for an Oxygen Certificate of Medical Necessity (CMN) (CMS-484.3) or an Enteral and Parenteral Nutrition CMN (CMS-10126) when completing a professional bill for Durable Medical Equipment (DME). I then need the ability to transmit the professional claim with the CMN data in the proprietary 837-P transaction to the Financial Services Center (FSC). | Yes | N/A | IB*2.0*608 | 5&6 | TC2928 - CIT - CMN Oxgyen_Regression | Pass | IB*2.0*608_T31 | NA
US9 - Transmitting SNF Claims with Appropriate Revenue (USEB-16)
N/A | US9 | EPIC - Maintain eBilling Compliance | N/A | US9 - Transmitting SNF Claims with Appropriate Revenue (USEB-16) | To resolve this request, the following bullet items need to be performed and the following rules need to be followed: o Receiver ID must be “ENVOYH” or “PARTA” o Payer Responsibility Sequence must be “P” o Payer Primary ID must be “12M61” o Claim must be a SNF Claim o UB-04 Bill Classification must be either 1, 2 or 3 If the above rules are met, then add new VCx, INS and LDAT output lines. And, the following routine (^IBCEF2) will be modified to validate a claim for the rules mentioned above. | Yes | N/A | IB*2.0*608 | 5&6 | TC2619: CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 | Pass | IB*2.0*608_T31 | DE526
N/A | US9 | EPIC - Maintain eBilling Compliance | N/A | US9 - Transmitting SNF Claims with Appropriate Revenue (USEB-16) | To resolve this request, the following bullet items need to be performed and the following rules need to be followed: o Receiver ID must be “ENVOYH” or “PARTA” o Payer Responsibility Sequence must be “P” o Payer Primary ID must be “12M61” o Claim must be a SNF Claim o UB-04 Bill Classification must be either 1, 2 or 3 If the above rules are met, then add new VCx, INS and LDAT output lines. And, the following routine (^IBCEF2) will be modified to validate a claim for the rules mentioned above. | Yes | N/A | IB*2.0*608 | 5&6 | TC2895 - CIT - Transmitting SNF Claims with Appropriate Revenue Codes – US9 Regression | Pass | IB*2.0*608_T31 | NA
US142 - Add T for Transmitted to RCB Screen
N/A | US142 | EPIC - Update eBilling Functionality | N/A | US142 - non-MCCF Unbilled Amounts Report | As an Integrated Billing Supervisor or clerk at a Veterans Affairs Medical Center (VAMC), I want to be able to sort the Unbilled Amounts Report such that I only see the following types of claims based on the selected Rate Type(s): CHAMPVA REIMB. INS. CHAMPVA TRICARE REIMB. INS. TRICARE INTERAGENCY INELIGIBLE | Yes | N/A | IB*2.0*608 | 5&6 | TC2233 - CIT eBilling TS1–Re-generate Unbilled Amounts Reports to Sort by Non-MCCF or MCCF Claim Types | Pass | IB*2.0*608_T31 | DE527, DE530
N/A | US142 | EPIC - Update eBilling Functionality | N/A | US142 - non-MCCF Unbilled Amounts Report | As an Integrated Billing Supervisor or clerk at a Veterans Affairs Medical Center (VAMC), I want to be able to sort the Unbilled Amounts Report such that I only see the following types of claims based on the selected Rate Type(s): CHAMPVA REIMB. INS. CHAMPVA TRICARE REIMB. INS. TRICARE INTERAGENCY INELIGIBLE | Yes | N/A | IB*2.0*608 | 5&6 | TC2234 - CIT eBilling TS2 – Re-generate Unbilled Amounts Reports to Sort by Both MCCF and Non-MCCF Claims US142_Regression | Pass | IB*2.0*608_T31 | DE487, DE528, DE748
US1908 - Add T for Transmitted to RCB Screen
N/A | US1908 | EPIC - Maintain eBilling Compliance | N/A | US1908 - Add T for Transmitted to RCB Screen | As a staff member at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to see an explanation of the “T” that displays next to entries in the View/Resubmit Claims - Live or Test option when I elect to view previously printed claims. | Yes | N/A | IB*2.0*608 | 5&6 | TC2180 - CIT eBilling TS1 - RCB Header Displays T for Test Claims – Printed Claims US1908 | Pass | IB*2.0*608_T31 | N/A
N/A | US1908 | EPIC - Maintain eBilling Compliance | N/A | US1908 - Add T for Transmitted to RCB Screen | As a staff member at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to see an explanation of the “T” that displays next to entries in the View/Resubmit Claims - Live or Test option when I elect to view previously printed claims. | Yes | N/A | IB*2.0*608 | 5&6 | TC2229 - CIT eBilling TS2 - RCB Legend Displays Explanation for T – Report US1908 - Regression | Pass | IB*2.0*608_T31 | NA
US 1909 - Remove Ability to Define Insurance Company as non-EDI
N/A | US1909 | EPIC - Maintain eBilling Compliance | N/A | US 1909 - Remove Ability to Define Insurance Company as non-EDI | As a staff member at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I no longer want the ability to define an Insurance Company as one that only accepts printed claims. I would also like to be able to receive a one-time report from each site showing me the value of the field that determines whether an Insurance Company is active for Electronic Data Interchange (EDI). | Yes | N/A | IB*2.0*608 | 5&6 | TC2179 - CIT eBilling TS1 Removal of EDI-Transmit option NO TS1 US1909 | Pass | IB*2.0*608_T31 | DE463, DE464, DE566
N/A | US1909 | EPIC - Maintain eBilling Compliance | N/A | US 1909 - Remove Ability to Define Insurance Company as non-EDI | As a staff member at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I no longer want the ability to define an Insurance Company as one that only accepts printed claims. I would also like to be able to receive a one-time report from each site showing me the value of the field that determines whether an Insurance Company is active for Electronic Data Interchange (EDI). | Yes | N/A | IB*2.0*608 | 5&6 | TC2236 - CIT eBilling TS1 Removal of EDI-Transmit option NO US1909_Regression |  | IB*2.0*608_T31 | NA
US 2486 - RCB – Match COB Data to Payer Sequence
N/A | US2486 | EPIC - Update eBilling Functionality | N/A | US2486 - RCB – Match COB Data to Payer Sequence | As a staff member at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to resubmit, to the Test queue, a claim using the option View/Resubmit Claims - Live or Test and have only the Coordination of Benefits (COB) data that is correct for the payer sequence be included in the transaction. | Yes | N/A | IB*2.0*608 | 5&6 | TC2789 - CIT eBilling TAS US2486-TS3 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev only_Regression | Pass | IB*2.0*608_T31 | NA
N/A | US2486 | EPIC - Update eBilling Functionality | N/A | US2486 - RCB – Match COB Data to Payer Sequence | As a staff member at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to resubmit, to the Test queue, a claim using the option View/Resubmit Claims - Live or Test and have only the Coordination of Benefits (COB) data that is correct for the payer sequence be included in the transaction. | Yes | N/A | IB*2.0*608 | 5&6 | TC2790 - eBilling TAS US2486-TS1 RCB - Match COB Data to Payer Sequence_Resubmit Claims_Dev_only | Pass | IB*2.0*608_T31 | DE624, DE630, DE638
N/A | US2486 | EPIC - Update eBilling Functionality | N/A | US2486 - RCB – Match COB Data to Payer Sequence | As a staff member at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to resubmit, to the Test queue, a claim using the option View/Resubmit Claims - Live or Test and have only the Coordination of Benefits (COB) data that is correct for the payer sequence be included in the transaction. | Yes | N/A | IB*2.0*608 | 5&6 | TC2791 - eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message | Pass | IB*2.0*608_T31 | DE618, DE659
N/A | US2486 | EPIC - Update eBilling Functionality | N/A | US2486 - RCB – Match COB Data to Payer Sequence | As a staff member at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to resubmit, to the Test queue, a claim using the option View/Resubmit Claims - Live or Test and have only the Coordination of Benefits (COB) data that is correct for the payer sequence be included in the transaction. | Yes | N/A | IB*2.0*608 | 5&6 | TC2792 - eBilling TAS US2486-TS2 RCB - Match COB Data to Payer Sequence_Skipped Production Claims Message_Regression | Pass | IB*2.0*608_T31 | NA
US2599 - Non-MCCF Pay-to Provider
N/A | US2599 | EPIC - Update eBilling Functionality | N/A | US2599 - Non-MCCF Pay-to Provider | As an Insurance Clerk or Integrated Billing Supervisor at a Veterans Affairs Medical Center (VAMC), I want to be able to define one or more Rate Types for which the non-MCCF Pay-to Address (formerly the TRICARE Pay-to Address) will be used on claims with one of those Rate Types. | Yes | N/A | IB*2.0*608 | 5&6 | TC2620: CIT - Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 | Pass | IB*2.0*608_T31 | DE536, DE570, DE572
N/A | US2599 | EPIC - Update eBilling Functionality | N/A | US2599 - Non-MCCF Pay-to Provider | As an Insurance Clerk or Integrated Billing Supervisor at a Veterans Affairs Medical Center (VAMC), I want to be able to define one or more Rate Types for which the non-MCCF Pay-to Address (formerly the TRICARE Pay-to Address) will be used on claims with one of those Rate Types. | Yes | N/A | IB*2.0*608 | 5&6 | TC2621 - CIT - Non-MCCF Pay-to Address Rate Types – CMS1500 | Pass | IB*2.0*608_T31 | NA
N/A | US2599 | EPIC - Update eBilling Functionality | N/A | US2599 - Non-MCCF Pay-to Provider | As an Insurance Clerk or Integrated Billing Supervisor at a Veterans Affairs Medical Center (VAMC), I want to be able to define one or more Rate Types for which the non-MCCF Pay-to Address (formerly the TRICARE Pay-to Address) will be used on claims with one of those Rate Types. | Yes | N/A | IB*2.0*608 | 5&6 | TC2622: CIT - Non-MCCF Pay-to Address Rate Types – UB04 - US2599 | Pass | IB*2.0*608_T31 | DE535
N/A | US2599 | EPIC - Update eBilling Functionality | N/A | US2599 - Non-MCCF Pay-to Provider | As an Insurance Clerk or Integrated Billing Supervisor at a Veterans Affairs Medical Center (VAMC), I want to be able to define one or more Rate Types for which the non-MCCF Pay-to Address (formerly the TRICARE Pay-to Address) will be used on claims with one of those Rate Types. | Yes | N/A | IB*2.0*608 | 5&6 | TC2623: CIT - Non-MCCF Pay-to Address Rate Types – J430D - US2599 | Pass | IB*2.0*608_T31 | DE537
N/A | US2599 | EPIC - Update eBilling Functionality | N/A | US2599 - Non-MCCF Pay-to Provider | As an Insurance Clerk or Integrated Billing Supervisor at a Veterans Affairs Medical Center (VAMC), I want to be able to define one or more Rate Types for which the non-MCCF Pay-to Address (formerly the TRICARE Pay-to Address) will be used on claims with one of those Rate Types. | Yes | N/A | IB*2.0*608 | 5&6 | TC2896 - CIT - 6.1 Non-MCCF Pay-to Address Rate Types – Editing Rate Types US2599 Regression | Pass | IB*2.0*608_T31 | NA
N/A | US2599 | EPIC - Update eBilling Functionality | N/A | US2599 - Non-MCCF Pay-to Provider | As an Insurance Clerk or Integrated Billing Supervisor at a Veterans Affairs Medical Center (VAMC), I want to be able to define one or more Rate Types for which the non-MCCF Pay-to Address (formerly the TRICARE Pay-to Address) will be used on claims with one of those Rate Types. | Yes | N/A | IB*2.0*608 | 5&6 | tc2897 - CIT - 6.1 Non-MCCF Pay-to Address Rate Types – UB04 - US2599 Regression | Pass | IB*2.0*608_T31 | NA
N/A | US2599 | EPIC - Update eBilling Functionality | N/A | US2599 - Non-MCCF Pay-to Provider | As an Insurance Clerk or Integrated Billing Supervisor at a Veterans Affairs Medical Center (VAMC), I want to be able to define one or more Rate Types for which the non-MCCF Pay-to Address (formerly the TRICARE Pay-to Address) will be used on claims with one of those Rate Types. | Yes | N/A | IB*2.0*608 | 5&6 | TC2901 - CIT - 6.2 Non-MCCF Pay-to Address Rate Types – CMS1500 Regression | Pass | IB*2.0*608_T31 | NA
N/A | US2599 | EPIC - Update eBilling Functionality | N/A | US2599 - Non-MCCF Pay-to Provider | As an Insurance Clerk or Integrated Billing Supervisor at a Veterans Affairs Medical Center (VAMC), I want to be able to define one or more Rate Types for which the non-MCCF Pay-to Address (formerly the TRICARE Pay-to Address) will be used on claims with one of those Rate Types. | Yes | N/A | IB*2.0*608 | 5&6 | TC2925 - CIT - Non-MCCF Pay-to Address Rate Types – J430D - US2599_Regression | Pass | IB*2.0*608_T31 | NA
US 3214 - Remove Fatal Error - Rendering Provider CMS 1500
N/A | US3214 | EPIC - Maintain eBilling Compliance | N/A | US3214 - Remove Fatal Error - Rendering Provider CMS 1500 | As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to authorize a professional Durable Medical Equipment (DME) claim without adding a Rendering Provider to the claim. I want to receive a non-fatal warning message reminding me that the Rendering Provider is normally required on a professional CMS 1500 claim. | Yes | N/A | IB*2.0*608 | 5&6 | TC2432 - CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214 | Pass | IB*2.0*608_T31 | DE502, DE503, DE509
N/A | US3214 | EPIC - Maintain eBilling Compliance | N/A | US3214 - Remove Fatal Error - Rendering Provider CMS 1500 | As a billing clerk at a VA Medical Center (VAMC) or Consolidated Patient Account Center (CPAC), I want to be able to authorize a professional Durable Medical Equipment (DME) claim without adding a Rendering Provider to the claim. I want to receive a non-fatal warning message reminding me that the Rendering Provider is normally required on a professional CMS 1500 claim. | Yes | N/A | IB*2.0*608 | 5&6 | TC2510 - CIT eBilling TS2 – Replace Fatal Error with Warning Msg for Rendering Provider on CMS 1500 US3214_Regression | Pass | IB*2.0*608_T31 | N/A