## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) eBilling Build 2 IB*2*577 Test Execution Log
July 6, 2017
Version 1.0

## Revision History
Revision History
Date | Version | Description | Author
2017-05-24 | 0.1 | Draft version - for preparation for MOU request | Lisa Bruno
2017-07-07 | 1 | Final version | Lisa Bruno

## Test Execution Log
Test Case | Build (Last Build: IB*2*577 T11) | Creation Date | Tester | Verdict
TC297: SQA eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | IB*2*577 T1 | 04/28/2017 08:26 AM EDT | Lisa Bruno | Pass
TC298: CIT eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | IB*2*577 T1 | 04/28/2017 08:23 AM EDT | Lisa Bruno | Pass
TC298: CIT eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 - Regression | IB*2*577 T11 | 07/07/2017 10:52 AM EDT | Mary Simons | Pass
TC301: SQA eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | IB*2*577 T1 | 04/28/2017 08:31 AM EDT | Mary Simons | Pass
TC303: SQA eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 | IB*2*577 T1 | 04/28/2017 08:32 AM EDT | Mary Simons | Pass
TC304: SQA eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 | IB*2*577 T1 | 04/28/2017 08:32 AM EDT | Mary Simons | Pass
TC306: SQA eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 | IB*2*577 T1 | 04/28/2017 08:33 AM EDT | Mary Simons | Pass
TC308: SQA eBilling TS8 COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 | IB*2*577 T1 | 04/28/2017 08:56 AM EDT | Lisa Bruno | Pass
TC317: SQA eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 | IB*2*577 T1 | 04/28/2017 08:57 AM EDT | Mary Simons | Pass
TC318: SQA eBilling TS11 COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 | IB*2*577 T1 | 04/28/2017 02:20 PM EDT | Mary Simons | Pass
TC573: SQA eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 | IB*2*577 T1 | 04/28/2017 08:31 AM EDT | Mary Simons | Pass
TC574: SQA eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 | IB*2*577 T1 | 04/28/2017 02:19 PM EDT | Mary Simons | Pass
TC594: SQA eBilling TS12 – Ambulance Field Lengths - US 127 | IB*2*577 T7 | 05/09/2017 03:31 PM EDT | Mary Simons | Pass
TC595: SQA eBilling TS13 – Lab or Service Facility Field Lengths - US127 | IB*2*577 T7 | 05/09/2017 02:13 PM EDT | Mary Simons | Fail
TC595: SQA eBilling TS13 – Lab or Service Facility Field Lengths - US127 | IB*2*577 T8 | 07/05/2017 11:18 AM EDT | Mary Simons | Pass
TC599: SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | IB*2*577 T3 | 05/03/2017 03:19 PM EDT | Mary Simons | Fail
TC599: SQA eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 | IB*2*577 T7 | 05/09/2017 03:40 PM EDT | Mary Simons | Pass
TC600: SQA eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | IB*2*577 T7 | 05/09/2017 03:41 PM EDT | Mary Simons | Pass
TC602: SQA eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 | IB*2*577 T7 | 05/09/2017 03:42 PM EDT | Mary Simons | Pass
TC603: SQA eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 | IB*2*577 T7 | 05/09/2017 03:47 PM EDT | Mary Simons | Pass
TC604: SQA eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 | IB*2*577 T7 | 05/09/2017 03:48 PM EDT | Mary Simons | Pass
TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | IB*2*577 T4 | 05/03/2017 06:15 PM EDT | Mary Simons | Fail
TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | IB*2*577 T5 | 05/04/2017 11:40 AM EDT | Mary Simons | Fail
TC605: SQA eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | IB*2*577 T7 | 05/09/2017 06:00 PM EDT | Mary Simons | Pass
TC606: SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | IB*2*577 T4 | 05/08/2017 06:00 PM EDT | Mary Simons | Fail
TC606: SQA eBilling TS20 – Unit or Basis for Measurements Code (Inst) US1166 | IB*2*577 T7 | 05/09/2017 06:09 PM EDT | Mary Simons | Pass
TC607: CIT eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 | IB*2*577 T 1 | 04/28/2017 08:22 AM EDT | Lisa Bruno | Pass
TC607: CIT eBilling TS1 COB Data in CLON’d Claims (Prim Medicare) – Inst - TAS US114 - Regression | IB*2*577 T11 | 07/07/2017 10:50 AM EDT | Mary Simons | Pass
TC610: SQA eBilling TS2 - COB Data in CLON’d Claims (Prim Medicare) - Prof TAS US114 | IB*2*577 T1 | 04/28/2017 08:26 AM EDT | Lisa Bruno | Pass
TC611: CIT eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 | IB*2*577 T1 | 04/28/2017 08:23 AM EDT | Lisa Bruno | Pass
TC611: CIT eBilling TS3 - COB Data in CLON’d Claims (Prim) - Prof - TAS US114 - Regression | IB*2*577 T11 | 07/07/2017 10:53 AM EDT | Mary Simons | Pass
TC612: CIT eBilling TS4 - COB Data in CLON’d Claims (Prim) - Inst TAS US114 - Regression | IB*2*577 T11 | 07/07/2017 10:53 AM EDT | Mary Simons | Pass
TC613: CIT eBilling TS5 - COB Data in CLON’d Claims (Sec Medicare) Professional - TAS US114 - Regression | IB*2*577 T11 | 07/07/2017 10:53 AM EDT | Mary Simons | Pass
TC614: CIT eBilling TS6 - COB Data in CLON’d Claims (Sec Medicare) – Inst - TAS US114 - Regression | IB*2*577 T11 | 07/07/2017 10:54 AM EDT | Mary Simons | Pass
TC615: CIT eBilling TS7 - COB Data in CLON’d Claims – Prof (Secondary) -TAS US114 - Regression | IB*2*577 T11 | 07/07/2017 10:54 AM EDT | Mary Simons | Pass
TC616: CIT eBilling TS8 - COB Data in CLON’d Claims (Secondary) – Inst - TAS US114 - Regression | IB*2*577 T11 | 07/07/2017 10:54 AM EDT | Mary Simons | Pass
TC617: CIT eBilling TS9 - COB Data in CLON’d Claims ( Medicare) - Prof TAS US114 - Regression | IB*2*577 T11 | 07/07/2017 10:55 AM EDT | Mary Simons | Pass
TC618: CIT eBilling TS10 - COB Data in CLON’d Claims ( Medicare) – Inst TAS US 114 - Regression | IB*2*577 T11 | 07/07/2017 10:55 AM EDT | Mary Simons | Pass
TC619: CIT eBilling TS11 - COB Data in CLON’d Claims (Tert Medicare) – Prof (Development Only) TAS US 114 - Regression | IB*2*577 T11 | 07/07/2017 10:56 AM EDT | Mary Simons | Pass
TC620: CIT eBilling TS12 – Ambulance Field Lengths - US 127 | IB*2*577 T7 | 05/11/2017 09:46 AM EDT | Lisa Bruno | Pass
TC620: CIT eBilling TS12 – Ambulance Field Lengths - US 127 | IB*2*577 T7 | 06/23/2017 01:27 PM EDT | Lisa Bruno | Pass
TC620: CIT eBilling TS12 – Ambulance Field Lengths - US 127 - Regression | IB*2*577 T11 | 06/30/2017 12:52 PM EDT | Lisa Bruno | Pass
TC621: CIT eBilling TS13 – Lab or Service Facility Field Lengths US 127 | IB*2*577 T7 | 05/17/2017 01:25 PM EDT | Lisa Bruno | Pass
TC621: CIT eBilling TS13 – Lab or Service Facility Field Lengths US 127 - Regression | IB*2*577 T11 | 06/30/2017 12:53 PM EDT | Lisa Bruno | Pass
TC622: CIT eBilling TS14 Authorization/Referral/P&C# Field Lengths US 127 - Regression | IB*2*577 T11 | 06/30/2017 12:53 PM EDT | Lisa Bruno | Pass
TC623: CIT eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 | IB*2*577 T7 | 06/13/2017 11:14 AM EDT | Lisa Bruno | Pass
TC623: CIT eBilling TS15 Pay-to Provider Field Lengths (Prof) US 127 - Regression | IB*2*577 T11 | 06/30/2017 12:53 PM EDT | Lisa Bruno | Pass
TC624: CIT eBilling TS16 – TRICARE Pay-to Provider Field Lengths (Prof) US127 - Regression | IB*2*577 T11 | 06/30/2017 12:52 PM EDT | Lisa Bruno | Pass
TC625: CIT eBilling TS17 – Pay-to Provider Field Lengths (Inst) US127 - Regression | IB*2*577 T11 | 06/30/2017 12:54 PM EDT | Lisa Bruno | Pass
TC628: CIT eBilling TS18 – TRICARE Pay-to Provider Field Lengths (Inst) US127 - Regression | IB*2*577 T11 | 06/30/2017 12:54 PM EDT | Lisa Bruno | Pass
TC629: CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 | IB*2*577 T7 | 05/17/2017 02:15 PM EDT | Lisa Bruno | Pass
TC629: CIT eBilling TS19 – Unit or Basis for Measurement Code (Prof) US11 - Regression | IB*2*577 T11 | 07/05/2017 12:43 PM EDT | Lisa Bruno | Pass
TC630: CIT eBilling TS20 – Unit or Basis for Measurements Code (Inst) US11 | IB*2*577 T7 | 05/17/2017 02:14 PM EDT | Lisa Bruno | Pass
TC630: CIT eBilling TS20 – Unit or Basis for Measurements Code (Inst) US11 - Regression | IB*2*577 T11 | 07/05/2017 01:00 PM EDT | Lisa Bruno | Pass
TC630: CIT eBilling TS20 – Unit or Basis for Measurements Code (Inst) US11 - Regression | IB*2*577 T11 | 07/05/2017 01:20 PM EDT | Lisa Bruno | Pass
TC742: SQA eBilling -US TS20b – Unit or Basis for Measurements Code (Inst) 1166 | IB*2*577 T7 | 07/05/2017 11:27 AM EDT | Mary Simons | Pass
TC743: CIT eBilling - TS20b – Unit or Basis for Measurements Code (Inst) US1166 | IB*2*577 T7 | 05/16/2017 08:34 AM EDT | Lisa Bruno | Pass
TC743: CIT eBilling - TS20b – Unit or Basis for Measurements Code (Inst) US1166 - Regression | IB*2*577 T11 | 07/05/2017 01:36 PM EDT | Lisa Bruno | Pass
TC800: SQA eBilling TS21 Store Payer IDs (Prof) - US129 | IB*2*577 T9 | 07/05/2017 11:15 AM EDT | Mary Simons | Pass
TC801: SQA eBilling TS22 Store Payer IDs (Prof) - US129 | IB*2*577 T9 | 07/05/2017 11:16 AM EDT | Mary Simons | Pass
TC803: SQA eBilling TS23 Store Payer IDs (Inst) - US129 | IB*2*577 T9 | 07/05/2017 11:14 AM EDT | Mary Simons | Pass
TC804: SQA eBilling TS24 Store Payer IDs (Inst) - US129 | IB*2*577 T9 | 07/05/2017 11:10 AM EDT | Mary Simons | Pass
TC805: SQA eBilling TS25 Payer ID Report - US976 | IB*2*577 T5 | 06/05/2017 10:12 AM EDT | Mary Simons | Fail
TC805: SQA eBilling TS25 Payer ID Report - US976 | IB*2*577 T6 | 06/05/2017 10:59 AM EDT | Mary Simons | Pass
TC805: SQA eBilling TS25 Payer ID Report - US976 | IB*2*577 T9 | 06/13/2017 02:34 PM EDT | Mary Simons | Fail
TC805: SQA eBilling TS25 Payer ID Report - US976 | IB*2*577 T10 | 06/14/2017 08:15 AM EDT | Mary Simons | Pass
TC807: CIT eBilling TS21 Store Payer IDs (Prof) - US129 | IB*2*577 T10 | 06/21/2017 10:00 AM EDT | Lisa Bruno | Pass
TC808: CIT eBilling TS22 Store Payer IDs (Prof) - US129 | IB*2*577 T10 | 06/23/2017 09:58 AM EDT | Lisa Bruno | Pass
TC810: CIT eBilling TS25 Payer ID Report - US976 | IB*2*577 T10 | 06/23/2017 01:26 PM EDT | Lisa Bruno | Pass
TC811: CIT eBilling TS24 Store Payer IDs (Inst) - US129 | IB*2*577 T10 | 06/23/2017 01:25 PM EDT | Lisa Bruno | Pass
TC812: CIT eBilling TS23 Store Payer IDs (Inst) - US129 | IB*2*577 T10 | 06/21/2017 10:08 AM EDT | Lisa Bruno | Pass
TC1152: CIT eBilling TS25 Payer ID Report - US976 - Regression Test Not Applicable - New Functionality | IB*2*577 T11 | 07/07/2017 1:24 PM EDT | Lisa Bruno | N/A
TC1153: CIT eBilling TS24 Store Payer IDs (Inst) - US129 - Regression Not Applicable - New Functionality | IB*2*577 T11 | 07/07/2017 1:26 PM EDT | Lisa Bruno | N/A