## risks with trigger (3)
Type | Id | Summary | Owned By | Status | Priority | Severity | Modified Date | Description | Risk Trigger | Risk Response | Risk Response Strategy | Follow-up Date
Risk | 498687 | US 118 Covered by Health Insurance Indicator Design not yet approved | Gomez, Enrique | New | Unassigned | 2 - High | 2017-04-11 12:14 | If US 118 Covered by Health Insurance Indicator is not design approved by 4/10/17, then the build 2 contents are at risk of not being delivered. | Last day of build 1 - if not approved will be unprepared for build 2. | Unassigned | Obtain Design approval before Build 2 begins. | 2017-04-14 11:00
Risk | 498627 | IOC Environment Patch Stack | Cramblet, Paul | Strategizing | 3 - Normal Queue | 3 - Medium | 2017-04-10 18:24 | If TAS VistA patches are installed on IOC production servers where VistA patching is six weeks more current than the servers with which the TAS patch was tested, then interdependent processing flow defects may be found that could not have been found in the delivery environments. | Any IOC or Warranty defect from processing with a patch that was not installed in the delivery environment (development through UAT) when the build completed the stabilization sprint. | Accept | At this time there is no plan to change the 2-week lag for deployed patch installations into the delivery environments. Effort is being made to reduce from 4 weeks to 2 weeks the time between patch build conclusion and patch IOC. Even that reduction leave a 4-week difference between the configuration used to test the patch and the IOC configuration in which the patch will be evaluated. No further compression of the timeline between patch build conclusion and patch IOC is planned. | 2017-12-29 11:00
Risk | 498601 | eBilling Parallel Activities | Cramblet, Paul | Strategizing | 3 - Normal Queue | 3 - Medium | 2017-04-10 17:09 | If Warranty defects occur on one build and/or IOC defects occur on a second build, then development work on a third build may be temporarily suspended while prioritized defect repair activity monopolizes environment occupancy. | Any occurrence of IOC defects or Warranty defects whose specifics necessitate current build environment displacement or work suspension. | Accept | This risk is accepted, because environments are insufficient to support parallel tracks. Lack of funding is the underlying cause, and workable solutions are limited. There is a slim possibility of using Albany accounts for development and a single Bay Pines account CHY17 for defect repair, but availability will depend on the specifics of the eBilling situation and delivery status of the other three eBusiness VistA products. (CHY17 is shared across all four VistA products.) There is also a slim possibility for limited use of the UAT environment to test IOC defects, depending on timing of defect discovery and specifics of the current build. To minimize IOC and Warranty defects to the extent possible, any that occur will be evaluated to determine why the defect was not found prior to production. When cause is inadequate test case(s) or inadequate environment setup, corrective action will be immediately taken. When cause is a payer specific situation impossible to detect without end-to-end testing, the ongoing gap will be documented. | 2017-09-29 11:00
Risk | 480406 | MCCF EDI TAS FY18 PMO Funding | Rudik, Toby | New | 3 - Normal Queue | 3 - Medium | 2017-03-14 09:37 | IF the MCCF EDI TAS PMO is not funded as requested for FY18 by 8/23/18, THEN the project’s ability to deliver products satisfying adaptive maintenance, product backlog requirements will be degraded. Increasing the risk of the VA becoming subject to financial penalties and reducing third-party payment collections, both of which would result in an adverse impact to funding patient care delivery. | The PMO support contract is not awarded by 8/23/18, one month prior to end of PoP. | Mitigate | Work with OI&T and VHA Management to assure UFR requests are identified and prepared for the Account Manager to act upon in advance of any deadlines. | 2018-08-23 11:00
Risk | 412803 | R0018 - EDE Funding | Rudik, Toby | Executing | 3 - Normal Queue | 3 - Medium | 2017-04-12 07:35 | If funding is not made available for EDE development and test environments, then the TAS pilot and subsequent eAdmin releases cannot move forward. | Inability to secure funding to cover the cost of ongoing EDE server usage and maintenance. | Mitigate | Determine current project funding and whether environment costs are covered on any specific BTT strips. Work with AITC to estimate cost for using AITC environments. Ensure project funding shortages are escalated to initiate intra or inter project fund transfers. | 2017-05-15 11:00
Risk | 498605 | ePharmacy Parallel Activities | Cramblet, Paul | Strategizing | 3 - Normal Queue | 3 - Medium | 2017-04-10 17:09 | If Warranty defects occur on one build and/or IOC defects occur on a second build, then development work on a third build may be temporarily suspended while prioritized defect repair activity monopolizes environment occupancy. | Any occurrence of IOC defects or Warranty defects whose specifics necessitate current build environment displacement or work suspension. | Accept | This risk is accepted, because environments are insufficient to support parallel tracks. Lack of funding is the underlying cause, and workable solutions are limited. There is a slim possibility of using Albany accounts for development and a single Bay Pines account CHY17 for defect repair, but availability will depend on the specifics of the ePharmacy situation and delivery status of the other three eBusiness VistA products. (CHY17 is shared across all four VistA products.) There is also a slim possibility for limited use of the UAT environment to test IOC defects, depending on timing of defect discovery and specifics of the current build. To minimize IOC and Warranty defects to the extent possible, any that occur will be evaluated to determine why the defect was not found prior to production. When cause is inadequate test case(s) or inadequate environment setup, corrective action will be immediately taken. When cause is a payer specific situation impossible to detect without end-to-end testing, the ongoing gap will be documented. | 2017-10-20 11:00
Risk | 498602 | eInsurance Parallel Activities | Cramblet, Paul | Strategizing | 3 - Normal Queue | 3 - Medium | 2017-04-10 17:09 | If Warranty defects occur on one build and/or IOC defects occur on a second build, then development work on a third build may be temporarily suspended while prioritized defect repair activity monopolizes environment occupancy. | Any occurrence of IOC defects or Warranty defects whose specifics necessitate current build environment displacement or work suspension. | Accept | This risk is accepted, because environments are insufficient to support parallel tracks. Lack of funding is the underlying cause, and workable solutions are limited. There is a slim possibility of using Albany accounts for development and a single Bay Pines account CHY17 for defect repair, but availability will depend on the specifics of the eInsurance situation and delivery status of the other three eBusiness VistA products. (CHY17 is shared across all four VistA products.) There is also a slim possibility for limited use of the UAT environment to test IOC defects, depending on timing of defect discovery and specifics of the current build. To minimize IOC and Warranty defects to the extent possible, any that occur will be evaluated to determine why the defect was not found prior to production. When cause is inadequate test case(s) or inadequate environment setup, corrective action will be immediately taken. When cause is a payer specific situation impossible to detect without end-to-end testing, the ongoing gap will be documented. | 2017-09-29 11:00
Risk | 498925 | MyVA Web-Based Access Requests | Cramblet, Paul | Strategizing | 3 - Normal Queue | 3 - Medium | 2017-04-11 13:42 | If the MyVA ePAS process does not work as communicated to preserve current VA access, then planned stripping of privileges granted via the old ePAS processes may bring development and testing activities to an abrupt halt. | VA Security stripping of current access privileges that result in lost access even though that access was requested and approved via new the MyVA ePAS single-request process. | Accept | The new process will be analyzed to document request guidelines for all users with access to the web-based architecture. Those users will be provided instructions to reapply for their access. Who has reapplied and whose requests are completed will be reported daily for progress assessment. High alert will be in effective as of the target stripping date to confirm access is uninterrupted and to escalate with urgency lost access should interruption occur. | 2017-05-01 11:00
Risk | 498618 | Testing Desktop Builds | Cramblet, Paul | Strategizing | 3 - Normal Queue | 3 - Medium | 2017-04-10 17:45 | If eAdministration builds cannot be tested on all valid VA desktop version and browser version combinations, then exhaustive GUI testing cannot be accomplished to ensure production processing defects do not result. | Any occurrence of an IOC defect or Warranty defect whose specifics reveal a desktop version or browser version anomaly which could not have been tested with available contractor GFEs. | Accept | This risk is accepted, because the variety of VA desktop builds in use cannot be made available to the testing team (who are allocated one GFE with a single desktop build). Allocating multiple GFEs to any single resource is not cost effective given the number of contractors still waiting for GFE assignment. To minimize the likelihood of production surprises, attempts will be made to recruit UAT and Pre-Prod business testers who have different desktop builds. Additionally, graphical features or application operation believed to be most susceptible will be noted for eBusiness team and field office awareness. Product defects will be analyzed to determine if untested desktop or browser versions were the cause. In those cases, effort will be made in the next build to recruit pre-prod testers with those same configurations. | 2017-09-29 11:00
Risk | 495956 | eAdmin VistA Data Access Dependency | Caneel, Glen J. (Leidos) | New | 4 - Low Priority | 4 - Low | 2017-04-10 12:23 | IF VistA Data Access (VDA) is dependent on the availability of VistA.js, THEN MCCF TAS will not be able to use VDA services. |  | Mitigate |  | 2017-04-10 11:00
Risk | 457341 | TAS VistA Access | Nichols, Terry A. (Leidos) | Executing | 3 - Normal Queue | 3 - Medium | 2017-02-01 14:31 | If access to the TAS VistA environments cannot be electronically controlled at the domain level, then those granted TAS VistA access will be able to log into TAS VistA domains not related to their project responsibilities, increasing potential for unplanned actions that necessitate recovery. | Inability to better regulate access by the start of Build 1 (not pilot build). | Mitigate | In addition to stipulating allowed access in the MCCF EDI TAS Test Policies & Practices, draft a Rules of Behavior document which all project members must sign. Routinely monitor access usage against authorized access, and immediately address violations. | 2017-04-28 11:00
Risk | 461739 | ePayments Accelerated Deployment | Cota-Robles, Curtis | New | 3 - Normal Queue | 3 - Medium | 2017-02-08 13:05 | If the development and release of the ePayments pilot user stories is accelerated by utilizing outdated test accounts, eliminating SQA testing and potentially reducing the IOC test period, then there is increased likelihood of production defects, potentially hindering the team’s availability to focus on first full-build development activities. | Inability to demonstrate code stability during CIT testing. | Accept | Ensure developers and CIT testers have access to needed environments well before the development cycle begins; escalate access issues if identified. Work with business to solidify and confirm functional requirements, as well as appropriate test cases to validate new functionality and preserve existing functionality. Include business representatives in early testing activities for continued awareness and feedback. Recruit test sites early to ensure IOC participants are prepared to execute tests on schedule without delays. Track IOC test progress on a daily basis to obviate end-of-cycle defect discovery. | 2017-06-21 11:00
Risk | 482214 | ePharmacy Sprint Regression Testing | Cramblet, Paul | Strategizing | 4 - Low Priority | 3 - Medium | 2017-04-11 13:33 | If CIT and SQA testing is limited to current sprint changes and does not include additional layers of regression to confirm earlier sprint work is unharmed, then the stabilization sprint may provide inadequate time before the build end date to repair and retest defects found as a result of all sprints finally being tested together. | Insufficient days remaining in the stabilization sprint to repair and retest identified defects. | Accept | No response plan is offered. Increasing layers of regression testing was intended to be a test practice, but was removed by testers with PM approval due to sprint time constraints. This accepted risk is logged for record and broader awareness of the potential project impact. | 2017-12-29 11:00
Risk | 466991 | eInsurance HL7 Message Approval | Gomez, Enrique | New | 2 - Give High Attention | 3 - Medium | 2017-03-01 08:03 | IF Outbound IIV Eligibility Request HL7 message (existing since 2002) is not formally approved by HL7 team by the start of Build 3 (Fall 2017), THEN we will not be able to proceed with development. | TBD and discussed at program meeting next week. | Mitigate |  | 2017-05-05 11:00
Risk | 480355 | MCCF EDI TAS FY18 Dev. Contract Funding | Rudik, Toby | New | 3 - Normal Queue | 3 - Medium | 2017-03-28 12:41 | IF the development contract funding for the MCCF EDI TAS program is not awarded and funded as requested for FY18 by 10/20/17, THEN the MCCF EDI TAS program will not have the required project resources necessary for completion and the Program's ability to deliver products satisfying adaptive maintenance, product backlog requirements will not be completed. Increasing the risk of the VA becoming subject to financial penalties and reducing third-party payment collections, both of which would result in an adverse impact to funding patient care delivery. | The Development contract funding is not awarded by 10/20/17, one month prior to end of PoP. | Mitigate | Work with OI&T and VHA Management to assure UFR requests are identified and prepared for the Account Manager to act upon in advance of any deadlines. | 2017-10-20 11:00
Risk | 482218 | ePayments Sprint Regression Testing | Cramblet, Paul | Strategizing | 4 - Low Priority | 3 - Medium | 2017-04-11 13:31 | If CIT and SQA testing is limited to current sprint changes and does not include additional layers of regression to confirm earlier sprint work is unharmed, then the stabilization sprint may provide inadequate time before the build end date to repair and retest defects found as a result of all sprints finally being tested together. | Insufficient days remaining in the stabilization sprint to repair and retest identified defects. | Accept | No response plan is offered. Increasing layers of regression testing was intended to be a test practice, but was removed by testers with PM approval due to sprint time constraints. This accepted risk is logged for record and broader awareness of the potential project impact. | 2017-12-29 11:00
Risk | 474780 | MCCF EDI TAS FY17 PMO Funding | Rudik, Toby | New | Unassigned | 2 - High | 2017-03-28 15:34 | IF the MCCF EDI TAS PMO is not funded as requested for FY17 by 8/23/17, THEN the project’s ability to deliver products satisfying adaptive maintenance, product backlog requirements will be degraded. Increasing the risk of the VA becoming subject to financial penalties and reducing third-party payment collections, both of which would result in an adverse impact to funding patient care delivery. |  | Mitigate | Work with OI&T and VHA Management to assure UFR requests are identified and prepared for the Account Manager to act upon in advance of any deadlines. | 2017-08-23 11:00
Risk | 482217 | eInsurance Sprint Regression Testing | Cramblet, Paul | Strategizing | 4 - Low Priority | 3 - Medium | 2017-04-11 13:32 | If CIT and SQA testing is limited to current sprint changes and does not include additional layers of regression to confirm earlier sprint work is unharmed, then the stabilization sprint may provide inadequate time before the build end date to repair and retest defects found as a result of all sprints finally being tested together. | Insufficient days remaining in the stabilization sprint to repair and retest identified defects. | Accept | No response plan is offered. Increasing layers of regression testing was intended to be a test practice, but was removed by testers with PM approval due to sprint time constraints. This accepted risk is logged for record and broader awareness of the potential project impact. | 2017-12-29 11:00
Risk | 412759 | R0007 - VIP Releases | Kutson, Stephanie Z. (Leidos) | Executing | 3 - Normal Queue | 2 - High | 2017-03-01 09:25 | If a defect is discovered during warranty and there is not a contingency plan in place to repair the defect without impacting builds in the release backlog, then a patch collision may occur and could nullify the readiness of patches in the release backlog. NOTE: This is the same risk that is encountered for all projects…having an environment available to fix warranty defects and handling patch collisions between code in development and warranty defect fixes that touch the same code. Still, it is important to document the risk. | Beginning a deployable build without the post-CD2 processes published and incorporated into the project schedule. | Mitigate | Updated 1/4/17: Mitigate - Document our processes in our SOP’s and refine them as we go through our production releases. The processes include the approach and timing for releasing builds to IOC and production. Strategy will also include environment options for repairing a production defect. All defects will be triaged to determine severity and priority. For lower severity or priority the defect will be fixed and released in next available build. For higher severity or priority a remediation build will be scheduled. | 2017-07-03 11:00
Risk | 498604 | ePayments Parallel Activities | Cramblet, Paul | Strategizing | 3 - Normal Queue | 3 - Medium | 2017-04-10 17:09 | If Warranty defects occur on one build and/or IOC defects occur on a second build, then development work on a third build may be temporarily suspended while prioritized defect repair activity monopolizes environment occupancy. | Any occurrence of IOC defects or Warranty defects whose specifics necessitate current build environment displacement or work suspension. | Accept | This risk is accepted, because environments are insufficient to support parallel tracks. Lack of funding is the underlying cause, and workable solutions are limited. There is a slim possibility of using Albany accounts for development and a single Bay Pines account CHY17 for defect repair, but availability will depend on the specifics of the ePayments situation and delivery status of the other three eBusiness VistA products. (CHY17 is shared across all four VistA products.) There is also a slim possibility for limited use of the UAT environment to test IOC defects, depending on timing of defect discovery and specifics of the current build. To minimize IOC and Warranty defects to the extent possible, any that occur will be evaluated to determine why the defect was not found prior to production. When cause is inadequate test case(s) or inadequate environment setup, corrective action will be immediately taken. When cause is a payer specific situation impossible to detect without end-to-end testing, the ongoing gap will be documented. | 2017-10-20 11:00
Risk | 490707 | eIns Resources & Capacity | Gomez, Enrique | New | 4 - Low Priority | 4 - Low | 2017-03-29 11:26 | IF there are not enough resources assigned to eInsurance product teams, and/or those who are assigned, do not have access/knowledge/skills/abilities, THEN it will be difficult to complete research, user stories, designs in a timely manner. |  | Mitigate |  | 2017-05-17 11:00
Risk | 467064 | eIns HL7 Mandatory Chgs to Message Structure | Gomez, Enrique | New | 2 - Give High Attention | 2 - High | 2017-03-29 10:23 | IF HL7 reports that they want us to change the existing message structure, that will lead to a whole new message structure, THEN that will create out of scope work and risk to production, which will lead to schedule slippage and additional development costs. This puts revenue operations at risk. |  | Mitigate | Mitigate - We may need to reverse engineer the message structure. Could use a blank Workbench Project then tweaked, FSC can provide samples to test engineering options. Require details; What are the milestones, when will the message be ready, who conducts the reviews, what is the 'actual' review/approval process. Will record a submittal and track. Jeff will reach out to Tim for timing details. | 2017-05-05 11:00
Risk | 412795 | R0014 - Ops Tempo | Rudik, Toby | Executing | 3 - Normal Queue | 3 - Medium | 2017-04-12 09:12 | If the backlog does not contain enough approved user stories to sustain steady development, then developers on the TAS T&M contract may be released to other billable projects. | Any time the backlog inventory is inadequate to begin the next build. | Mitigate | Leverage story points to determine the complexity of each build, especially the first. Track development progress against first build to determine a baseline speed at which team can deliver. Use first build track record and backlog complexity (story point total) to estimate how much work can be delivered in each build, allowing for expanded regression testing in each build. Ensure project backlog is always adequate to sustain a subsequent build before the current build completes. | 2017-05-10 11:00
Risk | 498689 | US198 Automatically create verification entry for future policies Design not approved | Gomez, Enrique | New | Unassigned | 2 - High | 2017-04-11 12:16 | If US198 Automatically create verification entry for future policies is not design approved by 4/10/17, then the build 2 contents are at risk of not being delivered. |  | Unassigned | Obtain design approval by 4/14/17. | 2017-04-14 11:00
Risk | 499461 | MyVA VistA Access Requests | Cramblet, Paul | Strategizing | 3 - Normal Queue | 3 - Medium | 2017-04-11 13:41 | If the MyVA ePAS process does not work as communicated to preserve current VA access, then planned stripping of privileges granted via the old ePAS processes may bring development and testing activities to an abrupt halt. | VA Security stripping of current access privileges that result in lost access even though that access was requested and approved via new the MyVA ePAS single-request process. | Accept | The new process will be analyzed to document request guidelines for all users with access to the VistA architecture. Those users will be provided instructions to reapply for their access. Who has reapplied and whose requests are completed will be reported daily for progress assessment. High alert will be in effective as of the target stripping date to confirm access is uninterrupted and to escalate with urgency lost access should interruption occur. | 2017-05-01 11:00
Risk | 482213 | eBilling Sprint Regression Testing | Cramblet, Paul | Strategizing | 4 - Low Priority | 3 - Medium | 2017-04-11 13:34 | If CIT and SQA testing is limited to current sprint changes and does not include additional layers of regression to confirm earlier sprint work is unharmed, then the stabilization sprint may provide inadequate time before the build end date to repair and retest defects found as a result of all sprints finally being tested together. | Insufficient days remaining in the stabilization sprint to repair and retest identified defects. | Accept | No response plan is offered. Increasing layers of regression testing was intended to be a test practice, but was removed by testers with PM approval due to sprint time constraints. This accepted risk is logged for record and broader awareness of the potential project impact. | 2017-12-29 11:00
Risk | 467033 | eIns VistA Tables & HL7 Approval | Gomez, Enrique | New | 3 - Normal Queue | 3 - Medium | 2017-03-06 07:57 | IF we go through this approval process and make required changes, and they (HL7 Approvals Team) reject the changes, THEN VistA will continue to contain tables that are out of sync with national standards resulting in additional costs for periodic updates. |  | Mitigate |  | 2017-05-05 11:00
Risk | 473160 | HL7 Message Approval | Mann, Julie R. (Leidos) | New | 3 - Normal Queue | 3 - Medium | 2017-03-29 10:05 | IF the need for HL7 approval and plan of obtaining the approval is not identified and laid out 6 months (2 full builds) prior to the required approval date, THEN there is risk of not obtaining approval due to the potential complexity of the activities, and the limited VA resources performing the HL7 review function. |  | Mitigate |  | 2017-05-05 11:00